## CR Effort
CR ID | Requested change | Scope basis | Estimated dev effort | Effort breakdown | Assumptions / dependencies
CR-01 | Extract passport-address PIN code from back-page scan; retain passport address as permanent address; allow a separate residence address; show the agency visa-submission jurisdiction. | Existing passport OCR extracts back-page address but no PIN; customer application captures passport address and residence data; no jurisdiction mapping exists. | 20–28 developer hours | OCR PIN extraction/validation and manual fallback: 5–7 h; separate address storage and API mapping: 4–5 h; jurisdiction rules and agency decision view: 5–8 h; customer form/UI: 3–4 h; integration and edge-case fixes: 3–4 h. | Estimate assumes an approved, current jurisdiction source for the relevant visa destinations/consulates and clear rule for using residence versus passport address. If PIN is unreadable or absent, collect it manually; do not infer jurisdiction from an uncertain scan.