## Sheet1
Requirement ID | Source Reference | Requirement Text | Feature/Page | Priority | Test Case IDs | Coverage Status | Execution Status | Defect IDs | Evidence Links | Notes
REQ-001 | /var/lib/qaagent/uploads/qa-20260523-210349/qaagent-functional-pm-requirements.md line 3 | An admin user can sign in, submit a QA run from the web form, see the created run in Test run history, and access report/log links for the requested run. | QA Agent web UI — Login, New test run, Test run history | High | TC-001, TC-002, TC-003, TC-004, TC-005, TC-006, TC-007, TC-008, TC-009 | Covered | Pass |  | screenshots/TC-001-pass-login-page-desktop.png, screenshots/TC-002-pass-invalid-login.png, screenshots/TC-003-pass-authenticated-dashboard.png, screenshots/TC-004-pass-required-field-validation.png, screenshots/TC-005-pass-create-run-submitted-desktop.png, screenshots/TC-006-pass-current-run-history-links.png, screenshots/TC-007-pass-current-run-report-opens.png, screenshots/TC-008-pass-current-run-logs-opens.png, screenshots/TC-009-pass-mobile-dashboard.png | All 9 planned UI test cases executed. Created run observed in history: qa-20260523-212010. Requested run checked: qa-20260523-210349.