## Sheet1
Execution ID | Test Case ID | Requirement ID | Environment | Browser/Device/Viewport | Executed At | Status | Actual Result | Evidence Path | Defect ID | Tester | Notes
EXE-001 | TC-001 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome desktop 1440x1000 | 2026-05-23T21:25:46Z | Pass | Unauthenticated visitors are directed to a simple QA Agent login screen with an admin password field and Login button. The page is visually minimal and understandable for an admin user. | screenshots/TC-001-pass-login-page-desktop.png |  | Hermes QA Agent acting as functional QA tester/product manager | Product observation: the password field uses placeholder text rather than a persistent visible label, which is understandable but less accessible.
EXE-002 | TC-002 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome desktop 1440x1000 | 2026-05-23T21:25:46Z | Pass | A wrong password is rejected and the user sees “Invalid password” with a “Try again” recovery link. | screenshots/TC-002-pass-invalid-login.png |  | Hermes QA Agent acting as functional QA tester/product manager | Safe negative test; no valid credential is shown or stored in artifacts.
EXE-003 | TC-003 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome desktop 1440x1000 | 2026-05-23T21:25:46Z | Pass | After valid login, the dashboard shows a New test run form and Test run history. Labels and buttons are understandable for creating and reviewing QA runs. | screenshots/TC-003-pass-authenticated-dashboard.png |  | Hermes QA Agent acting as functional QA tester/product manager | The UI feels functional and compact for an internal QA admin tool.
EXE-004 | TC-004 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome desktop 1440x1000 | 2026-05-23T21:25:46Z | Pass | The blank form does not submit. Browser validation tells the user: “Please fill out this field.”. | screenshots/TC-004-pass-required-field-validation.png |  | Hermes QA Agent acting as functional QA tester/product manager | Validation is browser-native rather than an inline product message; it is still understandable for a smoke flow.
EXE-005 | TC-005 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome desktop 1440x1000 | 2026-05-23T21:25:46Z | Pass | The submitted QA run appears in Test run history for project “qaagent-functional-pm-qa-ui-create-test” and target “https://qa.winds-os.com/health”. Visible run ID: qa-20260523-212527. | screenshots/TC-005-pass-create-run-submitted-desktop.png |  | Hermes QA Agent acting as functional QA tester/product manager | This confirms the core create-run happy path through the web UI.
EXE-006 | TC-006 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome desktop 1440x1000 | 2026-05-23T21:25:46Z | Pass | The requested run qa-20260523-211154 is visible in Test run history and exposes both Report and Logs links. Row shown to the user: qa-20260523-211154 qaagent-functional-pm-qa-ui-create-test https://qa.winds-os.com/health running Report Logs 2026-05-23T21:11:54Z. | screenshots/TC-006-pass-current-run-history-links.png |  | Hermes QA Agent acting as functional QA tester/product manager | This is the direct acceptance check for the user-provided run ID and scope.
EXE-007 | TC-007 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome desktop 1440x1000 | 2026-05-23T21:25:46Z | Pass | The Report link opens a browser-readable report location for the requested run: https://files.winds-os.com/qaagent-functional-pm-qa-ui-create-test/qa-20260523-211154/. HTTP status observed during execution: 200. | screenshots/TC-007-pass-current-run-report-opens.png |  | Hermes QA Agent acting as functional QA tester/product manager | The hosted dashboard for this run is verified again after publishing.
EXE-008 | TC-008 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome desktop 1440x1000 | 2026-05-23T21:25:46Z | Pass | The Logs link opens readable run logs for qa-20260523-211154; the page returns HTTP 200 and displays log text. | screenshots/TC-008-pass-current-run-logs-opens.png |  | Hermes QA Agent acting as functional QA tester/product manager | Log contents are not copied into the report to avoid exposing operational details.
EXE-009 | TC-009 | REQ-001 | Production-like QA web UI at https://qa.winds-os.com, target health endpoint https://qa.winds-os.com/health | Chrome emulated iPhone 12 mobile viewport | 2026-05-23T21:25:46Z | Pass | On a mobile-width viewport, the create-run form and history section remain reachable. The history table is dense and would be easier as mobile cards, but the flow is usable for smoke review. | screenshots/TC-009-pass-mobile-dashboard.png |  | Hermes QA Agent acting as functional QA tester/product manager | Product observation: history table is functional but not optimized for small screens.