## Sheet1
Execution ID | Test Case ID | Requirement ID | Environment | Browser/Device/Viewport | Executed At | Status | Actual Result | Evidence Path | Defect ID | Tester | Notes
EXE-001 | TC-001 | REQ-001 | https://qa.winds-os.com/ (desktop Chromium 1366x900 and mobile Chromium 390x844) | Desktop Chromium 1366x900 | 2026-05-23T21:32:50Z | Pass | Invalid password. Try again | screenshots/TC-001-pass-invalid-login.png |  | Hermes QA Agent functional QA persona | Product-facing UI test executed through browser. No credentials captured.
EXE-002 | TC-002 | REQ-001 | https://qa.winds-os.com/ (desktop Chromium 1366x900 and mobile Chromium 390x844) | Desktop Chromium 1366x900 | 2026-05-23T21:32:50Z | Pass | Dashboard opened after login. Visible sections/text: New test run, Target URL, Requirement doc, Create QA Run, Test run history, Report, Logs | screenshots/TC-002-pass-desktop-dashboard.png |  | Hermes QA Agent functional QA persona | Product-facing UI test executed through browser. No credentials captured.
EXE-003 | TC-003 | REQ-001 | https://qa.winds-os.com/ (desktop Chromium 1366x900 and mobile Chromium 390x844) | Desktop Chromium 1366x900 | 2026-05-23T21:32:50Z | Pass | Browser validation prevented submission and reported: [{"name":"target_url","message":"Please fill out this field."},{"name":"requirements","message":"Please select a file."}] | screenshots/TC-003-pass-required-field-validation.png |  | Hermes QA Agent functional QA persona | Product-facing UI test executed through browser. No credentials captured.
EXE-004 | TC-004 | REQ-001 | https://qa.winds-os.com/ (desktop Chromium 1366x900 and mobile Chromium 390x844) | Desktop Chromium 1366x900 | 2026-05-23T21:32:50Z | Pass | After form submission, the newest history row displayed: qa-20260523-213013 qaagent-functional-pm-qa-ui-create-test https://qa.winds-os.com/health queued — — 2026-05-23T21:30:13Z | screenshots/TC-004-pass-create-run-history.png |  | Hermes QA Agent functional QA persona | Product-facing UI test executed through browser. No credentials captured.
EXE-005 | TC-005 | REQ-001 | https://qa.winds-os.com/ (desktop Chromium 1366x900 and mobile Chromium 390x844) | Desktop Chromium 1366x900 | 2026-05-23T21:32:50Z | Fail | Newest run row after waiting: qa-20260523-213013 qaagent-functional-pm-qa-ui-create-test https://qa.winds-os.com/health queued — — 2026-05-23T21:30:13Z . Links visible: [{"text":"https://qa.winds-os.com/health","href":"https://qa.winds-os.com/health"}] | screenshots/TC-005-fail-report-log-links.png | DEF-001 | Hermes QA Agent functional QA persona | Product-facing UI test executed through browser. No credentials captured.
EXE-006 | TC-006 | REQ-001 | https://qa.winds-os.com/ (desktop Chromium 1366x900 and mobile Chromium 390x844) | Mobile Chromium 390x844 | 2026-05-23T21:32:50Z | Pass | Mobile dashboard loads and retains the create form and history sections. Horizontal scrolling may be needed for the history table on a phone-sized screen. | screenshots/TC-006-pass-mobile-dashboard.png |  | Hermes QA Agent functional QA persona | Product-facing UI test executed through browser. No credentials captured.