## Sheet1
Requirement ID | Source Reference | Requirement Text | Feature/Page | Priority | Test Case IDs | Coverage Status | Execution Status | Defect IDs | Evidence Links | Notes
REQ-001 | qaagent-functional-pm-requirements.md: line 11 | Unauthenticated access should lead users to a clear login page with understandable purpose, password field, and login action. | Login | High | TC-001 | Covered | Pass | — | screenshots/TC-001-pass-login-page.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-002 | qaagent-functional-pm-requirements.md: line 13 | Negative login: entering an incorrect password should not open the dashboard and should show a clear error/recovery path. | Login | High | TC-002 | Covered | Fail | DEF-001 | screenshots/TC-002-fail-invalid-login-error-page.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-003 | qaagent-functional-pm-requirements.md: line 15 | Positive login: entering the configured admin password should open the dashboard and show that the user is signed in. | Login | High | TC-003 | Covered | Pass | — | screenshots/TC-003-pass-dashboard-desktop.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-004 | qaagent-functional-pm-requirements.md: line 17 | Dashboard visual quality: the page should look polished and understandable on desktop, with readable labels, spacing, contrast, and clear sections for creating a run, history, and API information. | Dashboard | High | TC-004 | Covered | Pass | — | screenshots/TC-003-pass-dashboard-desktop.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-005 | qaagent-functional-pm-requirements.md: line 19 | Dashboard form comprehension: a non-technical user should understand required inputs: target URL, project name, current feature/scope, requirement document upload, optional test cases upload, and create action. | Create run form | High | TC-005 | Covered | Fail | DEF-002 | screenshots/TC-006-pass-create-form-ready.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-006 | qaagent-functional-pm-requirements.md: line 21 | Negative create-run flow: attempting to create a run without required fields or required document should prevent submission and guide the user through visible browser/app validation. | Create run form | High | TC-006 | Covered | Pass | — | screenshots/TC-004-pass-empty-form-target-validation.png; screenshots/TC-005-pass-required-doc-validation.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-007 | qaagent-functional-pm-requirements.md: line 23 | Positive create-run flow: using valid URL, project name, scope, and requirements upload should create a new QA run and show it in run history with queued/running/completed status. | Create run form / history | Critical | TC-007 | Covered | Pass | — | screenshots/TC-007-pass-created-run-in-history.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-008 | qaagent-functional-pm-requirements.md: line 25 | Run history usability: the history table should make it easy to understand each run’s ID, project, target URL, status, report link, logs link, created time, and any error. | Run history | High | TC-008 | Covered | Pass | — | screenshots/TC-003-pass-dashboard-desktop.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-009 | qaagent-functional-pm-requirements.md: line 27 | Report navigation: clicking a completed run’s Report link should open a hosted QA dashboard rather than a broken/missing page. | Report navigation | High | TC-009 | Covered | Pass | — | screenshots/TC-008-pass-report-dashboard.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-010 | qaagent-functional-pm-requirements.md: line 29 | Logs navigation: clicking Logs should show readable execution logs without exposing secrets. | Logs | High | TC-010 | Covered | Pass | — | screenshots/TC-009-pass-readable-logs-no-secrets.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-011 | qaagent-functional-pm-requirements.md: line 31 | Responsive UI: the dashboard/login experience should remain usable on a mobile viewport. | Responsive UI | High | TC-011 | Covered | Fail | DEF-003 | screenshots/TC-010-pass-mobile-login-responsive.png | Executed through browser UI; API/log checks used only as supporting evidence.
REQ-012 | qaagent-functional-pm-requirements.md: line 33 | Product-manager assessment: the QA report should include screenshots/evidence for tested UI states and explain results in plain product/user language, not only technical API checks. | QA report | High | TC-012 | Covered | Pass | — | screenshots/TC-001-pass-login-page.png; screenshots/TC-002-fail-invalid-login-error-page.png; screenshots/TC-003-pass-dashboard-desktop.png; screenshots/TC-004-pass-empty-form-target-validation.png; screenshots/TC-005-pass-required-doc-validation.png; screenshots/TC-006-pass-create-form-ready.png; screenshots/TC-007-pass-created-run-in-history.png; screenshots/TC-008-pass-report-dashboard.png; screenshots/TC-009-pass-readable-logs-no-secrets.png; screenshots/TC-010-pass-mobile-login-responsive.png | Executed through browser UI; API/log checks used only as supporting evidence.