## Sheet1
Execution ID | Test Case ID | Requirement ID | Environment | Browser/Device/Viewport | Executed At | Status | Actual Result | Evidence Path | Defect ID | Tester | Notes
EXE-001 | TC-001 | REQ-001 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | Login page is branded, centered, and clearly states “Sign in to create and review QA runs.” Password field and Login button are visible. | screenshots/TC-001-pass-login-page.png | — | Hermes QA Agent | Login page is simple and understandable.
EXE-002 | TC-002 | REQ-002 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Fail | Incorrect password does block access, but the user is sent to a plain unbranded white error page with only “Invalid password. Try again”. This is a recovery path but feels unfinished and less trustworthy than an in-page product error. | screenshots/TC-002-fail-invalid-login-error-page.png | DEF-001 | Hermes QA Agent | Product-facing recovery needs polish.
EXE-003 | TC-003 | REQ-003 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | Configured admin password opened the dashboard and showed a Logout link, confirming signed-in state. | screenshots/TC-003-pass-dashboard-desktop.png | — | Hermes QA Agent | Credential value was not recorded in artifacts.
EXE-004 | TC-004 | REQ-004 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | Desktop dashboard uses a polished dark theme, readable headings, clear cards, and understandable sections for New test run, Test run history, and API. | screenshots/TC-003-pass-dashboard-desktop.png | — | Hermes QA Agent | Some API/error wording is technical but layout is strong.
EXE-005 | TC-005 | REQ-005 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Fail | The form labels are understandable, but the Requirement doc is mandatory and not visually marked as required before submission. File upload controls have no helper text about accepted files or what the document should include. | screenshots/TC-006-pass-create-form-ready.png | DEF-002 | Hermes QA Agent | Non-technical users may not know the document is required until after an error.
EXE-006 | TC-006 | REQ-006 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | Empty form submission is blocked with browser validation for Target URL. Submitting without a requirement file is also blocked with “Please select a file.” Validation is visible and prevents accidental submission. | screenshots/TC-004-pass-empty-form-target-validation.png; screenshots/TC-005-pass-required-doc-validation.png | — | Hermes QA Agent | Validation works but relies on browser-native messages.
EXE-007 | TC-007 | REQ-007 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | A valid UI submission created run qa-20260523-201713 and placed it at the top of history with status queued. Report/log links were not yet available while queued, which is understandable. | screenshots/TC-007-pass-created-run-in-history.png | — | Hermes QA Agent | End-to-end create action reached the expected history outcome.
EXE-008 | TC-008 | REQ-008 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | History table shows run ID, project, URL, status, report, logs, created time, and error. Status colors help scanning. Existing failed run error is technical, but the table is usable. | screenshots/TC-003-pass-dashboard-desktop.png | — | Hermes QA Agent | Consider friendlier error summaries later.
EXE-009 | TC-009 | REQ-009 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | Completed run Report opened a hosted Client Acceptance QA Dashboard with summary cards, requirement/test tables, evidence gallery, defects section, and downloads. | screenshots/TC-008-pass-report-dashboard.png | — | Hermes QA Agent | Hosted report was usable.
EXE-010 | TC-010 | REQ-010 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | Logs page displayed readable run output and did not visibly expose passwords, API keys, tokens, cookies, or authorization headers. | screenshots/TC-009-pass-readable-logs-no-secrets.png | — | Hermes QA Agent | Logs are plain text and readable.
EXE-011 | TC-011 | REQ-011 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Fail | On a 390x844 mobile viewport, the login card is horizontally clipped on the right edge. The input and button are usable but the page does not fit cleanly within the viewport, reducing confidence on mobile. | screenshots/TC-010-pass-mobile-login-responsive.png | DEF-003 | Hermes QA Agent | Mobile responsiveness needs correction.
EXE-012 | TC-012 | REQ-012 | QA web app at https://qa.winds-os.com | Desktop Chromium via browser QA; TC-011 mobile Chrome headless 390x844 | 2026-05-23T20:21:59Z | Pass | This QA package includes traceability, test cases, execution results, defects, summary, hosted HTML, and screenshot evidence for each executed UI test case, written in product-facing language. | screenshots/TC-001-pass-login-page.png; screenshots/TC-002-fail-invalid-login-error-page.png; screenshots/TC-003-pass-dashboard-desktop.png; screenshots/TC-004-pass-empty-form-target-validation.png; screenshots/TC-005-pass-required-doc-validation.png; screenshots/TC-006-pass-create-form-ready.png; screenshots/TC-007-pass-created-run-in-history.png; screenshots/TC-008-pass-report-dashboard.png; screenshots/TC-009-pass-readable-logs-no-secrets.png; screenshots/TC-010-pass-mobile-login-responsive.png | — | Hermes QA Agent | Artifact verification completed before final response.