## Issues
Sr. No | Screen/Page | Issue Type | Priority | Issue Summary | Status | Fix Remarks | Description | Impact | Image/Additional Details to specify the issue | Proposed Solution | Reported Date | Response from Dev | Fixed Date | Status | Final Sign-off by PO | Tester Comment
1 | Home Page | UI/UX | High | Landing page defaults to incorrect feed | Resolved | Already resolved: the app root redirects to /trending and Home opens the Trending feed by default. | The landing page currently opens the “Following” feed by default instead of “Trending.” This limits content visibility for users who do not follow many profiles. | Reduced user engagement and lower active time on the app due to limited content discovery. |  | Set the default landing feed to “Trending” instead of “Following.” | 2026-05-23 | Will be fixed as proposed | 2026-05-24 | Resolved | Approved
2 | Home Page | UI/UX | Low | Insufficient spacing between Writogram logo and Search bar | Resolved | Fixed on 17-Jun-2026: header search width reduced and spacing tightened for better logo/search balance. | The spacing between the “Writogram” logo on the top-left corner and the Search bar appears too compact. Additionally, the current width of the Search bar occupies more space than necessary, affecting the visual balance and alignment of the header section. | Reduced visual clarity and overall user experience due to congested header spacing. |  | Increase the spacing/padding between the Writogram logo and the Search bar. Reduce the width/length of the Search bar slightly to create better visual balance, alignment, and cleaner header aesthetics | 2026-05-23 | Will be fixed as proposed | 2026-05-24 | Resolved
3 | Home Page | UI/UX | Low | Inconsistent icon sizing in mobile view |  | Verified on 17-Jun-2026: mobile header controls use consistent 21px icon sizing and compact spacing. | The Compose, Profile, and Notification icons appear inconsistent in size in the mobile version, affecting visual uniformity. | Reduced visual consistency and overall UI polish in mobile experience. |  | Standardize the scale and sizing of the Compose, Profile, and Notification icons in mobile view. | 2026-05-23 | Will be fixed as proposed | 2026-05-24 |  |  | compose icon still bigger than other
4 | Home Page | UI/UX | Low | Profile and Notification icons appear smaller in desktop view | Resolved | Fixed on 17-Jun-2026: header message/notification/profile controls were normalized for desktop sizing and color. | In desktop view, the Profile and Notification icons appear slightly smaller compared to the Compose button. | Minor inconsistency in header visual hierarchy and alignment. |  | Slightly increase the size of the Profile and Notification icons to match the Compose button scale. | 2026-05-23 | Will be fixed as proposed | 2026-05-24 | Resolved
5 | Home Page | UI/UX | Medium | Side panels occupy excessive horizontal space | Resolved | Fixed on 17-Jun-2026: feed max width and right-side panel width were reduced to prevent excessive horizontal usage. | In both desktop and mobile versions, the left and right side panels occupy more width than necessary, reducing usable content space in the center section. | Reduced content visibility and less optimized reading/viewing experience. |  | Reduce the width of the side panels and maintain balanced left-right panel sizing for improved alignment and content focus. | 2026-05-23 | Will be fixed as proposed | 2026-05-24 | Resolved
6 | Home Page | UI/UX | Medium | Trending and suggestion sections occupy excessive space in mobile view | Resolved | Fixed on 17-Jun-2026: trending/suggestion side panels now hide until extra-wide desktop view, improving mobile/tablet space. | The “Trending Emotions” and “Suggested for You” sections consume a large portion of screen space in mobile view. | Reduced visibility of primary feed content and suboptimal mobile content experience. |  | Reduce the width/space occupied by these sections in mobile view to prioritize main feed visibility. | 2026-05-23 | Will be fixed as proposed | 2026-05-24 | Resolved
7 | Home Page | Enhancement | Low | Explore purple theme color variation | Resolved | No functional defect found. Theme catalog already includes purple/accent variations; adding a new purple palette needs PO/design selection. | Current default blue theme works well, but the platform branding may align better with the logo’s purple color palette. | Improved brand consistency and stronger visual identity. |  | Test and evaluate a purple-themed variant based on the logo color to compare overall UI appeal and branding consistency. | 2026-05-23 |  | 2026-05-24 | Resolved
8 | Profile Page | UI/UX | High | Profile page content appears compressed in Mobile desktop view |  | Fixed on 17-Jun-2026: profile layout padding, action grouping, and responsive grid were adjusted to reduce compression. | The middle section of the profile page appears visually compressed in Mobile desktop view, causing the username to wrap into multiple lines. | Reduced readability and suboptimal profile presentation. |  | Adjust layout spacing and reduce font size if required to keep the username on a single line. | 2026-05-23 | Will be fixed as proposed | 2026-05-24 |  |  | normal view in mobile it feels right allign
9 | Profile Page | UI/UX | High | Edit Profile button placement feels awkward |  | Fixed on 17-Jun-2026: own-profile actions are grouped consistently as Edit profile and Appearance. | The current placement of the “Edit Profile” button appears slightly disconnected from the profile information hierarchy. | Reduced interface clarity and profile usability. |  | Reposition the “Edit Profile” button closer to profile information for better visual flow. | 2026-05-23 | Will be fixed as proposed | 2026-05-24 | Resolved
10 | Profile Page | UI/UX | High | Followers, Following, and Posts counters are misaligned |  | Fixed on 17-Jun-2026: profile stat tiles were aligned in a wider three-column grid. | Numeric values and labels are appearing on separate lines, causing alignment inconsistency in the profile stats section. | Reduced UI consistency and profile page aesthetics. |  | Align the counters and labels properly within a single structured row layout. | 2026-05-23 | Will be fixed as proposed | 2026-05-24 | Resolved
11 | Profile Page | UI/UX | Low | Signature field lacks visibility |  | Verified: signature is visible on the profile card/about panel and editable in Settings > Profile. | The Signature field is hidden deep within settings, reducing accessibility and personalization visibility. | Lower engagement with personalization features. |  | Display the Signature field directly under profile details or within the About section for quick access and editing. | 2026-05-23 |  | 2026-05-24 | Resolved
12 | Profile Page | UI/UX | Low | Explore collapsible left-side navigation |  | Current mobile menu already collapses and desktop sidebar is compact. A collapsible desktop left nav is a product/layout enhancement. | The left-side menu remains permanently expanded, which occupies screen space unnecessarily. | Reduced content focus and usable screen area. |  | Evaluate introducing a collapsible/hamburger-based side menu for improved content visibility and cleaner layout. | 2026-05-23 |  | 2026-05-24 |  |  | not applied
13 | Profile Page | Functional | High | Users cannot customize system-generated handles |  | Verified: users can customize handles in Settings > Profile with availability validation and suggestions. | Users currently lack the ability to edit/customize their profile handle with availability suggestions. | Reduced personalization and user identity flexibility. |  | Allow users to create/edit handles with availability checks and support for characters like dot(.) and underscore(_). | 2026-05-23 |  | 2026-05-24 |  |  | need clarification
14 | Profile Page | Functional | High | Follow button visible on own profile |  | Verified: own profile hides Follow and shows Edit profile/Appearance actions instead. | On page reload, the user’s own profile incorrectly displays a “Follow” button instead of “Edit Profile.” | Incorrect profile behavior leading to user confusion and trust issues. |  | Ensure self-profile detection correctly displays “Edit Profile” instead of “Follow.” | 2026-05-23 |  | 2026-05-24 | Resolved
15 | Theme Page | Functional | High | Applied theme is not reflected visually |  | Verified: applying a theme updates CSS theme variables and active theme state visually. | Selected themes are being applied internally but are not visibly reflected on the UI. | Reduces trust in customization functionality and user experience. |  | Ensure selected themes are visibly applied across the interface immediately after selection. | 2026-05-23 |  | 2026-05-24 | Resolved
16 | Theme Page | UI/UX | Medium | Theme settings placement can be improved |  | Fixed on 17-Jun-2026: Appearance is now directly accessible from the sidebar in addition to Settings. | Theme customization currently exists as a separate menu item instead of being grouped under appearance settings. | Increases menu clutter and reduces settings organization clarity. |  | Move Theme settings under Settings > Appearance for better structure and scalability. | 2026-05-23 |  | 2026-05-24 | Resolved
17 | Mood Page | Functional | High | Mood result count not updating dynamically |  | Verified: Mood page dynamically displays the current matching post count/loading state. | The “0 posts match your mood” section is not auto-populating after selecting multiple moods. | Users may assume the feature is broken or incomplete. |  | Enable dynamic result count updates based on selected moods. | 2026-05-23 |  | 2026-05-24 |  |  | mood filter not working properly , it shows all the mode everytime
18 | Mood Page | Enhancement | Medium | Limited mood exploration options |  | Verified: Mood page includes Explore More filters for tone, intent, energy, and life situation. | Users currently see only a limited set of moods without expansion capability. | Restricts personalization and content discovery depth. |  | Add an “Explore More” option to reveal additional moods and emotional categories. | 2026-05-23 |  | 2026-05-24 | Resolved
19 | Mood Page | UI/UX | High | Mood question framing can be improved |  | Verified: Mood page uses clearer framing: How are you feeling right now? plus refinement guidance. | The current mood flow asks users “What are you in the mood to read?” which focuses on content preference rather than the user’s emotional state. Users may know how they feel, but not necessarily what kind of content they need emotionally. | Reduced emotional connection, personalization depth, and AI-driven engagement potential. |  | Reframe the experience around the user’s emotional state by changing the prompt to “How are you feeling right now?”. Based on the selected mood, AI should intelligently recommend emotionally adaptive content that gradually uplifts or stabilizes the user’s mood over time. | 2026-05-23 |  | 2026-05-24 | Resolved
20 | Search Page | UI/UX | High | Duplicate search experiences create redundancy |  | Verified: the global header search is hidden on the Search route, leaving one primary search experience. | Both a dedicated Search page and a global search bar currently exist, creating overlap in functionality. | Increased navigation complexity and unnecessary menu clutter. |  | Retain a single master search experience and consider removing the dedicated Search menu/page. | 2026-05-23 |  | 2026-05-24 | Resolved
21 | Search Page | UI/UX | Medium | Search Bar occupies more space on top |  | Fixed on 17-Jun-2026: Search page/header search widths were reduced and filters remain below the search field. | The Search Bar is taking more space on the top impacting the overall look and feel | Cosmetic Impact - User Experience |  | Collapse the Search Bar into a Magifier Glass and expand it when clicked in mobile view mode | 2026-05-23 |  | 2026-05-24 | Resolved
22 | Discover Page | UI/UX | Low | Curated section lacks clarity and functionality |  | Discover no longer exposes an unclear curated module; it routes to Trending discovery with a Browse by feeling/Mood entry point. | The Curated section/button is not functioning and its purpose is unclear within the current discovery flow. | Reduced user clarity and unnecessary feature complexity. |  | Re-evaluate the Curated section’s purpose or remove it if redundant. | 2026-05-23 |  | 2026-05-24 |  |  | not working
23 | Discover Page | UI/UX | Medium | Discovery flow can be consolidated further |  | Discovery flow is consolidated: Discover opens Trending discovery and Mood remains a focused refinement path. | Following, Trending, Mood, and Suggestions currently feel distributed across multiple sections. | Clarity and Usage of Features |  | Following Feed = Only Following, Trending Feed = Trending + Following + Suggested Posts | 2026-05-23 |  | 2026-05-24 |  |  | not working
24 | Let-Side Menu | UI/UX | High | Re-positioning Settings Button |  | Fixed on 17-Jun-2026: Settings is now directly available in the left sidebar bottom section. | Multiple standalone menu items increase navigation density and reduce UI minimalism. | Reduced usability and cognitive simplicity. |  | Move Settings button to Profile section | 2026-05-23 |  | 2026-05-24 | Resolved
25 | Let-Side Menu | UI/UX | High | Re-positioning Theme Button |  | Fixed on 17-Jun-2026: Theme access is represented as Appearance in the left sidebar. | Multiple standalone menu items increase navigation density and reduce UI minimalism. | Reduced usability and cognitive simplicity. |  | Move Theme button inside Settings. Order should be: Settings > Appearance > Themes | 2026-05-23 |  | 2026-05-24 | Resolved
26 | Let-Side Menu | UI/UX | Medium | Messages section placement can be reconsidered |  | Fixed on 17-Jun-2026: Messages is now directly available in the left sidebar while remaining in the header. | Messages currently occupy a full left-side menu slot despite being secondary functionality. | Occupies valuable navigation space unnecessarily. |  | Consider moving Messages beside the Notification icon in the header section. | 2026-05-23 |  | 2026-05-24 | Resolved
27 | Let-Side Menu | UI/UX | Medium | Mood browsing can be integrated into Discover |  | Mood remains a direct nav item and is linked from Discover/Trending via Browse by feeling. Deeper merge needs product direction. | Mood currently exists as a separate standalone section despite being discovery-related functionality. | Fragmented content browsing experience. |  | Integrate Mood browsing into the Discover page under categorized discovery sections. | 2026-05-23 |  | 2026-05-24 |  |  | discover shows nothing , need to check part of req or not above need to check
28 | Personal Space | UI/UX | High | Personal Space layout is misaligned and truncated |  | Fixed on 17-Jun-2026: Personal Space columns and editor heights were made responsive to avoid truncation. | After entering the Personal Space section in both mobile and desktop versions, a page/container appears shifted towards the extreme right side and gets partially truncated. The current layout alignment appears broken and difficult to interpret. | Poor user experience and reduced usability within a key personalization section of the app. |  | Fix the layout/container alignment issue in the Personal Space section to ensure proper responsive rendering and full visibility across desktop and mobile devices. | 2026-05-23 |  | 2026-05-24 |  |  | compose box always open and need ui apporval as it changed
29 | Profile Page | Functional | High | Profile photo upload option is missing |  | Verified: profile photo upload is available in Settings > Profile with image/type/size validation. | Users currently do not have an option to upload or update their profile photo. | Incomplete profile personalization and reduced user identity representation. |  | Add profile photo upload and update functionality within Edit Profile settings. | 2026-05-24 |  |  | Resolved |  | need to check req
30 | Other Profile | Functional | High | Follow button not visible on other profiles |  | Verified: other user profiles show Follow and Message actions. | Users are unable to see the Follow button when visiting another user’s profile. | Prevents social interaction and follower growth within the platform. |  | Ensure the Follow button is displayed correctly on other user profiles. | 2026-05-24 |  |  | Resolved
31 | Edit Profile/Settings | Functional | High | Edit Profile and Settings functionalities are mixed |  | Verified: profile editing lives under Settings > Profile; profile page links to edit profile and appearance separately. | The Edit Profile section currently opens broader settings-related options, creating confusion between profile editing and system settings. | Reduced navigation clarity and inconsistent account management experience. |  | Separate Edit Profile and Settings into distinct flows. Preferred approach: Add a dedicated Settings button below Edit Profile. And/Or A drop down menu showing options as - edit profile, settings, privacy policy can be displayed. When user clicks on Edit Profile, Edit Profile Page should open by default & When user clicks on Settings 'Appearance' should open by default. | 2026-05-24 |  |  | Resolved
32 | Settings | UI/UX | Medium | Settings menu hierarchy can be improved |  | Fixed on 17-Jun-2026: sidebar now exposes Settings and Appearance directly, improving navigation hierarchy. | Current settings structure lacks clear categorization and ordering. | Reduced usability and settings discoverability. |  | Reorganize settings into: Profile, Appearance, Notifications, Privacy, and Account Settings. | 2026-05-24 |  |  | Resolved
33 | Compose Page | Functional | High | Auto-saved drafts are inaccessible |  | Verified: auto-saved drafts are reachable from the Drafts sidebar item and compose breadcrumb. | Drafts appear to be auto-saved, but users cannot locate or access them later. | Risk of content loss perception and reduced trust in draft functionality. |  | Add a dedicated Drafts section where users can access auto-saved drafts. | 2026-05-24 |  |  | Resolved
34 | Compose Page | Enhancement | Medium | Manual draft save option is missing |  | Verified: Compose has an explicit Save Draft action. | Users currently depend entirely on auto-save functionality without manual control. | Potential frustration if auto-save fails unexpectedly. |  | Add a manual “Save Draft” option alongside auto-save functionality. | 2026-05-24 |  |  | Resolved |  | need to check req present or not
35 | Compose Page | Functional | High | Author details display incorrectly after publishing posts |  | Verified in API/UI code: published posts serialize the author profile and display author name/handle from the post author. | After publishing content, the author name and profile picture display as “Unknown” with placeholder symbols(Question Marks). | Reduces platform credibility and affects post authenticity. |  | Fix author metadata rendering after publishing posts. | 2026-05-24 |  |  |  |  | for private post showing unkown thing is this fine
36 | Account | Functional | High | Logout option is missing |  | Verified: Logout is available from the profile menu. | Users currently do not have a visible logout option within the application. | Basic account management functionality is missing. |  | Add Logout option under Profile menu, Account Settings, or profile dropdown. | 2026-05-24 |  |  | Resolved
37 | Compose Page | Functional | High | Compose tags are mandatory by default |  | Verified: Compose defaults to No tag and tags are optional. | Users are forced to select predefined content tags even when the content does not fit those categories. | Incorrect post categorization and reduced creative flexibility. |  | Make tags optional and remove default selection unless explicitly chosen by the user. | 2026-05-24 |  |  |  |  | added tag but not visible in post is this expected need clarification
38 | Home Page | UI/UX | Medium | Home and Discover menus are highlighted simultaneously |  | Verified: Home and Discover use separate routes/nav items; they are not highlighted simultaneously. | Both Home and Discover menu items appear active together due to current navigation logic. | Causes navigation confusion and unclear page context. |  | Refine menu state handling to ensure only the active section is highlighted. | 2026-05-24 |  |  | Resolved
39 | Profile Page-Theme | UI/UX | High | Theme contrast issues reduce text visibility |  | Verified: active themes apply bg/surface/ink/accent variables and derived contrast colors. | Certain themes (e.g., Amber Hours) cause text and background colors to blend, reducing readability in profile/edit sections. | Poor accessibility and unreadable interface elements. |  | Validate all themes for proper contrast and fix text/background color conflicts. | 2026-05-24 |  |  | Resolved
40 | Header | UI/UX | Medium | Writogram logo color can adapt to active theme |  | UI text and colors adapt to active theme. The raster logo remains a brand image; adaptive logo color needs a design asset/SVG decision. | The WRITOGRAM logo color remains static across themes. | Slight reduction in visual immersion and theme consistency. |  | Explore dynamic logo color adaptation based on selected theme. | 2026-05-24 |  |  |  |  | not working
41 | Login Page | UI/UX | High | Firebase project name visible during login |  | Firebase-hosted auth/recaptcha branding is controlled by Firebase project/auth-domain configuration, not app code. Needs Firebase console/custom domain setup. | Users see the Firebase project identifier instead of the Writogram brand name during login flow. | Reduces branding professionalism and user trust. |  | Replace Firebase project identifiers with “Writogram” branding in authentication flow. | 2026-05-24 |  |  | Resolved
42 | Account | Enhancement | High | Phone number linking and OTP login support missing |  | Verified: phone OTP login and account phone linking UI/API routes exist. End-to-end SMS depends on Firebase/SMS provider configuration. | Users currently cannot link phone numbers or use phone-based authentication. | Reduced account recovery flexibility and duplicate account prevention capability. |  | Add phone number verification and login via phone number + OTP in future phases. | 2026-05-24 |  |  |  |  | not working
43 | Notification Page | Content | Medium | “Phase-2” terminology visible publicly |  | Verified: public Notification page does not expose Phase-2 terminology. | Internal roadmap terminology is exposed to end users. | Reduces product polish and professional presentation. |  | Replace “Phase-2” wording with “Coming Soon.” | 2026-05-24 |  |  | Resolved
44 | Saved Post | Functional | High | Saved posts section is not discoverable |  | Verified: Saved Posts is directly discoverable from the sidebar and the saved-posts page. | Users are unable to locate or access saved posts/content. | Reduced usability of content bookmarking feature. |  | Add a dedicated “Saved Items” section in the main navigation or profile area. | 2026-05-24 |  |  | Resolved
45 | Profile Drop-down | UI/UX | Medium | Profile dropdown navigation can improve usability |  | Fixed on 17-Jun-2026: profile dropdown is supplemented by direct sidebar links for Settings and Appearance. | Profile-related actions are distributed inconsistently across the app. | Reduced navigation clarity and account accessibility. |  | Introduce a profile dropdown containing Profile, Settings, and Logout options. | 2026-05-24 |  |  | Resolved
46 | Privacy Settings | Functional | High | “Who can follow me” privacy option is unclear |  | Fixed on 17-Jun-2026: Privacy now has an explicit Who can follow me selector with clear options. | Existing privacy options around following logic are semantically confusing. | Reduced clarity around privacy controls and account visibility. |  | Replace with clearer options such as “Stealth Mode” and give a Dummy toggle(if planned for future). Stealth Mode = Hide yourself from everyone. We can also make this account 'Anonymous' When Stealth Mode is ON. | 2026-05-24 |  |  | Resolved |  | need clarity for stealth mode
47 | Privacy Settings | Functional | High | Public location visibility setting lacks clarity |  | Fixed on 17-Jun-2026: location privacy label now says Show my location on my public profile. | Users are unclear where their location is being displayed publicly. | Creates confusion and potential privacy concerns. |  | Add explanatory text or remove the setting if unused. | 2026-05-24 |  |  | Resolved
48 | Mood Page | UI/UX | Medium | Mood category hierarchy lacks visual distinction |  | Verified: Mood Explore More has visually distinct group chips for Tone, Reading Intent, Content Energy, and Life Situations. | Mood categories and their values visually blend together in the interface. | Reduced readability and content scanning experience. |  | Differentiate category labels using bold styling or visual emphasis. | 2026-05-24 |  |  | Resolved
49 | Post Browsing | UI/UX | High | Reaction icons lack proper visual representation |  | Verified: reaction controls use distinct Lucide icons for Like, Hug, Insightful, and Relatable. | Reactions currently lack intuitive icons and labels are not visible in mobile interactions. | Reduced engagement clarity and weaker interaction experience. |  | Improve reaction icon design and ensure labels/tooltips are accessible on mobile. | 2026-05-24 |  |  |  |  | not implemented,need to check req
50 | Post Browsing | UI/UX | Medium | Comment button sizing is inconsistent |  | Verified: post action buttons, including Comments, use consistent compact bordered button sizing. | The comment button appears visually smaller compared to reaction buttons. | Minor inconsistency in action hierarchy and UI balance. |  | Align comment button sizing with other interaction buttons. | 2026-05-24 |  |  | Resolved
51 | Personal Space | Functional | High | Personal Space functionality requires clearer onboarding |  | Verified: Personal Space has PIN setup/unlock onboarding copy and private-space guidance. | The purpose and flow of Journal and Entries within Personal Space are not immediately understandable. | Reduced feature discoverability and user adoption. |  | Add onboarding/tooltips or improve section clarity during demos/onboarding. | 2026-05-24 |  |  | Resolved
52 | Post Browsing | Functional | High | Post reporting and user moderation options are missing |  | Verified: post menu exposes Report post, Block user, and Mute user; admin/moderation page is available for privileged users. | Users currently cannot report posts or block/mute other users. | Weak moderation and safety controls within the platform. |  | Add Report, Block, and Mute functionality to user/post actions. | 2026-05-24
53 | Support | Functional | High | Contact Support functionality is missing |  | Verified: Contact Us / Support page exists and is linked from the sidebar. | Users currently do not have an in-app method to contact support. | Reduced issue resolution accessibility and trust. |  | Add a Support/Contact Us section with Subject, Message field, and support email integration. | 2026-05-24 |  |  | Resolved |  | need to verify part of req or not
54 | Message | Functional | High | Users cannot initiate conversations from profiles |  | Verified: profiles expose Message action for other users and DMs can be initiated from that action. | A Conversations/Messages section exists, but users currently do not have a direct way to start a conversation from another user’s profile page. | Reduces social interaction, discoverability of messaging functionality, and overall platform engagement. |  | Add a “Message” button below the “Follow” button on user profiles/search results to allow direct conversation initiation. Messaging should be allowed even between non-followers/non-friends. | 2026-05-24
55 | Home Page | UI/UX | High | Home and Discover sections currently overlap in functionality |  | Home defaults to Trending while Discover routes to the same discovery surface; duplicate following/default behavior is removed. | Both Home and Discover are currently routing to the same page/feed experience, creating redundancy in navigation and reducing clarity between passive feed browsing and intentional content discovery. | Increased navigation confusion and reduced differentiation of Writogram’s emotional discovery experience. |  | Recommended approach: Keep both Home and Discover as separate experiences. Home should contain the personalized feed (Following, Trending, Suggested content), while Discover should focus on Mood-based and emotional/intellectual exploration. This also allows removal of the standalone Mood menu, simplifying the left navigation structure. | 2026-05-25
56 | Profile Page | Functional | High | Profile statistics are non-interactive and lack detailed view |  | Fixed on 17-Jun-2026: profile stats are clickable and load real Followers, Following, or Posts detail panels backed by API endpoints. | The Profile section currently displays only the count of Followers, Following, and Posts, but users cannot click and view the actual details/content associated with them. This limits profile usability and content accessibility. | Reduced user engagement, poor profile interaction experience, and limited visibility into personal content/social connections. |  | Make the Followers, Following, and Posts sections interactive/clickable. When selected, display the corresponding details/content in a dedicated container section below the profile card and visually highlight the active selected tab/button. | 2026-05-25
57 | Compose Page | Functional | High | Users cannot edit or delete posts after publishing |  | Verified: post owner action menu supports Edit post and Delete post. | Currently, users do not have an option to edit or delete posts once they are published. This limits content management flexibility and correction capabilities. | Reduced user control over published content and poor post-management experience. |  | Add a 3-dot options menu on the top-right corner of each post with Edit and Delete actions. Editing should allow modification of text, privacy settings, tags, and related metadata without any edit time restriction. | 2026-05-25
58 | Post Browsing | UI/UX | Medium | Comment input placeholder alignment appears visually awkward |  | Fixed on 17-Jun-2026: post detail comment input now uses responsive vertical alignment and min-height. | The “Add a thoughtful reply...” placeholder/input area appears positioned towards the top-left side of the comment container, creating an unbalanced visual appearance. | Reduced UI polish and slightly inconsistent comment interaction experience. | Comment-Reply.jpeg | Adjust the vertical alignment and spacing of the comment input area to achieve better left-bottom/center alignment within the container for improved visual balance. | 2026-05-25 |  |  | Resolved
59 | Post Browsing | UI/UX | Medium | “More from this author” section alignment appears disconnected |  | Fixed on 17-Jun-2026: post detail layout is responsive and the More from this author panel is aligned/sticky on desktop. | The “More from this author” container appears positioned slightly higher than the adjacent post content section, making the page layout feel visually uneven. | Reduced visual balance and overall UI alignment consistency. | More from This Author.jpeg | Move the “More from this author” section slightly downward to align better with the adjacent content container and improve overall page symmetry. | 2026-05-25
|  |  |  | Issues/observation | status | Remarks | Column 2
|  |  |  | to find my contacts already on Writogram (missing) | unable to find this
|  |  |  | profile photo feature not working , bio (≤ 200 chars) validatio ther but not user friendly msg that 200 char completed , location (city/country, optional) language preference joined date (missing) | fail(joined date still missing)
|  |  |  | User shall create a signature (text, ≤ 80 chars, optional emoji) that is automatically appended to every public/custom post. Signature can be edited or disabled. (there is no option for disable signature | pass
|  |  |  | System shall provide a curated catalog of 100–200 themes covering color palette, typography, and background style. Themes apply to the user’s app UI only.(only limited theme option ptovided not 100-200) | pass
|  |  |  | User shall preview and apply any theme instantly without restart. Last 5 used themes shown as recent.(last 5 used themes shown as recent functionalty not present) | fail
|  |  |  | serch bar type something click enter then second search bar also get appeared.only single bar should be there | pass
|  |  |  | on homepage where #1 #2 title number written it is visible in half #1 or #2 need to to do full scroll to see the full # number | fail(now they #1 number is merging with avatar )
|  |  |  | click follow no msg or indicators | fail(no msg there)
|  |  |  | post shown incorrect as after delete it is not updated and counted edit as new post | pass
|  |  |  | private acc post visble to other but private acc can not be followed (this is correct rigth) | fail
|  |  |  | User shall control who can: follow them (this functionality not present if it is interelated to private account then let me know) ), message them(message functonality not working so unable to test), see their followers list (user can see follower count if the parent/author has turned of follower toggle then also), and see their location(unable to test it as loaction was not captured). | see their followers list (user can see follower count if the parent/author has turned of follower toggle then also), and see their location(unable to test it as loaction was not captured).: these two pass provide calrification for other two please
|  |  |  | User shall block or mute any other user. Blocked users cannot view the user’s profile or content.(feature missing) | fail(mute functionality present but not working same for block not working properly)
|  |  |  | Profile photo must be an image ≤ 5 MB; auto-cropped to square.(unable to update profile photo so unale to check) | fail(avatar upload functionality not working)
|  |  |  | Signature is appended to public and custom posts only — not to private posts or DMs.(siganture is coming private post) | pass(custom left to test)
|  |  |  | in compose it showing msg even after correcting 300 word limit . | pass
|  |  |  | some publish thing coming under draft | need clarfication
|  |  |  | no msg after publish and save draft | fail
|  |  |  | tags are not visble in post(tags were added throught composeer) | pass
|  |  |  | private post shown as draft is this fine , private post only visble in draft section | now not need clarification about it
|  |  |  | custom post : unable to select user to whom this post should be visible and custome post not visible anywhere | fail (not woking and need clarification about scope)
|  |  |  | in composer last used setting is not deffault | pass
|  |  |  | Posts shall be editable within 30 minutes of publishing; after that, edits show an 'edited' marker with timestamp. (unable to edit the post) | pass
|  |  |  | Author can delete a post at any time; cascade-removes associated comments and reactions.(no delete option) | pass
|  |  |  | Private posts are excluded from all feeds, search, and AI emotion-tagging visible to others.(unable to verify as ai mood thing showing 0 post always ) | pass
|  |  |  | Posts deleted by the author are soft-deleted for 7 days for recovery, then hard-deleted.(unable to delete post) | pass(after delete comming under draft need to verify after 7 days
|  |  |  | Privacy selector defaults to user’s last-used setting and is changeable before publishing. Custom-audience post is invisible to anyone outside the selected list.(missing) | pass(custome one need clarification)
|  |  |  | M4. AI-Enhanced Creativity Engine (not present unable to test) | where it is
|  |  |  | M7 1:1 Direct Messaging (identified mode only) (message functionality not working) | fail(one user is able to send msg other not, unbale to slect whom to msg , a user sent msg of hi visbile to all the user )
|  |  |  | Reverse-chronological feed of posts from accounts the user follows, with optional ranking boosts for engagement. System shall compute trending posts using a velocity-weighted score over engagements (reads, reactions, replies) in the last 24 hours. (please provide the logic then i can test feed logic properly) | can you please share logic
|  |  |  | Editorially curated content (by Admin) shall be available as a 'Curated' tab. Refreshed at least daily.(this curated tab is missing) | fail
|  |  |  | User shall select one or more emotions from the mood selector; system returns public posts tagged with those emotions, ranked by recency × engagement × confidence. (0 post shown in mood) | fail(user select love then it returns love but with other articles aswell which are not relevant)
|  |  |  | Discovery feeds shall support filters: post type (Thought/Poem/Quote/Reflection), language, time window. (this is missing discovery feed shows home page items) | fail (missing)
|  |  |  | User shall bookmark any post for later reading. Bookmarks are private. (bookmark and save functionality same or diiferent if different then bookmark is missing) | need clarification
|  |  |  | Threaded replies on public/custom posts. Author can disable comments per post.(author is unable to disable the comment ) | pass
|  |  |  | Share a post outside the app via system share sheet, with deep-link back to Writogram. (share functionality not working) | pass(but there is no whatsapp share functionality)
|  |  |  | User shall mark a post as not interested; future feed ranking adjusts accordingly. (there is not aoption to mark post not intrested) | fail
|  |  |  | Selecting a mood returns at least 20 relevant public posts (where available) within 1 second of selection. Bookmarked posts are accessible offline (last 50).(functionality missing) | fail
|  |  |  | Custom posts are visible only to the explicitly selected audience.(not working) | need clarification
|  |  |  | reaction not working properly suppose user like one post and it impact to other post reaction like it increases the like on other post or apply reaction on other reactions multiple post get impacted with one reaction one post and unable to add multiple reactions | fail
|  |  |  | comments placeholder allignment and circle thing didn't have anything | fail
|  |  |  | recent searches thing not working and trending thing when user do invalid search these two modal appear | fail(trending search not working) and multiple filter not working
|  |  |  | User can add number and special character in reply and in post | fail
|  |  |  | click save and share no indicators and sahre not working I guess | pass
|  |  |  | explore more button have different tabs but not all tab visible under when click some tabs then other tab visible (mood ) and they are not highlighted properly | fail(highligh not working properly)
|  |  |  | edited post via draft then current post not edited new post appear with same and edited info | fail
|  |  |  | Mute functionality unable to test as notification thing not working | fail(funtionality present but not working)
|  |  |  | personal space user enter pin then log out or move to next screen then come back to personal space then user didnt need to enter pin journal is visible without entreing pin | pass
|  |  |  | when user click multiple time save enry then duplicate enry created (personal space) | pass
|  |  |  | in persona space user unable to save long journal with long title (if we have restriction for title then user us unable to see) | pass
|  |  |  | in personal space clender view is missing | pass
|  |  |  | Entries can be tagged with user-defined keywords for personal organization.(functionality missing) | pass
|  |  |  | Personal Space can be protected with a separate PIN or biometric in addition to app-level auth.(biometrci not availble and reset pin if exist or needed) | need clarification
|  |  |  | Journal entries are encrypted at rest. Server admins do not access journal content in normal operations.(unable to test as dont have admin access) | pass
|  |  |  | User shall export a journal as PDF or plain text for personal backup. (functionality missing) | pass
|  |  |  | Deleting an entry removes it from personal storage immediately; encrypted backups purge within 30 days.(delete option is missing) | pass(need to discuss about backup point)
|  |  |  | Exported PDF preserves date, tags, and entry text in a readable layout.(functionality missing so unable to test) | pass
|  |  |  | M10 Push and in-app notifications (notification not working so unable to test) | fail(not working)
|  |  |  | Filter by language, time window, post type, and emotion tags (for posts).(filters missing) Show recent searches and trending queries when search is empty.(functionality missing) Private and Personal Space content shall never be indexed; custom posts are indexed only for their allowed audience.(custom post unable to test) | fail(filters are not present until user type something in search box ) ,fail(treding querris not clickablele),need clarifiaction about custom
|  |  |  | Typing 3 characters returns suggestions within 500 ms.(typing 3 charachter search not working) Emotion-filtered search returns only posts whose detected emotions match(emotion fiter missing) | pass(typing 3 charchter return but slow ),fail (emotion filter not working propelry)
|  |  |  | Blocked users do not appear in each other’s search results.(it is happening) | fail
|  |  |  | M13 Admin Panel — core operator tools (unable to test didnt have the acccess) | fail(most of the admin functonality are missing plese check the doc)
|  |  |  | Users can report posts, comments, books, communities, and users with predefined reasons (harassment, spam, hate, sexual content, self-harm, copyright, other).(user can only report post and there were no options to selcted reason for reporting, after reporting nothing happens) | fail(user can still report comment)
|  |  |  | System runs automated checks on new content (text classification for hate, sexual content, self-harm risk).(user have written self harm content but nothing heppens) | fail
|  |  |  | Internal admin/moderator dashboard lists open reports with content snapshot, reporter info, history of accused user. Available actions: dismiss, warn user, remove content, restrict user, suspend user, permanently ban user. Cascade-delete options where applicable. Posts/messages flagged as self-harm trigger a supportive in-app resource overlay with helpline information localized to the user’s country. Users may appeal enforcement actions; appeals route to a separate review queue. All moderation actions are logged with actor, timestamp, target, and reason.Anonymous DM senders are subject to stricter automated thresholds. Repeated offenses escalate via a documented strike policy. CSAM detection triggers immediate removal and reporting per applicable law. A submitted report is visible in the moderation queue within 30 seconds. Removing content takes effect across all surfaces within 10 seconds. Self-harm overlay appears the moment a flagged composition is submitted. (unable to test as not ahve the admin access or functionality misisng) | fail(most of the admin fucntionality not present)
|  |  |  | Post vanished after sometime or 24 hr is this fine from feed | need clarification
|  |  |  | account have otp thing for email and phone not working | fail
|  |  |  | privacy have multiple toggle mostly static | meesage unable to test as functionality not working properly, what is stealth mode unable to find in doc , privacy toggle not working properly and ai toggle is static right now?
|  |  |  | theme it is applied but no msg appear | pass
|  |  |  | no validation messages on profile page for user | fail
|  |  |  | profile photo uploaded but not shown and saved but when you came back to profile page then again it shown no file selected | fail(for a acc i am able to upload pic for another not)
|  |  |  | no confirmation on logout | pass
|  |  |  | takes time to update and not calor on like reaction same for other reactions | fail
|  |  |  | now after the day thing vanished from draft | need clarification
|  |  |  | private post will be shown in draft only? | private post no visible anywhere
|  |  |  | draft got publish but also visible in draft section is this fine , no if fine user click resume from draft edit the current fraft and click publish then new draft publish current one not edited , no msg when click save draft ,delete draft then same published article not deleted this is right? | need clarification
photo is uploaded in profile but no file selcted shown
loaction in profile we can add number special character etc aswell
language slected other than english and saved but only eng got selcted
search bar loaction and top banner ui change when user write something in search bar and click enter
post is allowed to be delted after 30 min
site feelsa buit slow
user click publish then article not get published the behaviour is inconsistemt
explore more option in mood slect option then nothing it return
comments disabled but user can write in the input box
share dont have whatsapp option is this fine
|  |  |  | user can edit post after 30 min is this fine ? | need clarification
the reported post shown to admin but witout any post material
3 dot option button present at post not auto close
warn removes the post in admin ,suspend not works, ban also not works (admin post options )
personal space only need to enter pin one time
website taking time there is noticable delays
buttons are not disable after click user can press multiple times and multiple entry created global issue
|  |  |  | Send OTP with valid phone number | fail
|  |  |  | Send OTP with empty phone field,validation msg should appear | fail
|  |  |  | Login with empty email field Login with empty password field (validation msg should appear | fail
|  |  |  | no validation for user (no guidance) | pass
|  |  |  | to choose my preferred language during onboarding (mentioned in req its missing) | pass
|  |  |  | to be guided through a short setup flow (mentioned in req its missing) | fail(it appeared for new user one time when tried to test again created acc or via google login then this flow not appeared
System shall issue secure JWT-based session tokens with refresh-token rotation. Sessions expire after 30 days of inactivity. (how can i test , testing pending)
|  |  |  | deleted account but user is able to login is this fine | pass
|  |  |  | First-time users shall complete: language selection → basic profile (name, location optional) → signature setup → theme selection → first contact suggestions.(missing) | fail(it appeared for new user one time when tried to test again created acc or via google login then this flow not appeared
|  |  |  | Onboarding steps after language selection shall be skippable and resumable from the profile screen. (missing) | unable to test as it appeared for new user one time when tried to test again created acc or via google login then this flow not appeared
|  |  |  | create acc and sign in didnt have hyperlink blue calor | pass
|  |  |  | switch from create acc to log in vice versa data not get refreshed | pass
Username must be unique platform-wide, 3–20 characters, alphanumeric + underscore.(onboarding flow profile page dont have this validation)
user can enter number special character etc in location field of onboarding flow profile page
no validation for user on profile page of onboarding
|  |  |  | need to test find voices to follow page of onboarding once it is implemented | pending implementation and testing
bio is comming out of box when it is long > cllick profile > then observe
language is set but about box showing no language set
unable to move forward after clicking finish onboarding when user performs negative tesing if there are any validation then user should see them at the same screen only
when user click profile icon then setting /profile option selction box open soemtime for selection sometime it open but closes suddenly
google login new user then onboarding flow not shown
user selected kanada from onboarding flow but when he get logged in then the slected language prefernce was english
in many of the case onboarding flow not appear even when acc has been created by email psw so unable to test skip onboarding flow button
Verify empty email validation Verify empty password validation(creat acc validation miss)
Unable to see Blocked users
Report Post - Reasons/options missing
Block user - Confirmation is needed
Even though user is blocked, the post is visible in the Browse by Mood section

## Features List - Phase-wise
S.No | Feature | Requirement / Expected Behaviour | Purpose / Business Value | Priority | Suggested Phase | Response from Dev | Additional Comment (if any)
1 | Public Profile URL | Every user should have a public profile URL (e.g., writogram.com/username) that can be shared externally. | Personal identity and profile sharing. | High | P1
2 | Welcome Message for New Members | Automatically display/send a welcome message after successful registration explaining platform basics, badges, streaks and writing journey. | Better onboarding and user retention. | High | P1
3 | Rich Text Editor | Allow formatting while composing content. Support Bold, Italics, Underline, Headings, Lists, Quotes, Paragraphs and proper spacing. | Improves writing experience and readability and creative expression. | High | P1
4 | Badge/Title Framework | Create a flexible badge system where badges can be manually or automatically assigned based on predefined conditions. | Recognition, gamification and user motivation. | High | P1
5 | Badge Section in Profile | Add a dedicated "Badges" section in user profile showing all badges earned, descriptions and achievement dates. | Showcase achievements and build credibility. | High | P1
6 | Founding Member Badge | Exclusive recognition badge awarded to the first 100 approved members who join Writogram during its early launch phase which can be displayed on profile and posts. | Creates exclusivity and rewards early adopters. | High | P1
7 | Creator Partner Badge | Special badge for Instagram/content creator partners who actively collaborate with Writogram, promote the platform, participate in campaigns, or contribute to community growth. | Builds creator ecosystem and trust. | High | P1
8 | Referral Tracking System | Every user should have a unique referral link/code. Track successful signups through referrals. Display referral count in profile and make referral data available in admin panel. | Organic user acquisition and community-led growth. | High | P1
9 | Referral Achievement Badges | Automatic badges based on referral milestones (e.g., 10, 30, 50, 100, 300, 500, 1000 referrals). | Encourages community-driven growth. | High | P1
10 | Writing Streak System | Track consecutive writing/posting days. Show current streak and longest streak on profile. | Encourages habit formation and repeat usage. | High | P1
11 | Writing Streak Badges | Automatically award badges for streak milestones such as 7, 30, 50, 100 and 365 days. | Long-term engagement and retention. | High | P1
12 | Milestone Notifications | Trigger notifications whenever a user unlocks a badge, completes a streak, reaches referral milestones or gets featured. | Creates excitement and positive reinforcement. | High | P1
13 | Badge Visibility Controls - Show/Hide Badge on Profile/Posts (2 Toggles) | Users should be able to decide whether badges appear on profile, posts, comments and future share cards. | Personalization and flexibility. | High | P1
14 | Featured Badge Selection | Users may earn multiple badges. Allow them to choose one badge as their primary/featured badge. | Gives users control over their public identity. | High | P1
15 | Badge-Based Identity Display | Whenever a user publishes a post, their selected badge/title should appear near their name (if enabled). Example: Creator Partner, Founding Member, 100-Day Writer. | Makes badges visible and meaningful. | High | P1
16 | Founding Member Numbering | Founding members should receive a member number such as #12, #47, #83 etc. This can be shown in profile and milestone notifications. | Makes founding membership feel exclusive and collectible. | Low | P1
17 | WhatsApp Status Sharing | Generate a branded share card and allow users to share writings directly to WhatsApp Status. Generated cards should optionally support: [Author Name, Badge/Title, Writogram Branding, Profile URL] | Organic marketing and brand visibility, Increased user acquisition, virality, and social visibility through external sharing. This will help growth. | High | P1.5
18 | Instagram Story Sharing | Generate a branded story card and allow users to share writings directly to Instagram Stories. | Creator-driven growth and audience acquisition. | High | P1.5
19 | Share Card Templates | Provide at least 5 professionally designed templates for generating share cards. Users can choose a preferred style before sharing. | Better aesthetics and higher shareability. | High | P1.5
20 | Featured Authors Ranking (Weekly/Monthly - Spotlights) | Display top authors for week, month and year based on engagement and community interaction. System to highlight selected writings or authors every week based on engagement metrics such as likes, saves, shares and comments. | Encourages quality writing and healthy competition. | High | P1.5
21 | Personal Statistics Dashboard | Display user-specific statistics such as Total Posts, Total Reads/Views, Likes Received, Comments Received, Saves Received, Referral Count, Current Streak, Longest Streak, Spotlight Appearances and Badges Earned. | Helps users track growth and engagement. | High | P1.5
22 | Generic Badge Configuration Framework | Admin should be able to create new badges, titles, eligibility rules, badge descriptions and icons without requiring development changes. | Future-proof badge system. | High | P1.5
23 | Mood Insights Display | Display trending mood statistics on Discover/Mood pages so users can understand current writing trends. | Content discovery and user engagement. | High | P1.5
24 | Private Account Support | Users should be able to mark their account as private and approve or reject follow requests from other users. | Enhanced privacy controls and follower management. | High | P1.5
25 | Trending Mood Analytics | Identify and display most popular moods/emotions for the day, week and month based on published content. | Aligns with Writogram's emotion-centric identity. | Medium | P1.5
26 | Dedicated Leaderboard Page | Create a leaderboard page showing rankings such as Top Writers, Highest Streaks, Most Shared Authors, Most Saved Authors and Top Referrers. | Community recognition and gamification. | Medium | P1.5
27 | Highest Writing Streak Leaderboard | Display users with highest active writing streaks. | Motivates consistency and engagement. | Medium | P1.5
28 | Enhanced Admin Analytics Dashboard | Expand admin dashboard with metrics such as Total Users, DAU, WAU, MAU, Average Session Time, Posts Created, Referral Data, Trending Moods, Most Active Writers and Engagement Trends. | Better product decisions and growth monitoring. | High | P2
29 | Custom Audience Lists | Allow users to create custom groups/lists and selectively share writings with those audiences during publishing. | Advanced privacy controls and personalized sharing. | High | P2
30 | Music Attachment for Posts | Allow users to associate mood-based background music with writings. Music should enhance emotional storytelling. | Richer content experience and emotional immersion. | High | P2
31 | Image/Card Attachment Support | Allow users to optionally upload an lightweight images or visual cards to accompany writings. Writing remains primary and image appears below content. | Enhanced storytelling and visual expression. | High | P2
32 | Referral Leaderboard | Dedicated ranking of users who brought the most referrals to the platform. | Growth-focused gamification. | Medium | P2
33 | Layered Mood Discovery Framework | Expand mood discovery beyond emotions into multiple dimensions such as Emotion, Tone, Reading Intent, Life Situations and Content Energy. Users should be able to browse content using richer emotional and contextual filters. | Improves personalization, content discovery and future AI recommendation capabilities. | Medium | P2
34 | Font Customization | Allow users to select preferred writing fonts while composing content and optionally set a default font preference within account settings. | Improves writing personalization and creative expression. | Medium | P2
35 | Conversation Categorization | Categorize Conversations into sections such as: 1) Friends (mutual followers), 2) Followers, and 3) Others (non-followers/non-friends) to improve message organization as messaging activity grows. Suggested UI: top category tabs, left-side chat list pane, and right-side detailed conversation pane similar to modern messaging platforms. | Better messaging experience, discoverability and scalability. | Medium | P2
36 | Highlight Posts | Allow users to temporarily highlight selected posts for increased visibility on their profile or feeds. | Better visibility for important content and featured writings. | Medium | P2
37 | Spotlight History | Profile should display how many times a user was featured in Weekly Spotlight and optionally list those appearances. | Recognition and credibility. | Low | P2
38 | Achievement Timeline | A chronological timeline showing achievements such as badges earned, streak milestones, spotlight appearances and referral achievements. | Sense of progression and journey. | Low | P2
39 | AI Writing Assistance | AI-powered grammar correction, spelling correction, readability improvement and writing suggestions while composing. | Improves content quality. | High | P3
40 | AI Emotion Detection | Analyze writings before publishing and automatically identify emotions such as Love, Hope, Motivation, Nostalgia, Friendship, Sadness, Gratitude, Loneliness, Inspiration, etc. The detected emotion(s) may be suggested to the user for confirmation and can be used for mood assignment, discovery and recommendations. | Improves mood classification, personalization, content discovery and future recommendation capabilities. | High | P3
41 | AI Tag & Category Detection | Analyze writings before publishing and automatically suggest relevant tags, topics and content categories based on the writing. Examples include Relationships, Self Growth, Career, Family, Friendship, Motivation, Memories, Life Lessons, etc. Users may review, accept or modify suggested tags before publishing. | Reduces manual tagging effort, improves categorization accuracy and enhances content discovery. | High | P3
42 | Verified Badge | Verification system for notable writers and creators. | Trust and authenticity. | Medium | P3
43 | Premium Badge & Membership | Premium badge with future benefits such as analytics, profile customization and premium writing tools. | Monetization readiness. | Medium | P3
44 | Journal Sharing | Allow users to selectively share personal journal entries with specific trusted users while maintaining privacy controls. | Emotional collaboration and private content sharing. | Medium | P3
45 | Shared Journals | Allow multiple users to contribute to and maintain a shared journal space. | Collaborative emotional writing and relationship-based experiences. | Medium | P3
46 | Signature Image / Drawing Support | Allow users to upload or draw a custom signature that can optionally appear on their profile or published writings. | Stronger author identity and personalization. | Low | P3
47 | Rewards / Credits System | Introduce engagement-based credits, points or rewards that can be earned through activity and redeemed for platform benefits. | Long-term retention, engagement and gamification. | Low | P3
48 | Collaborative Books | Allow multiple authors to collaborate on long-form books and writing projects within Writogram. | Future expansion into collaborative writing. | Low | P3

## BadgesTitles - List
Badge Category | Badge Type | Awarded To / Eligibility | What It Signifies | Badge / Title
Special Limited Badge | Early Access Badge | First 100 approved users of Writogram | Recognized as one of the earliest believers and community members | Founding Member (#1 - #100)
Special Limited Badge | Creator Partnership Badge | Approved creators who actively collaborate with Writogram, contribute content, promote the platform and remain active contributors atleast for a certain initial period (30 Days) | Recognized as an official creator supporting Writogram's growth | Creator Partner
Referral Badge | Community Growth Badge | Refer 10 successful users | Contributed to building the Writogram community | Community Builder
Referral Badge | Community Growth Badge | Refer 30 successful users | Consistently supports community growth | Community Advocate
Referral Badge | Community Growth Badge | Refer 50 successful users | Influences others to join and engage with the platform | Community Influencer
Referral Badge | Community Growth Badge | Refer 100 successful users | Represents and promotes Writogram within the community | Community Ambassador
Referral Badge | Community Growth Badge | Refer 300 successful users | Major contributor to Writogram's expansion | Community Champion
Referral Badge | Community Growth Badge | Refer 500 successful users | Recognized leader within the Writogram ecosystem | Community Leader
Referral Badge | Community Growth Badge | Refer 750 successful users | Exceptional contribution to community building | Community Pioneer
Referral Badge | Community Growth Badge | Refer 1000 successful users | Legendary contribution to Writogram's growth | Community Legend
Writing Streak Badge | Consistency Badge | Maintain a 7-day writing streak | Demonstrates commitment to writing consistently | 7-Day Writer
Writing Streak Badge | Consistency Badge | Maintain a 30-day writing streak | Established a regular writing habit | 30-Day Writer
Writing Streak Badge | Consistency Badge | Maintain a 50-day writing streak | Demonstrates strong writing discipline | 50-Day Writer
Writing Streak Badge | Consistency Badge | Maintain a 100-day writing streak | Highly consistent contributor | 100-Day Writer
Writing Streak Badge | Consistency Badge | Maintain a 180-day writing streak | Long-term commitment to writing | 180-Day Writer
Writing Streak Badge | Consistency Badge | Maintain a 365-day writing streak | Elite writing consistency and dedication | 365-Day Writer
Recognition Badge | Featured Author Badge | Selected for Weekly Spotlight | Writing has been recognized for quality and engagement | Weekly Spotlight Author
Recognition Badge | Featured Author Badge | Selected multiple times for Weekly Spotlight (e.g., 10 times) | Consistently produces high-quality content | Spotlight Veteran
Recognition Badge | Featured Author Badge | Top ranked author for a month | Exceptional engagement and writing quality | Author of the Month
Recognition Badge | Featured Author Badge | Top ranked author for a year | One of Writogram's most impactful writers | Author of the Year
Achievement Badge | Milestone Badge | Publish first post | Started the writing journey on Writogram | First Words
Achievement Badge | Milestone Badge | Publish 100 posts | Significant contribution to the platform | Century Writer
Achievement Badge | Milestone Badge | Publish 500 posts | Major long-term contributor | Prolific Writer
Achievement Badge | Milestone Badge | Publish 1000 posts | Exceptional writing contribution | Master Storyteller
Verification Badge | Verification Badge | Approved by Writogram verification process | Verified identity and authenticity | Verified Writer
Membership Badge | Premium Membership Badge | Active premium member subscription | Premium member with additional benefits | Premium Member