# Proposal

OMARA DIGITECH PVT. LTD.

One Ecosystem. Endless Possibilities.

PROJECT EXECUTION PROPOSAL

Design, Build & Delivery of the Omara Digitech Digital Ecosystem

6 Static Websites  •  QmaxPay  •  E-Mart  •  1Q1Pay  •  Fincomax  •  ERP Suite

Indicative Commercial Range: ₹12–14 Lakh  +  applicable GST

Final value confirmed after the Phase 0 discovery stage, within this band

Engagement Duration: 4–5 Months  |  Model: Fixed-Price, Milestone-Based

Version 1.0  |  Status: For Client Review & Sign-Off

25 June 2026  |  Strictly Private & Confidential

# Document Control

| Field | Detail |
| --- | --- |
| Document title | Project Execution Proposal — Omara Digitech Digital Ecosystem |
| Prepared for | Omara Digitech Pvt. Ltd. (Rudranjali Organics Group) |
| Engagement | Phase 1 build of 6 static websites and 5 software platforms |
| Commercial value | ₹12–14 Lakh + applicable GST — final value confirmed after Phase 0 discovery |
| Pricing model | Fixed-price, milestone-based |
| Overall duration | 4–5 months from contract signing (incl. 1–2 week discovery) |
| Version | 1.0 — initial proposal |
| Status | For Client Review & Sign-Off |
| Classification | Strictly Private & Confidential |
| Date of issue | 25 June 2026 |

## Version History

| Version | Date | Summary of Change |
| --- | --- | --- |
| 1.0 | 25 Jun 2026 | Initial proposal — scope, approach, timeline, commercials and commercial protections. |

# 1. Executive Summary

Omara Digitech Pvt. Ltd. is establishing an integrated digital ecosystem spanning corporate web presence, a B2B payment-API infrastructure, a retail fintech platform, a multi-tier e-commerce engine, a professional-services marketplace, and an internal operations ERP. This proposal sets out a complete, fixed-price plan to design, build, test and go-live with the Phase 1 release of all of these in a single, coordinated programme.

The engagement is organised into seven workstreams delivered across three release waves, anchored by an upfront discovery sprint that locks requirements before any code is written. The programme is priced within a band of ₹12–14 Lakh plus applicable GST — the exact value is determined at the close of the Phase 0 detailed requirement-gathering stage and will, in all cases, fall within this range — and completes in 4–5 months.

## 1.1 What You Get

- Six responsive, SEO-ready static brand websites — delivered inside the first month.

- QmaxPay API Panel and the E-Mart multi-tier commerce platform — delivered within 2.5 months.

- 1Q1Pay fintech platform, Fincomax marketplace & compliance platform, and the ERP Suite — delivered within 4 months, with integrated go-live and stabilisation by month 5.

- A locked, signed-off requirement baseline; a sprint-based build with fortnightly demos; full QA, UAT support, and a 90-day post-go-live warranty.

# 2. Understanding of the Engagement

The deliverables form a single connected ecosystem rather than seven independent products. Ownership and integration are distinct concerns, and the build sequence respects both. The structure we will deliver against is as follows:

| Entity | Type | Role in the Ecosystem |
| --- | --- | --- |
| Rudranjali Organics | Static website (corporate parent) + Emart implementation for Rudranjali | Group holding company; brand story, vision/mission, group structure. |
| Omara Digitech | Static website (tech subsidiary) | Technology arm; portfolio of the platforms below. |
| QmaxPay | Software — B2B API panel | Payment-API infrastructure; the engine that powers 1Q1Pay. |
| 1Q1Pay | Software — retail fintech | Aggregated retail payment/banking services over QmaxPay; powers payments for E-Mart & Fincomax. |
| E-Mart | Software — multi-tier e-commerce | Distributor → Wholesaler → Retailer → Customer chain; checkout via QmaxPay/1Q1Pay. |
| Fincomax | Software — marketplace + compliance | Upwork-style professional-services marketplace; payments routed through 1Q1Pay. |
| ERP Suite | Software — operations platform | HRMS, CRM, Finance, Task & Team, Inventory, LMS on a multi-tenant SaaS foundation. |

Integration is not ownership: QmaxPay feeds 1Q1Pay, and 1Q1Pay carries payments for E-Mart and Fincomax. This dependency chain drives the release sequencing in Section 5 — the payment rail (QmaxPay) is built first so the platforms that depend on it can integrate against a stable interface.

# 3. Scope of Work

All software is delivered at Phase 1 (MVP) depth as defined in the approved Software Requirements Specifications. The table below summarises the seven workstreams; detailed scope follows.

| # | Workstream | Phase 1 Size | Phase 1 Coverage |
| --- | --- | --- | --- |
| 1 | 6 Static Brand Websites | 6 sites | Responsive corporate/product marketing sites with shared design system, CMS-lite content, enquiry forms, SEO meta. |
| 2 | QmaxPay — API Panel | 14 modules | API catalog, single-provider routing, prepaid wallet, single-tier reseller panel, developer portal, ledger & reports. |
| 3 | E-Mart — Multi-Tier Commerce | 17 modules | Multi-tier sourcing, catalog, inventory, orders, single gateway + COD, GST billing, admin & support. |
| 4 | 1Q1Pay — Fintech Platform | 22 modules | AEPS/DMT/BBPS/recharge/UPI over QmaxPay, single-tier retailer channel, prepaid wallet, KYC, settlement & reports. |
| 5 | Fincomax — Marketplace & Compliance | ~20 modules | Job marketplace, proposals, hiring, engagement workspace, messaging, reviews, compliance catalog/tracking, document vault. |
| 6 | ERP Suite | 6 modules + foundation | LMS, CRM, HRMS, Inventory, Finance, Task & Team on a multi-tenant SaaS foundation (auth, RBAC, billing, super-admin). |
| 7 | Phase 0 — Discovery & Readiness | 1–2 weeks | Requirement lock, delivery planning, environment & access readiness, sign-off baseline. |

## 3.1 Workstream 1 — Six Static Brand Websites

Six responsive marketing/corporate sites built on a shared design system and component library for speed and visual consistency: Rudranjali Organics, Omara Digitech, QmaxPay, 1Q1Pay, Fincomax and E-Mart.

- Up to 6–8 content pages per site (home, about/vision-mission, products/services, ecosystem, news/announcements, careers where relevant, contact).

- Lightweight CMS for editable text/images/banners; contact & enquiry forms with email routing and spam protection.

- Responsive layouts, SEO meta/Open-Graph, sitemap, analytics tag, and basic performance optimisation.

- Brand-aligned visuals from supplied logos/colour palette; client provides final copy, imagery and legal pages.

Excluded: e-commerce/transactional features on the static sites, multi-language, blog editorial workflows, and bespoke per-page animations beyond the agreed design system.

## 3.2 Workstream 2 — QmaxPay API Panel (Phase 1)

A B2B API repository and panel with 14 functional modules plus admin and support, built to the QmaxPay SRS guardrails.

- User & identity management, API repository/catalog, provider/upstream aggregation (one provider per API).

- API key & credential management, subscription/plans/pricing, prepaid wallet & billing, transaction & routing engine.

- Single-tier reseller / white-label panel, settlement & payout (report-only margins), developer portal & documentation.

- Webhooks & callbacks, rate limiting/quota, reports & analytics, risk/fraud/compliance basics.

Guardrails: one provider per API (no least-cost routing), single-tier resellers (no cascades), prepaid-only wallet, report-only margins, static documentation (no live console). Provider go-live depends on client-supplied credentials and third-party approvals (see Section 12).

## 3.3 Workstream 3 — E-Mart Multi-Tier Commerce (Phase 1)

A single web admin application delivering one coherent end-to-end flow across the Distributor → Wholesaler → Retailer → Customer chain, covering all 17 modules at Phase 1 depth (EM-UM through EM-ST).

- Identity & roles, multi-tier hierarchy & Strict/Flexible sourcing toggle, catalog, tier pricing & margin, inventory & warehouse.

- Storefront/checkout (registered users), order management with GST invoice, procurement/PO, payment & wallet (single gateway + COD), logistics.

- Commission (report-only), promotions/coupons, reports & analytics, GST tax & compliance, notifications, admin panel, support ticketing.

Excluded: native mobile apps, partner API gateway, loyalty/rewards, AI forecasting, multi-language/currency, courier APIs, returns flow, partial shipments.

## 3.4 Workstream 4 — 1Q1Pay Fintech Platform (Phase 1)

A fintech and payment-services platform aggregating retail banking transactions through QmaxPay and delivering them via a single-tier retailer network — 22 MVP modules across four groups.

- Group A — Core platform & access: identity, RBAC, KYC onboarding, retailer-funded prepaid wallet, ledger.

- Group B — Fintech services over the QmaxPay integration layer: AEPS, money transfer/DMT, BBPS, recharge, UPI/QR.

- Group C — Commercial, settlement & operations: pricing, commissions, settlement, reconciliation, reports.

- Group D — Administration, compliance & support: super-admin, notifications, audit, support.

Dependencies: live fintech rails (AEPS, DMT, BBPS, UPI) require sponsor-bank/aggregator agreements, sandbox access and regulatory clearances obtained by the client; software is delivered ready to integrate (see Section 12).

## 3.5 Workstream 5 — Fincomax Marketplace & Compliance (Phase 1)

A web-based professional-services marketplace connecting clients with verified professionals (CA, CS, Lawyer, Accountant, Bookkeeper, CFA, CFO), with a lean compliance-management layer — approximately 20 modules across four groups; payments routed through 1Q1Pay.

- Core platform & access: roles, onboarding & KYC, wallet/billing account.

- Marketplace front-end & profiles: storefront, search & discovery, professional and client profiles.

- Job marketplace & engagement: job posting, proposals/bidding, hiring & contracts, engagement workspace with milestones, messaging, ratings & reviews.

- Compliance services: compliance catalog & applicability, tracking & calendar, document collection & vault.

Excluded / deferred: Phase 2 “Fincomax Books” (53-module bookkeeping suite), automated/third-party KYC, e-signature, government-portal integration, auto-filing, native mobile apps.

## 3.6 Workstream 6 — ERP Suite (Phase 1)

A multi-tenant SaaS operations platform with six Phase 1 functional modules on a shared foundation layer (Requirement IDs ERP-[Module]-[NNN]). Per the design decision, Team Management is delivered as a thin layer over the HRMS org structure and RBAC rather than as a standalone data model.

- Functional modules: LMS (Learning Management), CRM, HRMS, Inventory, Finance (Indian GST-compliant), Task & Team Management.

- Foundation layer: tenant onboarding, subscription/billing, authentication, module-level RBAC, platform super-admin, notifications.

- Non-functional baseline: multi-tenant scaling, TLS + at-rest encryption, audit logging, automated backup, responsive web, 99.5% target availability.

Open assumptions confirmed at Phase 0 sign-off: A-01 LMS = Learning Management (not Lead/Loan Management); A-02 multi-tenant SaaS for businesses (not individual consumers). Phase 2 (~43 modules: operations, supply chain, manufacturing, sales, marketing) is excluded.

# 4. Delivery Approach & Methodology

## 4.1 Phase 0 — Discovery, Requirement Lock & Readiness (1–2 weeks)

Before any build begins, a rigorous discovery sprint converts the existing SRS baselines into a locked, signed delivery plan. This phase is the single most important protection against downstream rework.

- Requirement walkthrough and confirmation of every module’s Phase 1 depth and exclusions, per platform.

- Confirmation of open assumptions (e.g., ERP A-01/A-02) and architectural decisions.

- Integration mapping: QmaxPay → 1Q1Pay → E-Mart/Fincomax payment contracts and shared identity/wallet behaviour.

- Environment & access readiness checklist: cloud/hosting, repositories, domains, third-party sandbox credentials, content and brand assets.

- Detailed sprint plan, UAT plan, acceptance criteria and the signed requirement baseline.

Deliverable: a signed Delivery Plan & Requirement Baseline, together with the confirmed contract value fixed within the ₹12–14 Lakh band. The build clock for each workstream starts only against this baseline; subsequent changes follow the change-control process in Section 10.

## 4.2 Agile, Sprint-Based Build

Each platform is built on its already-defined sprint sequence (e.g., the E-Mart and 1Q1Pay 8-sprint plans, the Fincomax 10-sprint plan, the ERP build-sprint sequence). We run two-week sprints with a working demo at each sprint close, so progress is visible and course-corrections are cheap.

- Fortnightly sprint demos and a shared progress dashboard.

- Continuous integration with code review; staged environments (dev → staging → UAT).

- Release waves sequenced by dependency: static sites first, then QmaxPay + E-Mart, then 1Q1Pay + Fincomax + ERP.

## 4.3 Quality Assurance

- Test cases derived from the requirement IDs in each SRS, ensuring traceability from requirement to test.

- Functional, integration, regression, cross-browser and responsive testing; security smoke testing on auth, RBAC and payment flows.

- Defect triage by severity (Sev-1 to Sev-4); Sev-1/Sev-2 are gating for UAT sign-off.

## 4.4 Security & Data Protection Posture

- TLS in transit and encryption at rest; role-based access control and secure session handling across platforms.

- Secrets/credential management for third-party API keys; audit logging of key actions.

- Least-privilege access to environments; PII handled per the data-protection clause in Section 15.

## 4.5 Governance & Communication

| Cadence | Forum | Participants & Purpose |
| --- | --- | --- |
| Daily | Internal stand-up | Omara delivery team — progress, blockers. |
| Weekly | Status report + call | Client SPOC — RAG status, risks, decisions needed. |
| Fortnightly | Sprint demo | Stakeholders — working software review & feedback. |
| Per milestone | Acceptance review | Client sign-off against acceptance criteria. |

A single Client SPOC (single point of contact) with decision authority is required to keep the cadence and timeline intact.

# 5. Project Timeline & Milestones

The programme runs over 4–5 months from contract signing. Release waves overlap where dependencies allow, so the static sites and the QmaxPay/E-Mart wave are well underway before the final wave begins.

## 5.1 Release Schedule

| Wave | Deliverable | Window | Target Completion |
| --- | --- | --- | --- |
| Phase 0 | Discovery, requirement lock & readiness | Weeks 1–2 | End of Week 2 |
| Wave 1 | 6 Static Brand Websites — live | Weeks 2–4 | End of Month 1 |
| Wave 2 | QmaxPay API Panel + E-Mart — UAT sign-off | Weeks 3–10 | Month 2.5 |
| Wave 3 | 1Q1Pay + Fincomax + ERP Suite — UAT sign-off | Weeks 5–16 | Month 4 |
| Closeout | Integrated UAT, stabilisation & go-live | Weeks 16–20 | Month 5 |

## 5.2 Payment-Linked Milestones

| Milestone | Trigger | Target | % of Fee |
| --- | --- | --- | --- |
| M0 — Mobilisation | Contract signing & kickoff | Week 0 | 20% |
| M1 — Baseline locked | Phase 0 requirement & delivery-plan sign-off | End Week 2 | 10% |
| M2 — Websites live | 6 static websites accepted | End Month 1 | 10% |
| M3 — Wave 2 accepted | QmaxPay + E-Mart UAT sign-off | Month 2.5 | 25% |
| M4 — Wave 3 accepted | 1Q1Pay + Fincomax + ERP UAT sign-off | Month 4 | 25% |
| M5 — Go-live & closure | Integrated go-live & project closure | Month 5 | 10% |

Timelines assume on-time milestone sign-offs, timely provision of third-party credentials/approvals, and a continuously available Client SPOC. Client-side delays pause the affected workstream clock (Section 11).

# 6. Team & Engagement Model

A dedicated, cross-functional pod delivers the programme, scaled across the three waves. Roles may be shared across workstreams to maintain consistency and cost efficiency.

| Role | Responsibility |
| --- | --- |
| Engagement / Delivery Manager | Single accountable owner; governance, milestones, risk and client communication. |
| Solution Architect | Cross-platform architecture, integration contracts (QmaxPay ↔ 1Q1Pay ↔ E-Mart/Fincomax), tech standards. |
| Backend Engineers | APIs, business logic, data models, third-party integrations, multi-tenant foundation. |
| Frontend Engineers | Admin panels, storefronts, retailer/customer touchpoints, responsive UI. |
| Web/UI Developer | Static websites, shared design system, brand-aligned templates. |
| QA Engineer(s) | Test design from requirement IDs, functional/regression/integration testing, defect triage. |
| DevOps | Environments, CI/CD, deployments, backups, monitoring. |

Engagement model: fixed-price, milestone-based. Omara Digitech retains delivery management and quality ownership end-to-end.

# 7. Commercial Proposal

Indicative Commercial Range: ₹12–14 Lakh + applicable GST This is an indicative range. The exact contract value is determined at the close of the Phase 0 detailed requirement-gathering and delivery-planning stage, once module depth and integration scope are confirmed against the signed baseline. In every case the final value will fall between ₹12 Lakh and ₹14 Lakh.

## 7.1 Payment Schedule

Payments are milestone-based per the percentage split below, raised on milestone achievement (Section 5.2) and payable within the agreed credit period (Section 15). The rupee value of each milestone is the stated percentage of the final confirmed contract value; the last two columns show the value at each end of the ₹12–14 Lakh band.

| Milestone | % of Fee | At ₹12L (₹) | At ₹14L (₹) |
| --- | --- | --- | --- |
| M0 — Mobilisation (on signing) | 20% | 2,40,000 | 2,80,000 |
| M1 — Requirement baseline sign-off | 10% | 1,20,000 | 1,40,000 |
| M2 — Static websites accepted | 10% | 1,20,000 | 1,40,000 |
| M3 — QmaxPay + E-Mart UAT sign-off | 25% | 3,00,000 | 3,50,000 |
| M4 — 1Q1Pay + Fincomax + ERP UAT sign-off | 25% | 3,00,000 | 3,50,000 |
| M5 — Go-live & project closure | 10% | 1,20,000 | 1,40,000 |
| Total | 100% | 12,00,000 | 14,00,000 |

## 7.3 Commercial Notes

- The contract value is confirmed at the close of Phase 0 and will be between ₹12 Lakh and ₹14 Lakh; the milestone percentages above then apply to that confirmed value.

- All amounts are in Indian Rupees and exclusive of GST and any other applicable statutory taxes/levies, which are charged at actuals.

- Third-party costs are excluded and billed at actuals or borne directly by the client: cloud/hosting, domains, SSL, SMS/email gateways, payment-aggregator/AEPS/BBPS/UPI charges, KYC vendor fees, and any paid licences.

- This proposal is valid for 30 days from the date of issue.

- Scope changes are handled through the change-control process (Section 10) and priced separately.

# 8. Assumptions

This proposal is prepared on the following assumptions. If any prove incorrect at Phase 0, scope, cost and/or timeline will be revisited through change control.

- All software is delivered at Phase 1 (MVP) depth as defined in the approved SRS documents; every module is present in thin, working form.

- Static websites are informational/marketing sites with CMS-lite editing; they are not transactional.

- QmaxPay operates one provider per API, prepaid-only wallets, single-tier resellers and report-only margins.

- 1Q1Pay uses a single-tier retailer→customer channel and retailer-funded prepaid wallets; live rails depend on client-provided agreements/credentials.

- E-Mart is web-only (no native mobile apps), single payment gateway plus COD, manual B2B onboarding verification.

- Fincomax routes payments through 1Q1Pay; KYC review is manual; Fincomax Books (Phase 2) is excluded.

- ERP is a multi-tenant SaaS for businesses; LMS denotes Learning Management; English UI at MVP.

- The client provides timely sign-offs, content/brand assets, and all third-party accounts, credentials and sandbox/production approvals.

- Hosting, infrastructure and third-party service fees are outside the quoted fee.

- One empowered Client SPOC is available throughout the engagement.

# 9. Out of Scope (Phase 2 and Beyond)

The following are explicitly excluded from this engagement and recorded to prevent scope creep. They can be quoted as future phases.

- Native mobile applications for any platform (Phase 1 is responsive web).

- QmaxPay: smart/least-cost routing, multi-provider failover, sub-reseller cascades, automated payouts & reconciliation, postpaid/credit billing, interactive API console & SDKs, public status/SLA monitoring, third-party publisher marketplace.

- E-Mart: partner API gateway, loyalty/rewards, AI forecasting & auto-replenishment, multi-language/multi-currency, courier APIs & live tracking, returns and partial-shipment flows.

- Fincomax: Fincomax Books (53-module bookkeeping suite), automated/third-party/video KYC, e-signature, government-portal integration, auto-filing, penalty calculators.

- ERP: the ~43 Phase 2 modules (operations, supply chain, manufacturing, sales, marketing, project management, CMS, etc.) and any extensions to Phase 1 modules.

- Cross-cutting: data migration from legacy systems, third-party licensing, content authoring/copywriting, paid marketing, ongoing managed hosting/support beyond the warranty period, and any statutory licensing or legal/regulatory advisory.

# 10. Change Management & Scope Control

The signed requirement baseline (Phase 0) defines what is in scope. Any addition, removal or material modification is managed through a written Change Request (CR) and is not absorbed silently.

- The client raises a CR, or Omara raises one where a request exceeds the baseline.

- Omara assesses impact on scope, effort, cost and timeline and issues a written estimate.

- Work on the CR begins only after the client approves it in writing; cost and schedule are adjusted accordingly.

- Minor clarifications consistent with the baseline are handled within sprints at no charge; anything that changes module depth, adds modules, or pulls Phase 2 items forward is a chargeable CR.

Repeated or cumulative changes that materially affect the critical path may shift downstream milestone dates. The fixed price is valid against the locked baseline only.

# 11. Client Responsibilities & Dependencies

Timely fulfilment of the following is essential to the timeline. Delay in any item pauses the clock on the affected workstream, and resulting schedule slippage is not attributable to Omara.

- Nominate an empowered SPOC and make stakeholders available for discovery, demos and acceptance within the agreed windows.

- Provide all content, copy, logos, brand assets, legal/policy pages and product data for the websites and platforms.

- Procure and hand over all third-party accounts and credentials: cloud/hosting, domains, SSL, repositories, SMS/email gateways.

- Obtain and provide fintech enablement: payment-aggregator/PG merchant accounts, sponsor-bank/AEPS/DMT/BBPS/UPI agreements, sandbox and production credentials, and any KYC-vendor contracts.

- Secure all statutory licences, registrations and regulatory approvals required to operate the fintech and compliance services.

- Provide UAT resources and complete acceptance testing within each milestone’s UAT window.

- Settle milestone invoices within the agreed credit period.

# 12. Third-Party, Regulatory & Compliance Dependencies

Several capabilities — particularly within QmaxPay, 1Q1Pay and Fincomax — depend on external parties and regulatory clearances that are outside Omara Digitech’s control. This section is a material protection and is read together with Sections 8, 11 and 15.

## 12.1 Third-Party Integration Dependency

Live payment and banking rails (AEPS, DMT, BBPS, recharge, UPI/QR, payment gateway) depend on the availability, behaviour, sandbox access and production approval of external aggregators, banks and providers. Omara delivers the software ready to integrate against documented interfaces; activation of any live rail is contingent on the client supplying working credentials and the provider granting go-live. Timelines for live-rail enablement are estimates and may shift with provider lead times.

## 12.2 Regulatory & Licensing Dependency

Omara Digitech delivers software capability only. Obtaining and maintaining all licences, registrations and statutory approvals — including any payment-aggregator/payment-gateway authorisation, NBFC/lending permissions, AEPS sponsorship, GST e-invoicing enablement and professional-services compliance obligations — is solely the client’s responsibility. Omara does not provide legal, financial, tax or regulatory advice, and is not liable for the client’s regulatory standing.

## 12.3 Compliance-Engine Disclaimer (Fincomax)

The Fincomax compliance catalog, tracking and calendar are administrative tools maintained from client-supplied data. They do not constitute legal or statutory advice, do not auto-file with any authority, and do not guarantee compliance outcomes. Responsibility for the accuracy and statutory correctness of any filing rests with the client and the engaged professionals.

# 13. Acceptance, Warranty & Support

## 13.1 Acceptance & Deemed Acceptance

- Each milestone is delivered with acceptance criteria agreed at Phase 0. The client tests within a 7-business-day UAT window per milestone.

- Sign-off is given when no open Sev-1/Sev-2 defects remain. Sev-3/Sev-4 items are scheduled within warranty and do not block acceptance.

- If the client neither signs off nor logs qualifying defects within the UAT window, the deliverable is deemed accepted and the milestone payment falls due.

## 13.2 Defect Severity

| Severity | Definition | Handling |
| --- | --- | --- |
| Sev-1 Critical | Core flow unusable; no workaround. | Gating; fixed before sign-off. |
| Sev-2 Major | Significant function impaired; workaround exists. | Gating; fixed before sign-off. |
| Sev-3 Minor | Limited impact, minor defect. | Scheduled within warranty. |
| Sev-4 Cosmetic | Cosmetic/UI nicety. | Best-effort / backlog. |

## 13.3 Warranty

A 30-day warranty from each go-live covers Sev-1/Sev-2 defects against the signed baseline at no charge. The warranty excludes new requirements, enhancements, third-party/provider faults, issues from client-side configuration or data, and changes made outside Omara’s control.

## 13.4 Post-Warranty Support

Ongoing support, maintenance, managed hosting and Phase 2 enhancements are available under a separate Annual Maintenance/Support agreement, quoted on request.

# 14. Risk Management

| Risk | Mitigation |
| --- | --- |
| Scope creep across seven workstreams | Locked Phase 0 baseline + formal change control (Sections 8, 10). |
| Third-party / provider sandbox or go-live delays | Software built to documented interfaces; client procures credentials early; clock pauses on dependency (Sections 11, 12). |
| Regulatory/licensing delays affecting fintech go-live | Clear delineation that licensing is client-owned; software delivered ready-to-integrate (Section 12). |
| Late sign-offs / SPOC unavailability | Defined cadence, UAT windows and deemed-acceptance (Sections 4, 13). |
| Aggressive timeline vs. broad scope | Phase 1 MVP depth, dependency-sequenced waves, reusable design system, parallel streams (Sections 3, 5). |
| Integration risk (QmaxPay ↔ 1Q1Pay ↔ E-Mart/Fincomax) | QmaxPay built first; integration contracts fixed at Phase 0; staged environments. |

# 15. Commercial Terms & Conditions

## 15.1 Payment Terms

- Milestone invoices are payable within 7 days of invoice date unless otherwise agreed in the contract.

## 15.2 Intellectual Property

- On receipt of full payment, IP in the bespoke deliverables created for the client transfers to the client.

- Pre-existing tools, frameworks, libraries, reusable components and know-how remain the property of Omara Digitech and are licensed to the client for use within the deliverables.

- Third-party/open-source components remain under their respective licences.

## 15.3 Confidentiality & Data Protection

- Each party keeps the other’s confidential information secure and uses it only for the engagement.

- Omara handles client and end-user data under applicable Indian data-protection law and the agreed security posture; the client remains the data controller and is responsible for lawful collection and consent.

## 15.4 Limitation of Liability

- Omara’s aggregate liability under the engagement is capped at the total fees actually paid for the affected workstream.

- Neither party is liable for indirect, incidental, consequential, or loss-of-profit/data damages.

- Omara is not liable for losses arising from third-party services, provider outages, the client’s regulatory standing, or client-supplied data/configuration.

## 15.5 Timeline Contingencies & Force Majeure

- Dates assume on-time sign-offs, credentials and payments; client-side delay shifts the affected schedule by at least the delay period.

- Neither party is liable for delays caused by events beyond reasonable control (force majeure).

## 15.6 Termination

- Either party may terminate for material, uncured breach on 15 days’ written notice.

- On termination, the client pays for all work completed and in-progress to the termination date, including the current milestone pro-rata; accepted deliverables and their IP follow the payment terms above.

## 15.7 General

- This proposal forms the basis of a definitive agreement; in any conflict, the signed agreement prevails.

- Governing law and jurisdiction to be specified in the definitive agreement.

# 16. Why This Plan Wins

- Ecosystem fluency: the plan is built on the approved SRS baselines and respects the real ownership and integration map, so the payment rail is delivered before the products that depend on it.

- Discipline by design: Phase 1 MVP depth, explicit exclusions and a locked baseline make an ambitious scope genuinely deliverable in 4–5 months.

- Fast, visible value: six brand sites live in month one, the QmaxPay/E-Mart wave by month 2.5 — momentum the business can show stakeholders early.

- Cash tied to delivery: milestone payments track accepted value, de-risking spend for the client and focusing the team on shippable outcomes.

- Protected on both sides: clear change control, dependency and regulatory disclaimers, acceptance rules and warranty keep the engagement clean and predictable.

Strictly Private & Confidential — Omara Digitech Pvt. Ltd.

# Overview

Here's a feature table across all seven entities. For Rudranchali Organics and Omara Digitech the features reflect what a static corporate/brand website would carry; the rest are drawn from the requirements work already done in this project.

| Entity | Type | Key features |
| --- | --- | --- |
| Rudranjali Organics | Static website (parent co.) | Corporate brand homepage; promoter/brand story & values; group-structure section showcasing Omara Digitech and subsidiaries; organic product/category showcase; news/announcements; contact & enquiry form; responsive + SEO meta |
| Omara Digitech | Static website (tech subsidiary) | Ecosystem overview ("One Ecosystem. Endless Possibilities."); product portfolio (1Q1Pay, QmaxPay, Fincomax, E-Mart); solutions/services; vision–mission–values; credibility stats & why-choose-us; leadership/team; careers; partner/contact enquiry |
| QmaxPay | B2B API repository | API catalog (payments, payouts, recharge/BBPS, AEPS, KYC/verification); developer portal with docs, sandbox & API keys; single-provider-per-API routing; prepaid wallet; single-tier reseller onboarding; transaction ledger & reports; report-only margin config |
| 1Q1Pay | Retail fintech (B2C/B2B) | Aggregated services (AEPS, money transfer/DMT, BBPS, recharge, UPI/QR) running over QmaxPay APIs; single-tier Retailer→Customer channel; retailer-funded prepaid wallet; retailer/web/customer-app touchpoints; KYC onboarding; settlement & reports (22 MVP modules) |
| Fincomax | Marketplace + professional services | Upwork-style marketplace linking clients to verified pros (CA, CS, Lawyer, Accountant, Bookkeeper, CFA, CFO); quote-based engagement with milestone escrow; compliance engine (ROC, GST, income tax, TDS, PF/ESI, labour, FEMA); payments via 1Q1Pay; messaging, proposals, reviews. Phase 2: Fincomax Books |
| E-Mart | Multi-tier e-commerce | Distributor → Wholesaler/Master → Retailer → End-Customer chain; product catalog & ordering; warehousing/inventory; single payment gateway + COD; Indian GST billing; manual B2B onboarding verification; email/SMS/in-app notifications; web-only responsive (17 modules) |
| ERP | SaaS ops platform (under 1Q1Pay) | Phase-1 modules: LMS, CRM, HRMS, Inventory, Finance, Task & Team management; multi-tenant SaaS foundation (subscription/billing, RBAC, auth, super-admin, notifications); Phase 2 ~43 modules (operations, supply chain, manufacturing, sales, marketing) |

Want this exported as a branded Word doc in the same format as your other deliverables, or expanded into per-entity website sitemaps for the two static sites?

Got it — that flips two things in the hierarchy. Rudranchali Organics is actually the corporate parent above Omara Digitech (not a store on E-Mart), and E-Mart + the ERP suite both sit under 1Q1Pay as products rather than as a shared foundation. Here's the corrected structure.The chain now reads top-down: Rudranchali Organics owns Omara Digitech, which runs the three brands, and 1Q1Pay carries E-Mart and the ERP as its product line. The payment relationships are unchanged — QmaxPay is the engine feeding 1Q1Pay (and therefore E-Mart's checkout), and 1Q1Pay powers Fincomax's payment add-ons.

A couple of things to confirm so the picture is exact:

- Does Fincomax also sit under Omara Digitech as a peer brand to QmaxPay/1Q1Pay (as drawn), or does it belong somewhere else in the Rudranchali group?

- The ERP here is the same LMS/HRMS/CRM/Finance/Task SaaS we scoped earlier — confirm it's grouped as a 1Q1Pay product and not a standalone Omara offering.

Want me to add the audiences each brand serves, or keep it as a clean ownership-and-integration map?

Rudranjali Organics

Phase 1 6 websites

- Rudranjali Organics - Static website

- E-store mart - Ecommerce website with ability to manage

- Omara Digipay - Master website

- 1q1 Pay

- Fincomax

- Qmax

Modules in each website

- Rudranjali Organics - Static website with detail about the company, founder, vision/mission etc

- E-store mart - Ecommerce website with ability to manage

- Omara Digipay - Master website

# Emart

E-STORE MART

Multi-Tier E-Commerce Platform

Phase 1 Software Requirements Document

For Sign-Off

Omara Digitech Pvt. Ltd.

Version 1.0  |  Status: Draft — Pending Approval

# 1. Document Control

| Prepared for | Omara Digitech Pvt. Ltd. |
| --- | --- |
| Product line | E-Mart (Phase 1 B2C/B2B Platform) |
| Sourcing model | Hybrid (per-product/region Strict / Flexible toggle) |
| Scope | Phase 1 only — single end-to-end flow, all modules touched thinly |
| Version | 1.0 — initial draft |
| Status | Draft — Pending Approval |

# 2. Introduction & Scope

2.1 Purpose — This document defines the functional and non-functional requirements for the Phase 1 of E-Store Mart, an e-commerce platform that operates both a B2C storefront and a B2B multi-tier distribution chain (Distributor → Wholesaler/Master → Retailer → End Customer).

2.2 Phase 1 Objective — Deliver one coherent, working end-to-end flow: a Distributor lists stock, downstream tiers source it under a configurable mapping, customers purchase, payment and delivery complete, and an admin oversees the entire chain. Every module is present in thin form; depth and automation are deferred to later phases.

2.3 In Scope — The seventeen functional modules defined in Section 4, at Phase 1 depth.

2.4 Out of Scope (Phase 2+) — Mobile apps, partner API gateway, loyalty/rewards, AI forecasting & auto-replenishment, multi-language/multi-currency, and all per-module deferred items listed under each requirement.

Detailed List of Modules

## Softwares - 1 Admin (Web App).

## 1. User & Identity Management

- Five roles, each with a fixed admin-defined permission set

- Customers self-register and are active immediately

- B2B accounts (Distributor/Wholesaler/Retailer) self-register → land in "Pending Approval"

- Admin manually reviews uploaded PAN/GST docs → marks Approved or Rejected

- Login via mobile/email + OTP

- Profile holds business name, contact, GSTIN, one or more addresses

- Account states limited to: Pending, Active, Rejected

- No sub-users, no automated document validation

## 2. Multi-Tier Hierarchy & Sourcing

- Admin manually links each tier to its parent (R1 → W1 → D1)

- Each product (or region group) carries one setting: Strict or Flexible

- Strict = buy only from mapped parent; Flexible = buy from any eligible upstream

- This single toggle is what makes the platform "hybrid"

- No priority ordering, no auto-fallback if mapped seller is out of stock

- Mapping and toggle both managed from simple admin screens

## 3. Product Catalog

- Two-level category tree

- Each product: name, description, basic variant(s), SKU, HSN, price link, images

- Created via form or imported through a fixed-format Excel template

- Tier-submitted products stay inactive until admin approves; admin can create directly

- Product status: Active or Inactive only (Inactive = hidden from store/ordering)

- No per-tier visibility filtering beyond the sourcing toggle

## 4. Pricing & Margin

- One price per tier: Distributor, Wholesaler, Retailer, Customer (MRP/selling)

- Basic quantity slab supported (e.g. 10+ units = lower price)

- Optional region flag for a manual alternate price set

- No future-dated pricing, no approval step — edits take effect immediately

- Margin is implicit in the gap between tier prices

## 5. Inventory & Warehouse

- Single quantity figure held per tier/location

- Two manual actions: inward (add received stock) and outward (deduct on dispatch)

- Stock reserved on order placement; released on cancellation

- Low-stock alert (in-app + email) at an admin-set per-product threshold

- No inter-warehouse transfers, batch/expiry, or formal reconciliation

- Corrections via direct stock adjustment entry

## 6. Storefront / Customer

- Keyword search, category browse, basic filters (category, price, brand)

- Product detail page: variants, price, images, add-to-cart

- Cart with quantity change and removal

- Checkout for registered users only (address + coupon + payment + confirm)

- Order history with one-click reorder

- No wishlist, reviews, or guest checkout

## 7. Order Management

- Orders from customers (B2C) or B2B tiers buying upstream

- Auto-routed to correct seller per tier mapping + Strict/Flexible toggle

- Stock and (for B2B) credit checked; seller confirms or rejects

- Fixed status lifecycle: Placed → Confirmed → Shipped → Delivered (manual transitions)

- GST-compliant invoice generated on confirmation

- Cancellation allowed before shipping → releases reserved stock

- No partial shipments or returns flow

## 8. Procurement / Purchase

- B2B buy-up as a purchase order (Retailer → Wholesaler, Wholesaler → Distributor)

- Upstream seller sees the PO and fulfills manually

- PO records intent and gets marked fulfilled

- No auto-reorder, goods-receipt note, or purchase returns

## 9. Payment & Wallet

- Two checkout methods: single online gateway (QmaxPay/1Q1Pay) + COD

- Each B2B tier has a credit ledger with a static admin-set credit limit

- B2B orders draw against available credit; blocked if limit exceeded

- Refunds processed manually by admin, recorded as ledger entry

- No automated settlement cycle, aging engine, or second gateway

## 10. Logistics & Delivery

- Pin-code serviceability check at checkout

- Flat or zone-based delivery charge (pre-configured by admin)

- Manual status update as shipped/delivered

- Self-pickup option

- No courier API, live tracking, or delivery-proof capture

## 11. Commission, Incentives & Settlement

- Simple per-tier commission (flat or percentage, admin-defined)

- Surfaced as a report of earnings per period

- Informational only — nothing auto-paid, no settlement statement

## 12. Promotions & Marketing

- Coupon codes (flat or %, with validity window, applied at checkout)

- Homepage banner upload/swap by admin

- No scheme builder, campaigns, or outbound marketing

## 13. Reports & Analytics

- Role-scoped dashboard (orders, sales, outstanding totals)

- Four core reports: sales by tier/product, inventory, GST summary, commission

- Date-filterable, Excel export

- No trend charts, slow-mover analysis, or scheduled delivery

## 14. Tax & Compliance

- Admin configures GST rates

- Auto CGST/SGST (intra-state) vs IGST (inter-state) based on buyer/seller state

- HSN code per product; GST-compliant invoice on confirmed orders

- No e-invoice/e-way bill or TCS/TDS handling

## 15. Notifications

- Fixed triggers: order placed, confirmed, shipped, and B2B account approved/rejected

- Channels: email + SMS + in-app alert

- Fixed templates, no WhatsApp/push, no user preferences

## 16. Admin Control Panel

- Master settings (GST rates, delivery zones, thresholds)

- Role/permission configuration

- Full user management (approve, suspend, edit)

- CMS for static policy pages (Terms, Privacy, About, FAQ)

- Basic audit log of key actions

- No feature toggles, system-health view, or backup UI

## 17. Support & Ticketing

- Raise ticket with subject, category, message

- Admin sees queue, replies in thread, marks Open/Closed

- No SLA, escalation, assignment routing, or knowledge base

# 3. Assumptions & Constraints

• Web-based responsive platform (desktop + mobile browser); no native apps in Phase 1.

• Single payment gateway (QmaxPay / 1Q1Pay) plus Cash on Delivery.

• Indian tax regime — GST (CGST / SGST / IGST).

• B2B onboarding involves manual admin verification of documents.

• Sourcing logic is a per-product/region toggle, not a rules-priority engine.

• Notifications limited to email, SMS, and in-app.

# 4. Functional Requirements

Requirement IDs follow the pattern EM-[Module]-[Number].

## 4.1 User & Identity Management (EM-UM)

• EM-UM-01 — System shall support five roles: Super Admin, Distributor, Wholesaler/Master, Retailer, Customer.

• EM-UM-02 — Customers self-register and are activated immediately.

• EM-UM-03 — B2B accounts self-register into a Pending Approval state.

• EM-UM-04 — Admin shall manually review uploaded PAN/GST documents and Approve or Reject.

• EM-UM-05 — Login via mobile/email with OTP.

• EM-UM-06 — Profile stores business name, contact, GSTIN, and one or more addresses.

• EM-UM-07 — Account states limited to Pending, Active, Rejected.

• Excluded (Phase 2+): sub-users, 2FA, automated KYC validation.

## 4.2 Multi-Tier Hierarchy & Sourcing (EM-HS)

• EM-HS-01 — Admin shall manually map each tier to its parent.

• EM-HS-02 — Each product or region group carries a single sourcing setting: Strict or Flexible.

• EM-HS-03 — Strict restricts purchasing to the mapped parent; Flexible permits any eligible upstream.

• EM-HS-04 — No auto-fallback on stock-out; unavailable items simply show no availability.

• Excluded (Phase 2+): rules-priority engine, tree visualization, bulk re-mapping.

## 4.3 Product Catalog (EM-PC)

• EM-PC-01 — Two-level category tree.

• EM-PC-02 — Product attributes: name, description, basic variant(s), SKU, HSN, price link, images.

• EM-PC-03 — Product creation via form or fixed-format Excel import.

• EM-PC-04 — Tier-submitted products remain inactive pending admin approval; admin may create directly.

• EM-PC-05 — Product status: Active or Inactive (Inactive hidden from store/ordering).

• Excluded (Phase 2+): per-tier visibility rules, advanced attributes, draft workflows.

## 4.4 Pricing & Margin (EM-PR)

• EM-PR-01 — One price per tier (Distributor, Wholesaler, Retailer, Customer/MRP).

• EM-PR-02 — Basic quantity slab supported.

• EM-PR-03 — Optional region flag for a manual alternate price set.

• EM-PR-04 — Price edits take effect immediately (no approval/scheduling).

• Excluded (Phase 2+): future-dated pricing, margin-rule automation, change history.

## 4.5 Inventory & Warehouse (EM-IN)

• EM-IN-01 — Single stock quantity per tier/location.

• EM-IN-02 — Manual inward and outward stock actions.

• EM-IN-03 — Stock reserved on order; released on cancellation.

• EM-IN-04 — Low-stock alert (in-app + email) at admin-set threshold.

• EM-IN-05 — Corrections via direct stock adjustment entry.

• Excluded (Phase 2+): multi-warehouse transfer, batch/expiry, serial tracking, reconciliation logs.

## 4.6 Storefront / Customer (EM-SF)

• EM-SF-01 — Keyword search, category browse, basic filters (category, price, brand).

• EM-SF-02 — Product detail page with variants, price, images, add-to-cart.

• EM-SF-03 — Cart with quantity change and removal.

• EM-SF-04 — Checkout for registered users (address + coupon + payment + confirm).

• EM-SF-05 — Order history with one-click reorder.

• Excluded (Phase 2+): wishlist, reviews, guest checkout.

## 4.7 Order Management (EM-OM)

• EM-OM-01 — Orders from customers (B2C) and B2B tiers buying upstream.

• EM-OM-02 — Auto-routing to correct seller per tier mapping + sourcing toggle.

• EM-OM-03 — Stock and B2B credit checked before confirmation.

• EM-OM-04 — Seller confirms or rejects order.

• EM-OM-05 — Status lifecycle: Placed → Confirmed → Shipped → Delivered (manual transitions).

• EM-OM-06 — GST-compliant invoice generated on confirmation.

• EM-OM-07 — Cancellation allowed before shipping; releases reserved stock.

• Excluded (Phase 2+): partial/split fulfillment, returns/replacement.

## 4.8 Procurement / Purchase (EM-PO)

• EM-PO-01 — B2B purchase order from a tier to its upstream parent.

• EM-PO-02 — Upstream seller views PO and fulfills manually.

• EM-PO-03 — PO marked fulfilled on completion.

• Excluded (Phase 2+): auto-reorder, goods-receipt note, purchase returns.

## 4.9 Payment & Wallet (EM-PM)

• EM-PM-01 — Online gateway (QmaxPay / 1Q1Pay) and COD at checkout.

• EM-PM-02 — Credit ledger per B2B tier with static admin-set credit limit.

• EM-PM-03 — B2B orders draw on available credit; blocked when limit exceeded.

• EM-PM-04 — Refunds processed manually and recorded as ledger entries.

• Excluded (Phase 2+): automated settlement, aging engine, multi-gateway.

## 4.10 Logistics & Delivery (EM-LD)

• EM-LD-01 — Pin-code serviceability check at checkout.

• EM-LD-02 — Flat or zone-based delivery charge (admin pre-configured).

• EM-LD-03 — Manual shipped/delivered status update.

• EM-LD-04 — Self-pickup option.

• Excluded (Phase 2+): courier API, live tracking, delivery-proof capture.

## 4.11 Commission, Incentives & Settlement (EM-CM)

• EM-CM-01 — Per-tier commission (flat or percentage, admin-defined).

• EM-CM-02 — Earnings surfaced as a period report.

• EM-CM-03 — Informational only; no auto-payout or settlement statement.

• Excluded (Phase 2+): target incentives, payout generation, hold/release.

## 4.12 Promotions & Marketing (EM-PT)

• EM-PT-01 — Coupon codes (flat or %, validity window, applied at checkout).

• EM-PT-02 — Homepage banner upload/swap.

• Excluded (Phase 2+): scheme builder, campaigns, outbound marketing.

## 4.13 Reports & Analytics (EM-RP)

• EM-RP-01 — Role-scoped dashboard (orders, sales, outstanding totals).

• EM-RP-02 — Core reports: sales by tier/product, inventory, GST summary, commission.

• EM-RP-03 — Date-filterable with Excel export.

• Excluded (Phase 2+): trend analytics, slow-mover detection, scheduled reports.

## 4.14 Tax & Compliance (EM-TX)

• EM-TX-01 — Admin configures GST rates.

• EM-TX-02 — Auto CGST/SGST (intra-state) vs IGST (inter-state) by buyer/seller state.

• EM-TX-03 — HSN per product; GST-compliant invoice on confirmed orders.

• Excluded (Phase 2+): e-invoice/e-way bill, TCS/TDS.

## 4.15 Notifications (EM-NT)

• EM-NT-01 — Triggers: order placed, confirmed, shipped, B2B account approved/rejected.

• EM-NT-02 — Channels: email, SMS, in-app.

• Excluded (Phase 2+): WhatsApp/push, template editor, user preferences.

## 4.16 Admin Control Panel (EM-AD)

• EM-AD-01 — Master settings (GST rates, delivery zones, thresholds).

• EM-AD-02 — Role/permission configuration.

• EM-AD-03 — User management (approve, suspend, edit).

• EM-AD-04 — CMS for static policy pages (Terms, Privacy, About, FAQ).

• EM-AD-05 — Basic audit log of key actions.

• Excluded (Phase 2+): feature toggles, system-health view, backup UI.

## 4.17 Support & Ticketing (EM-ST)

• EM-ST-01 — Raise ticket (subject, category, message).

• EM-ST-02 — Admin views queue, replies in thread, marks Open/Closed.

• Excluded (Phase 2+): SLA, escalation, assignment routing, knowledge base.

# 5. Non-Functional Requirements

• NFR-01 Platform: Responsive web (desktop + mobile browser).

• NFR-02 Security: OTP authentication, RBAC, encrypted credentials, secure payment handling.

• NFR-03 Performance: Catalog/listing pages load within acceptable web norms under expected Phase 1 load.

• NFR-04 Availability: Single-region hosting; routine backups.

• NFR-05 Compliance: GST-compliant invoicing; PCI handled via the payment gateway.

• NFR-06 Auditability: Key admin actions logged.

• NFR-07 Usability: Role-appropriate dashboards; consistent UI.

# 6. Acceptance Criteria (Phase 1 Sign-off Gate)

Phase 1 is accepted when a single end-to-end flow is demonstrable:

1. A Distributor is onboarded and approved, and lists a product with tier pricing and stock.

2. A Retailer (mapped, under a sourcing toggle) raises an order/PO and it routes to the correct upstream seller.

3. A Customer places and pays for an order; a GST-compliant invoice is generated with correct tax breakup.

4. Stock decrements, the credit ledger updates, and order status moves through the full lifecycle to Delivered.

5. Notifications fire on the defined triggers, and the admin can view orders, sales, inventory, and commission reports.

# 7. Build Sprint Sequencing

The Phase 1 is sequenced into eight sprints ordered by dependency — each builds on what the previous delivered, ending in a sign-off demo. Sprint length is a delivery decision (typically 2 weeks each).

| Sprint | Focus | Modules / Requirement Sets |
| --- | --- | --- |
| Sprint 0 | Foundation | Project setup, architecture, DB schema, hosting, auth scaffolding |
| Sprint 1 | Identity & Hierarchy | EM-UM, EM-HS, EM-AD (core admin: users, roles, settings) |
| Sprint 2 | Catalog, Pricing & Stock | EM-PC, EM-PR, EM-IN |
| Sprint 3 | Storefront & Orders | EM-SF, EM-OM |
| Sprint 4 | B2B Flow & Money | EM-PO, EM-PM, EM-TX |
| Sprint 5 | Fulfillment & Comms | EM-LD, EM-NT |
| Sprint 6 | Revenue & Reporting | EM-CM, EM-PT, EM-RP |
| Sprint 7 | Support & Hardening | EM-ST, UAT, bug-fix, acceptance demo & sign-off |

Dependency logic: identity and hierarchy must exist before catalog/pricing can be tier-scoped; catalog and stock must exist before orders; orders must exist before B2B procurement, payment, and tax; fulfillment and notifications layer onto confirmed orders; commission, promotions, and reporting consume completed transaction data; support and hardening close the Phase 1.

# 1q1 Pay

1Q1Pay

One QR. One Payment. All Solutions.

Software Requirements Specification

Phase 1

Omara Digitech Pvt. Ltd.

Version 2.0    |    June 2026    |    Status: Draft for Sign-off

# Table of Contents

# Document Control

| Field | Detail |
| --- | --- |
| Document | 1Q1Pay — Software Requirements Specification (Phase 1) |
| Product | 1Q1Pay — Fintech & Payment Services Platform |
| Owner | Omara Digitech Pvt. Ltd. |
| Version | 2.0 |
| Date | June 2026 |
| Status | Draft for Sign-off |
| ID Convention | 1QP-[Module]-[Number] |

| Version | Summary |
| --- | --- |
| 1.0 | Initial Phase 1 requirements baseline — module structure, architectural decisions, functional requirements, Phase 1 / Phase 2 split and build sequence. |
| 1.1 | Expanded functional specification — per-module purpose and dependency notes added to Section 4. |
| 2.0 | Professional-services marketplace removed from 1Q1Pay scope (relocated to Fincomax). 1Q1Pay reduced to a fintech & payment services platform — related modules, roles, decisions, requirements and build sequence updated. |

# 1.  Introduction

## 1.1  Purpose

This document defines the requirements for Phase 1 of 1Q1Pay, a product of Omara Digitech Pvt. Ltd. It establishes the agreed module structure, architectural decisions, functional scope and build sequence, and serves as the sign-off baseline for design and development.

## 1.2  Product Overview

1Q1Pay is a fintech and payment services platform. It acts as an aggregator, orchestrating retail payment and banking transactions through QmaxPay APIs and delivering them to end customers through a single-tier retailer network.

Core services include AEPS and Micro ATM, domestic money transfer, BBPS and bill payments, recharge, and UPI / QR acceptance. A shared platform spine — access, wallet, retailer management, settlement, reporting and administration — supports these services.

Note: the professional-services marketplace previously associated with this platform is delivered under Fincomax and is out of scope for 1Q1Pay.

## 1.3  Scope (Phase 1)

## A · Core Platform & Access

USR · User, Role & Access Management — identity and permission backbone for every actor.

- Role model: Super Admin, Platform Ops, Retailer, Customer, Service Provider, each with a distinct permission set

- Registration & login via mobile/email + OTP; password/PIN credentials

- RBAC enforced at module and action level (a Retailer can transact but not configure pricing)

- Per-role profile management (business details for retailers/providers, basic for customers)

- Session handling across devices with timeout and forced-logout

- Self-service password/PIN reset & recovery

KYC · Onboarding & KYC — verify and activate every retailer, provider, and regulated-txn customer.

- Retailer onboarding: application → document upload → verification → activation

- Customer KYC captured only where a regulated service (AEPS/DMT) requires it

- Provider credential verification — professional membership/registration numbers + certificates

- Document upload with format/expiry validation (PAN, Aadhaar, shop & bank proof)

- KYC status tracking with re-KYC triggers on expiry or data change

- Central admin review/approval queue with accept/reject + reason

RET · Retailer Management — manage the retailer base directly under the platform (single-tier).

- Searchable retailer directory with KYC status

- Lifecycle controls: activate / suspend / deactivate

- Wallet linkage and per-retailer transaction limits

- Commission-plan assignment

- Basic performance dashboard (volume, earnings)

WAL · Wallet & Balance Management — prepaid balance engine funding all retailer fintech transactions.

- One prepaid wallet per retailer

- Top-up via admin credit, payment gateway, or bank transfer (with approval)

- Double-entry ledger with running balance and full trail

- Hold/release for in-flight transactions (funds locked until confirmation/refund)

- Low-balance alerts and thresholds

- Statement with export

## B · Fintech & Payment Services (orchestrated over QmaxPay)

QMX · QmaxPay Integration Layer — the single rail every fintech module uses to reach providers.

- QmaxPay API authentication & key/credential management

- Unified request/response handler shared by all Group B modules

- Timeout, retry and failure handling with consistent error semantics

- Transaction ID mapping (1Q1Pay ↔ QmaxPay) for end-to-end traceability

- Response normalization into common status codes

- Reconciliation feed against QmaxPay as the single counterparty

- Dependency: every fintech service's availability is bounded by this layer

AEP · AEPS & Micro ATM — Aadhaar-authenticated cash services at the retailer counter.

- AEPS authentication via Aadhaar + biometric capture

- Cash withdrawal, balance enquiry, mini statement

- Receipt and status display

- Daily limit enforcement

- Dependency: biometric device certification

DMT · Domestic Money Transfer — send money to any bank account from the counter.

- Beneficiary registration with penny-drop validation

- IMPS/NEFT transfer execution

- Real-time status tracking

- Refund/failure handling with wallet reversal

- Sender KYC and limit checks

- Receipt generation

BBP · BBPS & Bill Payments — pay utility and recurring bills across BBPS billers.

- Biller category and biller fetch

- Bill fetch and amount validation

- Bill payment execution

- Status and receipt

- BBPS complaint/dispute raising

RCH · Recharge — prepaid recharges across telecom and allied services.

- Operator and circle auto-detection

- Mobile and DTH recharge

- FASTag recharge

- Plan browsing

- Status and receipt

UPI · UPI & QR Acceptance — let retailers collect digital payments into their wallet.

- Static and dynamic QR generation

- UPI collect requests

- Payment status callback handling

- Settlement of collected funds to the retailer wallet

- Transaction history

IDV · Identity & Utility Services — verification utilities supporting onboarding and regulated txns.

- e-KYC / Aadhaar verification

- PAN verification

- Verification result logging for audit

- DSC issuance request → Phase 2

TRV · Travel Services (Phase 2) — flight/bus/train/hotel search, booking & ticketing, cancellation/refund, booking history.

PAN · PAN Card Services (Phase 2) — new PAN application, correction/reprint, status tracking.

INS · Insurance Services (Phase 2) — motor/health/life product catalog, quote & purchase, policy retrieval.

LON · Loan & Credit Services (Phase 2) — product listing & eligibility, lead capture, application status.

## D · Commercial, Settlement & Operations

PRC · Pricing, Commission & Margin Engine — define what things cost and who earns what.

- Fintech retail pricing as a markup over QmaxPay wholesale cost

- Retailer commission plans per service

- Marketplace commission % configuration

- Slab/tier and effective-dated pricing → Phase 2

STL · Settlement & Payout — move money out to retailers and providers.

- Retailer commission accrual and disbursement

- Provider payout processing

- Settlement reports and cycles

- Failed-payout handling and retry

RPT · Reporting, MIS & Analytics — visibility across both engines.

- Transaction reports by service, retailer, date

- Revenue and commission reports

- Marketplace engagement reports

- Export to PDF/Excel

- Performance MIS → Phase 2

NOT · Notifications & Communications — keep all actors informed.

- SMS (transaction, OTP, status)

- Email

- In-app notifications

- Template management → Phase 2

## E · Administration, Compliance & Support

ADM · Admin Console & Platform Configuration — the control room for operators.

- Central admin dashboard

- Service enable/disable toggles

- Master data and configuration management

- User/role administration

CMP · Compliance, Audit & Security — keep the platform within regulatory and security bounds.

- Transaction limits and velocity checks

- AML/KYC enforcement

- Audit logs of critical actions

- Data security and encryption

- Regulatory reporting hooks → Phase 2

SUP · Support, Ticketing & Helpdesk — resolve user issues.

- Ticket creation and tracking

- Category/priority routing

- SLA & escalation, knowledge base → Phase 2

distributor tier, and advanced operations features are deferred to Phase 2 (see Section 5).

## 1.4  Definitions & Abbreviations

| Term | Meaning |
| --- | --- |
| AEPS | Aadhaar Enabled Payment System |
| DMT | Domestic Money Transfer |
| BBPS | Bharat Bill Payment System |
| IMPS / NEFT | Immediate Payment Service / National Electronic Funds Transfer |
| UPI | Unified Payments Interface |
| e-KYC / KYC | Electronic / Know Your Customer verification |
| DSC | Digital Signature Certificate |
| AML | Anti-Money Laundering |
| RBAC | Role-Based Access Control |
| MIS | Management Information System |

# 2.  Architectural Decisions

The following decisions are locked for Phase 1 and govern the requirements in this document.

| Decision Area | Resolution |
| --- | --- |
| Fintech provider connectivity | Consume QmaxPay APIs — fintech modules are an orchestration / UX / margin layer; no direct provider integration in Phase 1. |
| Channel model | Single-tier: Retailer → Customer. Distributor tier and multi-level overrides deferred to Phase 2. |
| Wallet model | Prepaid. Fintech is retailer-funded — retailer wallet, walk-in customers. Customer wallet deferred to Phase 2. |
| Requirement ID convention | 1QP-[Module]-[Number]. |
| Dependency constraint | 1Q1Pay fintech availability is bounded by QmaxPay; reconciliation is against a single counterparty. |

# 3.  User Roles

| Role | Description |
| --- | --- |
| Super Admin | Full platform control (Omara Digitech) — configuration, oversight, master data. |
| Platform Ops | Day-to-day operations — KYC approvals and support. |
| Retailer | Outlet operator; offers fintech services to walk-in customers via a prepaid wallet. |
| Customer | End user; consumes fintech services through a retailer. |

# 4.  Functional Specification

Each module is presented with its purpose, any key dependencies, and a table of its requirements. Every requirement is marked Phase 1 or Phase 2; Phase 2 items appear for traceability but are out of Phase 1 scope.

## 4.1  Group A — Core Platform & Access

### User, Role & Access Management (USR)

Purpose:  Identity and permission backbone for every actor on the platform.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-USR-001 | Role definitions: Super Admin, Platform Ops, Retailer, Customer | Phase 1 |
| 1QP-USR-002 | Registration & login (mobile / email + OTP) | Phase 1 |
| 1QP-USR-003 | Role-based access control at module and action level | Phase 1 |
| 1QP-USR-004 | Profile management per role | Phase 1 |
| 1QP-USR-005 | Session & multi-device management | Phase 1 |
| 1QP-USR-006 | Password / PIN reset & recovery | Phase 1 |

### Onboarding & KYC (KYC)

Purpose:  Verify and activate every retailer and regulated-transaction customer before they transact.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-KYC-001 | Retailer onboarding workflow (apply → upload → verify → activate) | Phase 1 |
| 1QP-KYC-002 | Customer KYC for regulated transactions (Aadhaar / PAN) | Phase 1 |
| 1QP-KYC-004 | Document upload & validation | Phase 1 |
| 1QP-KYC-005 | KYC status tracking & re-KYC triggers | Phase 1 |
| 1QP-KYC-006 | Admin review / approval queue | Phase 1 |

### Retailer Management (RET)

Purpose:  Manage the retailer base directly under the platform (single-tier).

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-RET-001 | Retailer directory & profiles | Phase 1 |
| 1QP-RET-002 | Activation / suspension / deactivation | Phase 1 |
| 1QP-RET-003 | Wallet linkage & limits | Phase 1 |
| 1QP-RET-004 | Commission plan assignment | Phase 1 |
| 1QP-RET-005 | Retailer performance dashboard (basic) | Phase 1 |

### Wallet & Balance Management (WAL)

Purpose:  Prepaid balance engine that funds all retailer fintech transactions.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-WAL-001 | Prepaid wallet per retailer | Phase 1 |
| 1QP-WAL-002 | Load / top-up (admin credit, payment gateway, bank transfer + approval) | Phase 1 |
| 1QP-WAL-003 | Ledger (credit / debit, running balance) | Phase 1 |
| 1QP-WAL-004 | Hold / release for in-flight transactions | Phase 1 |
| 1QP-WAL-005 | Low-balance alerts & thresholds | Phase 1 |
| 1QP-WAL-006 | Wallet statement & export | Phase 1 |

## 4.2  Group B — Fintech & Payment Services (orchestrated over QmaxPay)

### QmaxPay Integration Layer (QMX)

Purpose:  The single rail through which every fintech module reaches providers, isolating QmaxPay specifics from the rest of the platform.

Dependency:  All fintech services depend on this layer; its availability bounds theirs.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-QMX-001 | QmaxPay API authentication & credential management | Phase 1 |
| 1QP-QMX-002 | Unified request / response handler for all fintech services | Phase 1 |
| 1QP-QMX-003 | Timeout, retry & failure handling | Phase 1 |
| 1QP-QMX-004 | Transaction ID mapping (1Q1Pay ↔ QmaxPay) | Phase 1 |
| 1QP-QMX-005 | Response normalization & status codes | Phase 1 |
| 1QP-QMX-006 | Reconciliation feed (single counterparty) | Phase 1 |

### AEPS & Micro ATM (AEP)

Purpose:  Aadhaar-authenticated cash services for walk-in customers at the retailer counter.

Dependency:  Requires biometric device certification (external dependency).

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-AEP-001 | AEPS authentication (Aadhaar + biometric) | Phase 1 |
| 1QP-AEP-002 | Cash withdrawal | Phase 1 |
| 1QP-AEP-003 | Balance enquiry | Phase 1 |
| 1QP-AEP-004 | Mini statement | Phase 1 |
| 1QP-AEP-005 | Receipt & status | Phase 1 |
| 1QP-AEP-006 | Daily limit enforcement | Phase 1 |

### Domestic Money Transfer (DMT)

Purpose:  Send money to any bank account from the retailer counter.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-DMT-001 | Beneficiary registration & validation (penny-drop) | Phase 1 |
| 1QP-DMT-002 | IMPS / NEFT transfer | Phase 1 |
| 1QP-DMT-003 | Status tracking | Phase 1 |
| 1QP-DMT-004 | Refund / failure handling | Phase 1 |
| 1QP-DMT-005 | Sender KYC & limit checks | Phase 1 |
| 1QP-DMT-006 | Receipt generation | Phase 1 |

### BBPS & Bill Payments (BBP)

Purpose:  Pay utility and recurring bills across BBPS billers.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-BBP-001 | Biller category & biller fetch | Phase 1 |
| 1QP-BBP-002 | Bill fetch & validation | Phase 1 |
| 1QP-BBP-003 | Bill payment | Phase 1 |
| 1QP-BBP-004 | Status & receipt | Phase 1 |
| 1QP-BBP-005 | BBPS complaint / dispute raise | Phase 1 |

### Recharge (RCH)

Purpose:  Prepaid recharges across telecom and allied services.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-RCH-001 | Operator & circle detection | Phase 1 |
| 1QP-RCH-002 | Mobile / DTH recharge | Phase 1 |
| 1QP-RCH-003 | FASTag recharge | Phase 1 |
| 1QP-RCH-004 | Plan browsing | Phase 1 |
| 1QP-RCH-005 | Status & receipt | Phase 1 |

### UPI & QR Acceptance (UPI)

Purpose:  Let retailers collect digital payments via UPI / QR into their wallet.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-UPI-001 | Static / dynamic QR generation | Phase 1 |
| 1QP-UPI-002 | Collect request | Phase 1 |
| 1QP-UPI-003 | Payment status callback | Phase 1 |
| 1QP-UPI-004 | Settlement to retailer wallet | Phase 1 |
| 1QP-UPI-005 | Transaction history | Phase 1 |

### Identity & Utility Services (IDV)

Purpose:  Verification utilities that support onboarding and regulated transactions.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-IDV-001 | e-KYC / Aadhaar verification | Phase 1 |
| 1QP-IDV-002 | PAN verification | Phase 1 |
| 1QP-IDV-004 | Verification result logging | Phase 1 |
| 1QP-IDV-003 | Digital Signature (DSC) issuance request | Phase 2 |

## 4.3  Group C — Commercial, Settlement & Operations

### Pricing, Commission & Margin Engine (PRC)

Purpose:  Define what services cost and who earns what.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-PRC-001 | Fintech retail pricing (markup over QmaxPay wholesale cost) | Phase 1 |
| 1QP-PRC-002 | Retailer commission plans per service | Phase 1 |
| 1QP-PRC-004 | Slab / tier configuration | Phase 2 |
| 1QP-PRC-005 | Effective-dated pricing | Phase 2 |

### Settlement & Payout (STL)

Purpose:  Move money out to retailers.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-STL-001 | Retailer commission accrual & disbursement | Phase 1 |
| 1QP-STL-003 | Settlement reports & cycles | Phase 1 |
| 1QP-STL-004 | Failed payout handling | Phase 1 |

### Reporting, MIS & Analytics (RPT)

Purpose:  Provide visibility across the platform.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-RPT-001 | Transaction reports (by service, retailer, date) | Phase 1 |
| 1QP-RPT-002 | Revenue & commission reports | Phase 1 |
| 1QP-RPT-005 | Export (PDF / Excel) | Phase 1 |
| 1QP-RPT-004 | Retailer performance MIS | Phase 2 |

### Notifications & Communications (NOT)

Purpose:  Keep all actors informed across channels.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-NOT-001 | SMS notifications (transaction, OTP, status) | Phase 1 |
| 1QP-NOT-002 | Email notifications | Phase 1 |
| 1QP-NOT-003 | In-app notifications | Phase 1 |
| 1QP-NOT-004 | Template management | Phase 2 |

## 4.4  Group D — Administration, Compliance & Support

### Admin Console & Platform Configuration (ADM)

Purpose:  The control room for platform operators.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-ADM-001 | Central admin dashboard | Phase 1 |
| 1QP-ADM-002 | Service enable / disable toggles | Phase 1 |
| 1QP-ADM-003 | Master data & configuration management | Phase 1 |
| 1QP-ADM-004 | User / role administration | Phase 1 |

### Compliance, Audit & Security (CMP)

Purpose:  Keep the platform within regulatory and security bounds.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-CMP-001 | Transaction limits & velocity checks | Phase 1 |
| 1QP-CMP-002 | AML / KYC enforcement | Phase 1 |
| 1QP-CMP-003 | Audit logs (critical actions) | Phase 1 |
| 1QP-CMP-004 | Data security & encryption | Phase 1 |
| 1QP-CMP-005 | Regulatory reporting hooks | Phase 2 |

### Support, Ticketing & Helpdesk (SUP)

Purpose:  Resolve user issues.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-SUP-001 | Ticket creation & tracking | Phase 1 |
| 1QP-SUP-002 | Category / priority routing | Phase 1 |
| 1QP-SUP-003 | SLA & escalation | Phase 2 |
| 1QP-SUP-004 | Knowledge base / FAQ | Phase 2 |

# 5.  Phase 2 Backlog

Modules and features deferred from Phase 1, carried from the locked architectural decisions.

## 5.1  Deferred Modules

### Travel Services (TRV)

Purpose:  Travel booking as a value-added retail service.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-TRV-001 | Search (flight / bus / train / hotel) | Phase 2 |
| 1QP-TRV-002 | Booking & ticketing | Phase 2 |
| 1QP-TRV-003 | Cancellation & refund | Phase 2 |
| 1QP-TRV-004 | Booking history & vouchers | Phase 2 |

### PAN Card Services (PAN)

Purpose:  PAN application services at the retailer counter.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-PAN-001 | New PAN application | Phase 2 |
| 1QP-PAN-002 | Correction / reprint | Phase 2 |
| 1QP-PAN-003 | Application status tracking | Phase 2 |

### Insurance Services (INS)

Purpose:  Sell partner insurance products through retailers.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-INS-001 | Product catalog (motor / health / life) | Phase 2 |
| 1QP-INS-002 | Quote & purchase | Phase 2 |
| 1QP-INS-003 | Policy status & document retrieval | Phase 2 |

### Loan & Credit Services (LON)

Purpose:  Originate loan and credit leads.

| Req. ID | Requirement | Status |
| --- | --- | --- |
| 1QP-LON-001 | Product listing & eligibility | Phase 2 |
| 1QP-LON-002 | Lead capture & application | Phase 2 |
| 1QP-LON-003 | Application status tracking | Phase 2 |

## 5.2  Deferred Features (within Phase 1 modules)

• Identity & Utility: Digital Signature (DSC) issuance — 1QP-IDV-003

• Pricing: slab / tier configuration (1QP-PRC-004); effective-dated pricing (1QP-PRC-005)

• Operations: retailer performance MIS (1QP-RPT-004); notification templates (1QP-NOT-004); regulatory reporting hooks (1QP-CMP-005); SLA & escalation (1QP-SUP-003); knowledge base (1QP-SUP-004)

• Channel: distributor tier, territory mapping, multi-level override commissions

# 6.  Build Sequence (Indicative)

A proposed sprint sequence for the Phase 1 scope. Sequencing is open to adjustment during planning.

| Sprint | Focus | Modules |
| --- | --- | --- |
| 1 | Foundation | USR, ADM (base), CMP (security & audit baseline) |
| 2 | Onboarding & Wallet | KYC, RET, WAL |
| 3 | QmaxPay integration & first rails | QMX, RCH, BBP |
| 4 | Money movement & identity | DMT, UPI, IDV (e-KYC, PAN verify) |
| 5 | AEPS | AEP (+ biometric device certification) |
| 6 | Money-out & pricing | STL, PRC |
| 7 | Visibility & support | RPT, NOT, SUP |
| 8 | Hardening, UAT, compliance review, go-live | All — stabilization |

Note: AEPS (Sprint 5) carries an external dependency on biometric device certification; if certification timelines slip, AEP can be decoupled and shipped as a fast-follow without blocking the remaining sprints.

# Qmax Pay - API Panel

QmaxPay

API Aggregator Repository

API Infrastructure for Digital Payments

Phase 1 Software Requirements Document

Version 1.0  |  For Sign-off

Omara Digitech Pvt. Ltd.

One Ecosystem. Endless Possibilities.

# 1. Overview & Scope of work

QmaxPay is a B2B aggregator API repository. It catalogues APIs (payments, payouts, recharge/BBPS, AEPS, verification/KYC, and more), maps each to an upstream provider, and resells access to developers, merchants, and resellers through a managed panel with prepaid wallet billing and white-label reselling.

This document defines Phase 1 only. Anything listed under Out of Scope is reserved for Phase 2 and must not be built in the Phase 1.

## 1. User & Identity Management

- Three roles only: Super Admin, Reseller, Developer/Merchant

- Self-registration form: name, business name, mobile, email, PAN, GSTIN

- New B2B accounts land in Pending; admin reviews uploaded PAN/GST → marks Active or Rejected

- Login via mobile/email + OTP

- Profile holds business name, contact, GSTIN, one address

- Account states limited to: Pending, Active, Rejected

- No sub-users, no staff accounts, no automated KYC validation, no 2FA

## 2. API Repository / Catalog Management

- Admin-maintained list of APIs, each with: name, category, description, status (Live/Inactive)

- One production endpoint URL per API

- A linked documentation reference per API (points to the doc page in Module 10)

- Merchants browse only Live APIs they're entitled to

- No versioning, no beta/deprecated states, no self-service publishing

## 3. Provider / Upstream Aggregation Engine

- Each API mapped to exactly one upstream provider

- Admin stores provider credentials and the base (cost) price per API

- Manual enable/disable toggle per API-provider mapping

- Requests pass straight through to the mapped provider — no routing, failover, or health checks

## 4. API Key & Credential Management

- One production key + one sandbox key generated per merchant

- View, regenerate, and revoke keys from the panel

- Basic IP whitelist per key (list of allowed IPs)

- No scopes, no scheduled rotation, no per-API key permissions

## 5. Subscription, Plans & Pricing

- Admin sets a single per-call price per API

- One flat markup % defined per reseller tier, applied over base price

- One default plan applies to all merchants

- No subscription/slab/volume pricing, no custom enterprise quotes, no bundles

## 6. Wallet, Credits & Billing

- Prepaid wallet per merchant/reseller

- Each successful API call auto-debits the per-call price from the wallet

- Manual top-up via QmaxPay/1Q1Pay; balance updates on confirmation

- Running ledger of credits and debits

- Basic invoice generated per top-up

- Calls are blocked when balance is insufficient

- No postpaid/credit limits, no auto-debit, no billing cycles, no GST e-invoicing

## 7. Transaction & Routing Engine

- Receives merchant request, validates key + balance + rate limit

- Forwards to the single mapped provider, receives response

- Returns a normalized response to the merchant

- Idempotency key prevents duplicate processing

- Every request/response logged with timestamp, status, and amount debited

- No retries, no multi-provider normalization, no async queue

## 8. Reseller / White-Label Panel

- Single tier of resellers, each created under Super Admin

- Reseller onboards its own merchants

- Reseller sets its own markup over the base/admin price

- Branded login: reseller logo + name on the panel

- No sub-reseller chains, no custom domains, no multi-level commission cascade

## 9. Settlement & Payout

- On each transaction, the reseller's margin (sell price − base price) is auto-credited to the reseller's wallet

- Margins shown as a settlement report only

- No outbound payout run, no provider-statement reconciliation, no hold/release

## 10. Developer Portal & Documentation

- Static documentation page per API: endpoint, parameters, sample request, sample response

- Sandbox key available for testing

- Copy-paste cURL samples

- No interactive "try-it" console, no SDKs, no auto-generated docs, no changelog

## 11. Webhooks & Callbacks

- Merchant configures one callback URL

- System POSTs transaction status to that URL after completion

- Delivery attempt is logged

- No multi-event subscriptions, no retry/backoff, no signature-verification UI

## 12. Rate Limiting, Quota & Throttling

- Fixed rate limit per key (requests/second)

- Hard daily call cap per key

- Requests over the limit are rejected with a standard error

- No per-plan quotas, no overage billing, no configurable rules

## 13. Reports & Analytics

- Per-role dashboard: wallet balance, today's call count, success/fail counts

- API-wise usage report (calls, success rate, amount spent)

- Full transaction log, filterable by date

- Excel export

- No provider-wise analytics, no revenue trends, no scheduled reports

## 14. Risk, Fraud & Compliance

- Audit log of key actions (approvals, price changes, key revocations)

- Complete transaction trail

- Basic velocity check — flags/blocks abnormal call spikes

- KYC gate: merchant must be Approved before any production key works

- No fraud-rules engine, no AML scoring, no PCI-DSS tooling

## 15. Notifications & Alerts

- Email + SMS triggers: low wallet balance, account approved/rejected, provider-down (admin-flagged)

- Matching in-app alert

- Fixed templates

- No webhook alerts, no quota-breach triggers, no template editor, no preferences

## 16. Admin Control Panel

- Provider/API configuration (credentials, base price, enable/disable)

- Pricing & markup configuration per reseller tier

- User management (approve, suspend, edit)

- Role configuration

- Master settings

- Audit log

- No feature toggles, no system-health view, no backup UI

## 17. Support & Ticketing

- Merchant/reseller raises a ticket (subject, category, message)

- Admin sees the queue and replies in a thread

- Status limited to Open/Closed

- No SLA timers, no escalation, no assignment routing, no knowledge base

# 2. Key Decisions Locked

| Decision Area | Locked Choice |
| --- | --- |
| Routing model | Single provider per API — no routing, no failover, no least-cost logic |
| Reseller model | Single-tier resellers under Super Admin — no sub-reseller cascades |
| Billing model | Prepaid wallet only — no postpaid/credit |
| Margins | Report-only — auto-credited, no payouts |
| Documentation | Static docs — no live try-it console |

# 3. User Roles (Phase 1)

| Role | Responsibilities |
| --- | --- |
| Super Admin | Full platform control, provider & pricing config, user approvals, reports, settings |
| Reseller | Onboards own merchants, sets own markup, branded panel, views own reports |
| Developer / Merchant | Consumes APIs via keys, manages wallet, views usage & transactions, raises tickets |

No sub-users or staff accounts in Phase 1.

# 4. Functional Requirements by Module

## 4.1  User & Identity Management

• Three roles only: Super Admin, Reseller, Developer/Merchant.

• Self-registration form: name, business name, mobile, email, PAN, GSTIN.

• New B2B accounts land in Pending; admin reviews uploaded PAN/GST and marks Active or Rejected.

• Login via mobile/email + OTP.

• Profile holds business name, contact, GSTIN, one address.

• Account states limited to: Pending, Active, Rejected.

• Excluded: sub-users, staff accounts, automated KYC validation, 2FA.

## 4.2  API Repository / Catalog Management

• Admin-maintained list of APIs; each has name, category, description, status (Live/Inactive).

• One production endpoint URL per API.

• A linked documentation reference per API (points to 4.10).

• Merchants browse only Live APIs they are entitled to.

• Excluded: versioning, beta/deprecated states, self-service publishing.

## 4.3  Provider / Upstream Aggregation Engine

• Each API mapped to exactly one upstream provider.

• Admin stores provider credentials and base (cost) price per API.

• Manual enable/disable toggle per API-provider mapping.

• Requests pass straight through to the mapped provider.

• Excluded: multi-provider, failover, least-cost routing, health checks, hot-swap.

## 4.4  API Key & Credential Management

• One production key + one sandbox key generated per merchant.

• View, regenerate, and revoke keys from the panel.

• Basic IP whitelist per key (list of allowed IPs).

• Excluded: scopes, scheduled rotation, per-API key permissions.

## 4.5  Subscription, Plans & Pricing

• Admin sets a single per-call price per API.

• One flat markup % per reseller tier, applied over base price.

• One default plan applies to all merchants.

• Excluded: subscription/slab/volume pricing, custom enterprise quotes, bundles.

## 4.6  Wallet, Credits & Billing

• Prepaid wallet per merchant/reseller.

• Each successful API call auto-debits the per-call price.

• Manual top-up via QmaxPay/1Q1Pay; balance updates on confirmation.

• Running ledger of credits and debits.

• Basic invoice generated per top-up.

• Calls blocked when balance is insufficient.

• Excluded: postpaid/credit limits, auto-debit, billing cycles, GST e-invoicing.

## 4.7  Transaction & Routing Engine

• Receives merchant request; validates key + balance + rate limit.

• Forwards to the single mapped provider; receives response.

• Returns a normalized response to the merchant.

• Idempotency key prevents duplicate processing.

• Every request/response logged with timestamp, status, and amount debited.

• Excluded: retries, multi-provider normalization, async queue.

## 4.8  Reseller / White-Label Panel

• Single tier of resellers, each created under Super Admin.

• Reseller onboards its own merchants.

• Reseller sets its own markup over the base/admin price.

• Branded login: reseller logo + name on the panel.

• Excluded: sub-reseller chains, custom domains, multi-level commission cascade.

## 4.9  Settlement & Payout

• On each transaction, the reseller margin (sell − base) is auto-credited to the reseller wallet.

• Margins shown as a settlement report only.

• Excluded: outbound payout run, provider-statement reconciliation, hold/release.

## 4.10  Developer Portal & Documentation

• Static documentation page per API: endpoint, parameters, sample request, sample response.

• Sandbox key available for testing.

• Copy-paste cURL samples.

• Excluded: interactive try-it console, SDKs, auto-generated docs, changelog.

## 4.11  Webhooks & Callbacks

• Merchant configures one callback URL.

• System POSTs transaction status to that URL after completion.

• Delivery attempt is logged.

• Excluded: multi-event subscriptions, retry/backoff, signature-verification UI.

## 4.12  Rate Limiting, Quota & Throttling

• Fixed rate limit per key (requests/second).

• Hard daily call cap per key.

• Requests over the limit rejected with a standard error.

• Excluded: per-plan quotas, overage billing, configurable rules.

## 4.13  Reports & Analytics

• Per-role dashboard: wallet balance, today's call count, success/fail counts.

• API-wise usage report (calls, success rate, amount spent).

• Full transaction log, filterable by date.

• Excel export.

• Excluded: provider-wise analytics, revenue trends, scheduled reports.

## 4.14  Risk, Fraud & Compliance

• Audit log of key actions (approvals, price changes, key revocations).

• Complete transaction trail.

• Basic velocity check — flags/blocks abnormal call spikes.

• KYC gate: merchant must be Approved before any production key works.

• Excluded: fraud-rules engine, AML scoring, PCI-DSS tooling.

## 4.15  Notifications & Alerts

• Email + SMS triggers: low wallet balance, account approved/rejected, provider-down (admin-flagged).

• Matching in-app alert.

• Fixed templates.

• Excluded: webhook alerts, quota-breach triggers, template editor, preferences.

## 4.16  Admin Control Panel

• Provider/API configuration (credentials, base price, enable/disable).

• Pricing & markup configuration per reseller tier.

• User management (approve, suspend, edit).

• Role configuration.

• Master settings.

• Audit log.

• Excluded: feature toggles, system-health view, backup UI.

## 4.17  Support & Ticketing

• Merchant/reseller raises a ticket (subject, category, message).

• Admin sees the queue and replies in a thread.

• Status limited to Open/Closed.

• Excluded: SLA timers, escalation, assignment routing, knowledge base.

# 5. Out of Scope (Phase 2+)

• Mobile apps (reseller + merchant)

• Smart / least-cost routing and multi-provider failover

• Public status page & SLA monitoring

• Third-party API publisher marketplace

• Sub-reseller cascades

• Automated payouts & provider reconciliation

• Postpaid/credit billing and GST e-invoicing

• Interactive API console and SDKs

# 6. Cross-Cutting Simplifications (Scope Guardrails)

• One provider per API (no routing engine).

• Single-tier resellers (no cascades).

• Prepaid-only wallet (no credit).

• Report-only margins (no payouts).

• Static documentation (no live console).

• Fixed notification triggers and templates.

# Fincomax

FINCOMAX

Professional Services Marketplace & Compliance Platform

Software Requirements Specification (Phase 1)

with Execution Plan

Omara Digitech Pvt. Ltd.

Version 1.1

21 June 2026  |  Confidential

# Table of Contents

# 1. Introduction

This document specifies the Minimum Viable Product (Phase 1) for Fincomax, a web-based professional-services marketplace operated by Omara Digitech Pvt. Ltd. Fincomax connects businesses and individuals (Clients) with verified professionals — Chartered Accountants, Company Secretaries, Lawyers, Accountants, Bookkeepers, CFAs and CFOs — through an open job marketplace, and layers a lean compliance-management capability on top. All payments and identity checks are routed through 1Q1Pay.

The Phase 1 is deliberately scoped to the minimum services required to take the business live. Items listed under “Excluded” against each module are explicit non-goals for this release and are recorded to prevent scope creep.

## 1.1 Scope

A · Core Platform & Access

USR — User, Role & Access Management

- Four fixed roles: Admin, Ops, Professional, Client

- Self-registration for Professional & Client; Admin/Ops created internally

- Login via email/mobile + OTP

- RBAC — menus and actions gated by role

- Basic profile + session management

- Excluded: sub-roles, team accounts under a professional, 2FA, social login

ONB — Onboarding & KYC

- Separate guided flows for Client and Professional

- Document upload (ID/PAN; membership certificate for professionals)

- Ops review queue → Approve / Reject with reason

- Account states: Pending, Active, Rejected

- Excluded: automated/third-party KYC, video KYC, re-KYC cycles

WAL — Wallet & Billing Account

- Prepaid wallet per Client; payout balance per Professional

- Manual top-up via 1Q1Pay; balance updates on confirmation

- Running ledger of credits/debits

- Excluded: postpaid/credit limits, auto-debit, multi-currency

B · Marketplace Front-End & Profiles

WEB — Marketplace Front-End / Storefront

- Public landing with category entry points

- Browse open jobs and browse professionals (talent)

- Category / sub-category pages

- Responsive web (desktop + mobile browser)

- Excluded: native mobile app, multi-language, CMS/blog

SRCH — Search & Discovery

- Keyword search across jobs and professionals

- Filters: category, skill, rating, budget/rate

- Sort by recent / rating

- Excluded: AI recommendations, saved searches, alerts

PRF — Professional Profile & Portfolio

- Profile: name, headline, professional type, skills, bio

- Rate (hourly/fixed), availability flag

- Portfolio samples + on-platform work history

- Credential/membership number captured at onboarding, shown as "verified"

- Excluded: skill tests, video intro, profile analytics

CPRF — Client / Business Profile

- Client profile: name, contact, business name

- Entity & registration details: PAN, GSTIN, CIN (for invoicing/compliance)

- Posting and hire history

- Excluded: multiple entities per client, org sub-accounts

C · Job Marketplace & Engagement

JOB — Job Posting Platform

- Post a job: title, scope, category, budget (fixed/hourly), deadline, attachments

- Job states: Draft, Open, In Progress, Delivered, Closed, Cancelled

- Ops can view all postings

- Excluded: job templates, repost automation, featured/promoted listings

PROP — Proposals & Bidding

- Professional submits proposal: cover note, quoted price, timeline

- One proposal per professional per job

- Client views all proposals on a job

- Excluded: client invites/headhunting, proposal credits, counter-offer threads

HIRE — Hiring & Contracts

- Client shortlists and awards to one professional

- System generates a contract record (scope, price, timeline, parties)

- Both parties accept to activate the engagement

- Excluded: multi-hire per job, e-signature integration, custom contract templates

JMG — Job & Engagement Management

- Engagement workspace tied to the awarded job

- Milestones/deliverables with status (pending → submitted → approved)

- Professional submits deliverables; Client approves or requests changes

- Lifecycle transitions drive payment release (links to PAY)

- Excluded: time-tracking/timesheets, sub-tasks, scheduling/Gantt

MSG — Messaging & Collaboration

- In-app 1:1 messaging within an engagement

- File/attachment exchange

- Excluded: group chat, calls/video, presence, external email threads

RVW — Ratings & Reviews

- Two-way review (Client ↔ Professional) on job closure

- Star rating + comment, aggregated onto profiles

- Excluded: moderation workflow, response-to-review, weighted scoring

D · Compliance Services

CMP — Compliance Catalog & Applicability

- Admin-maintained master (ROC, GST, Income Tax, TDS, PF/ESI, etc.)

- Each item: name, category, frequency, applicable entity type

- Map applicable compliances to a client by entity type

- Excluded: auto-applicability rules engine, statutory law text, region variants

CTRK — Compliance Tracking & Calendar

- Per-client list of applicable compliances with due dates

- Status: Upcoming, Due, Filed, Overdue

- Reminders/escalations via NOT

- Excluded: government-portal integration, auto-filing, penalty calculators

DOC — Document Collection & Vault

- Checklist-driven document requests per compliance/job

- Secure client upload, stored in per-client vault

- Professional/Ops access for the engagement

- Excluded: OCR/extraction, version history, e-sign, retention policies

E · Payments, Pricing & Settlement

1QP — 1Q1Pay Integration Layer

- Single shared connector to 1Q1Pay for collections and payouts

- Request/response handling + basic transaction reconciliation

- Excluded: multiple PSPs, failover/routing, direct bank integration

PAY — Payments, Escrow & Milestone Release

- Client funds job amount upfront into escrow (escrow ledger)

- Release to professional on milestone/job approval

- UPI/QR collection via 1Q1Pay; receipts

- Excluded: auto refunds beyond manual, chargebacks, card vaulting

IDV — PAN & e-KYC / Identity Services

- PAN and basic e-KYC verification calls (via 1Q1Pay) at onboarding

- Verification result flagged on profile

- Excluded: DSC issuance, Aadhaar offline XML, bank-account verification

PRC — Pricing, Commission & Fees

- Admin sets platform commission % on job value

- Optional flat service fee on compliance packages

- Commission computed at settlement, shown in reports

- Excluded: tiered/slab commission, coupons, professional subscriptions

STL — Settlement, Payout & GST Invoicing

- On completion: deduct commission, credit professional payout balance

- Manual/scheduled payout via 1Q1Pay

- GST-compliant invoice for platform fee/services

- Excluded: automated daily settlement, TDS computation, e-invoicing/IRN

F · Operations, Admin & Support

RPT — Reporting, MIS & Analytics

- Core reports: jobs (posted/active/closed), revenue/commission, payouts, compliance status, professional performance

- Export to CSV/Excel

- Role-based dashboards (Admin/Ops)

- Excluded: custom report builder, scheduled emailed reports, BI drilldowns

NOT — Notifications & Communications

- Channels: SMS, email, in-app

- Triggers: onboarding status, proposal/hire, milestone, payment, compliance reminder

- Excluded: WhatsApp/push, template designer, marketing campaigns

ADM — Admin Console & Configuration

- Dashboard; manage categories & compliance master data

- User approvals, service/feature toggles

- Dispute oversight and manual overrides

- Excluded: granular multi-admin permissions, audit-config UI, feature-flag framework

AUD — Audit, Security & Data Privacy

- Activity/audit logs for key actions (approvals, payments, document access)

- Encryption at rest/in transit; role-based access to sensitive data

- Excluded: SIEM integration, full DLP, configurable retention

SUP — Support, Ticketing & Helpdesk

- Ticket creation by Client/Professional; Ops routing & resolution

- States: Open, In Progress, Resolved, Closed

- Links to dispute handling from RVW/JMG

- Excluded: live chat/bot, SLA automation, knowledge base

## 1.2 Requirement ID Convention

Each Phase 1 requirement carries a traceable identifier in the form FCX-[Module]-[Number], e.g. FCX-USR-01. Phase 2 (Fincomax Books) modules use the FBK-[Module] prefix. Module codes are listed in Sections 4 and 5.

## 1.3 Document Control

| Version | Date | Change |
| --- | --- | --- |
| 1.0 | 21 Jun 2026 | Initial Phase 1 SRS with execution plan. |
| 1.1 | 21 Jun 2026 | Added Section 5 — Phase 2 scope: Fincomax Books (bookkeeping & accounting), no committed timeline. |

# 2. Architectural Decisions (Locked)

| Decision | Resolution |
| --- | --- |
| Product identity | Professional-services marketplace (Upwork-style) with a lean compliance layer. Retail/POS is out of scope. |
| Marketplace model | Open job posting plus proposal/bidding; client awards each job to a single professional. |
| Engagement model | Milestone-based engagement with escrow; payment released on client approval. |
| Payments | All collections and payouts routed through 1Q1Pay via a single connector. No direct PSP or bank integration. |
| Compliance scope | Tracking-and-document layer only (catalog, calendar, vault). No government-portal integration or auto-filing. |
| Platform | Web-only responsive (desktop + mobile browser). Single wallet currency (INR). Indian GST compliance. |
| Verification | Manual Ops review for onboarding; PAN / e-KYC performed via 1Q1Pay. |

# 3. User Roles (Phase 1)

| Role | Responsibilities |
| --- | --- |
| Admin | Full platform control: master data, categories, compliance catalog, pricing, approvals, reports, settings. |
| Ops | Onboarding review, dispute handling, support, oversight of settlements and payouts. |
| Professional | Profile & portfolio, browse and bid on jobs, deliver work, receive payouts, service compliance work. |
| Client | Post jobs, hire professionals, fund escrow, manage compliance obligations, raise tickets. |

# 4. Functional Requirements by Module (Phase 1)

All requirements below are Phase 1. Module code shown in brackets is used as the ID prefix.

## Group A · Core Platform & Access

User, Role & Access Management  [USR]

Purpose: Single identity and access-control foundation for all roles.

| Req ID | Requirement |
| --- | --- |
| FCX-USR-01 | Four fixed roles: Admin, Ops, Professional, Client. |
| FCX-USR-02 | Self-registration for Professional and Client; Admin/Ops created internally. |
| FCX-USR-03 | Login via email/mobile with OTP. |
| FCX-USR-04 | Role-based access control gating menus and actions. |
| FCX-USR-05 | Basic profile and session management. |

Excluded: sub-roles, team accounts under a professional, 2FA, social login.

Onboarding & KYC  [ONB]

Purpose: Verify and activate clients and professionals before they transact.

| Req ID | Requirement |
| --- | --- |
| FCX-ONB-01 | Separate guided onboarding flows for Client and Professional. |
| FCX-ONB-02 | Document upload (ID/PAN; membership certificate for professionals). |
| FCX-ONB-03 | Ops review queue with Approve / Reject and reason. |
| FCX-ONB-04 | Account states: Pending, Active, Rejected. |

Excluded: automated/third-party KYC, video KYC, re-KYC cycles.

Wallet & Billing Account  [WAL]

Purpose: Hold prepaid client funds and professional payout balances.

| Req ID | Requirement |
| --- | --- |
| FCX-WAL-01 | Prepaid wallet per Client; payout balance per Professional. |
| FCX-WAL-02 | Manual top-up via 1Q1Pay; balance updates on confirmation. |
| FCX-WAL-03 | Running ledger of credits and debits. |

Excluded: postpaid/credit limits, auto-debit, multi-currency.

## Group B · Marketplace Front-End & Profiles

Marketplace Front-End / Storefront  [WEB]

Purpose: Public-facing entry point to browse jobs and talent.

| Req ID | Requirement |
| --- | --- |
| FCX-WEB-01 | Public landing page with category entry points. |
| FCX-WEB-02 | Browse open jobs and browse professionals (talent). |
| FCX-WEB-03 | Category and sub-category pages. |
| FCX-WEB-04 | Responsive web (desktop and mobile browser). |

Excluded: native mobile app, multi-language, CMS/blog.

Search & Discovery  [SRCH]

Purpose: Help clients and professionals find relevant jobs and talent.

| Req ID | Requirement |
| --- | --- |
| FCX-SRCH-01 | Keyword search across jobs and professionals. |
| FCX-SRCH-02 | Filters: category, skill, rating, budget/rate. |
| FCX-SRCH-03 | Sort by recent or rating. |

Excluded: AI recommendations, saved searches, alerts.

Professional Profile & Portfolio  [PRF]

Purpose: Represent a professional's identity, skills and track record.

| Req ID | Requirement |
| --- | --- |
| FCX-PRF-01 | Profile: name, headline, professional type, skills, bio. |
| FCX-PRF-02 | Rate (hourly/fixed) and availability flag. |
| FCX-PRF-03 | Portfolio samples and on-platform work history. |
| FCX-PRF-04 | Credential/membership number captured at onboarding, shown as verified. |

Excluded: skill tests, video intro, profile analytics.

Client / Business Profile  [CPRF]

Purpose: Capture client and legal-entity details for hiring and invoicing.

| Req ID | Requirement |
| --- | --- |
| FCX-CPRF-01 | Client profile: name, contact, business name. |
| FCX-CPRF-02 | Entity and registration details: PAN, GSTIN, CIN. |
| FCX-CPRF-03 | Posting and hire history. |

Excluded: multiple entities per client, organisation sub-accounts.

## Group C · Job Marketplace & Engagement

Job Posting Platform  [JOB]

Purpose: Let clients publish work for professionals to bid on.

| Req ID | Requirement |
| --- | --- |
| FCX-JOB-01 | Post a job: title, scope, category, budget (fixed/hourly), deadline, attachments. |
| FCX-JOB-02 | Job states: Draft, Open, In Progress, Delivered, Closed, Cancelled. |
| FCX-JOB-03 | Ops visibility over all postings. |

Excluded: job templates, repost automation, featured/promoted listings.

Proposals & Bidding  [PROP]

Purpose: Let professionals respond to jobs with a quote and plan.

| Req ID | Requirement |
| --- | --- |
| FCX-PROP-01 | Professional submits a proposal: cover note, quoted price, timeline. |
| FCX-PROP-02 | One proposal per professional per job. |
| FCX-PROP-03 | Client views all proposals on a job. |

Excluded: client invites/headhunting, proposal credits, counter-offer threads.

Hiring & Contracts  [HIRE]

Purpose: Convert an accepted proposal into a binding engagement.

| Req ID | Requirement |
| --- | --- |
| FCX-HIRE-01 | Client shortlists and awards the job to one professional. |
| FCX-HIRE-02 | System generates a contract record (scope, price, timeline, parties). |
| FCX-HIRE-03 | Both parties accept to activate the engagement. |

Excluded: multi-hire per job, e-signature integration, custom contract templates.

Job & Engagement Management  [JMG]

Purpose: Run the active engagement from start to delivery.

| Req ID | Requirement |
| --- | --- |
| FCX-JMG-01 | Engagement workspace tied to the awarded job. |
| FCX-JMG-02 | Milestones/deliverables with status (pending, submitted, approved). |
| FCX-JMG-03 | Professional submits deliverables; Client approves or requests changes. |
| FCX-JMG-04 | Lifecycle transitions trigger payment release (links to PAY). |

Excluded: time-tracking/timesheets, sub-tasks, scheduling/Gantt.

Messaging & Collaboration  [MSG]

Purpose: Enable direct communication within an engagement.

| Req ID | Requirement |
| --- | --- |
| FCX-MSG-01 | In-app 1:1 messaging within an engagement. |
| FCX-MSG-02 | File / attachment exchange. |

Excluded: group chat, calls/video, presence, external email threads.

Ratings & Reviews  [RVW]

Purpose: Build trust through post-engagement feedback.

| Req ID | Requirement |
| --- | --- |
| FCX-RVW-01 | Two-way review (Client and Professional) on job closure. |
| FCX-RVW-02 | Star rating and comment, aggregated onto profiles. |

Excluded: moderation workflow, response-to-review, weighted scoring.

## Group D · Compliance Services

Compliance Catalog & Applicability  [CMP]

Purpose: Maintain the master of compliances and map them to clients.

| Req ID | Requirement |
| --- | --- |
| FCX-CMP-01 | Admin-maintained compliance master (ROC, GST, Income Tax, TDS, PF/ESI, etc.). |
| FCX-CMP-02 | Each item: name, category, frequency, applicable entity type. |
| FCX-CMP-03 | Map applicable compliances to a client by entity type. |

Excluded: auto-applicability rules engine, statutory law text, region variants.

Compliance Tracking & Calendar  [CTRK]

Purpose: Track due dates and filing status per client.

| Req ID | Requirement |
| --- | --- |
| FCX-CTRK-01 | Per-client list of applicable compliances with due dates. |
| FCX-CTRK-02 | Status: Upcoming, Due, Filed, Overdue. |
| FCX-CTRK-03 | Reminders and escalations via NOT. |

Excluded: government-portal integration, auto-filing, penalty calculators.

Document Collection & Vault  [DOC]

Purpose: Collect and securely store client documents.

| Req ID | Requirement |
| --- | --- |
| FCX-DOC-01 | Checklist-driven document requests per compliance/job. |
| FCX-DOC-02 | Secure client upload stored in a per-client vault. |
| FCX-DOC-03 | Professional / Ops access for the engagement. |

Excluded: OCR/extraction, version history, e-sign, retention policies.

## Group E · Payments, Pricing & Settlement

1Q1Pay Integration Layer  [1QP]

Purpose: Single abstraction over 1Q1Pay for all money movement.

| Req ID | Requirement |
| --- | --- |
| FCX-1QP-01 | Single shared connector to 1Q1Pay for collections and payouts. |
| FCX-1QP-02 | Request/response handling with basic transaction reconciliation. |

Excluded: multiple PSPs, failover/routing, direct bank integration.

Payments, Escrow & Milestone Release  [PAY]

Purpose: Secure client funds and release them on approved work.

| Req ID | Requirement |
| --- | --- |
| FCX-PAY-01 | Client funds the job amount upfront into escrow (escrow ledger). |
| FCX-PAY-02 | Release to professional on milestone/job approval. |
| FCX-PAY-03 | UPI/QR collection via 1Q1Pay with receipts. |

Excluded: auto refunds beyond manual, chargebacks, card vaulting.

PAN & e-KYC / Identity Services  [IDV]

Purpose: Verify identity during onboarding.

| Req ID | Requirement |
| --- | --- |
| FCX-IDV-01 | PAN and basic e-KYC verification calls (via 1Q1Pay) at onboarding. |
| FCX-IDV-02 | Verification result flagged on profile. |

Excluded: DSC issuance, Aadhaar offline XML, bank-account verification.

Pricing, Commission & Fees  [PRC]

Purpose: Define how the platform earns on jobs and packages.

| Req ID | Requirement |
| --- | --- |
| FCX-PRC-01 | Admin sets platform commission % on job value. |
| FCX-PRC-02 | Optional flat service fee on compliance packages. |
| FCX-PRC-03 | Commission computed at settlement and shown in reports. |

Excluded: tiered/slab commission, coupons, professional subscriptions.

Settlement, Payout & GST Invoicing  [STL]

Purpose: Close out engagements financially and bill compliantly.

| Req ID | Requirement |
| --- | --- |
| FCX-STL-01 | On completion: deduct commission and credit professional payout balance. |
| FCX-STL-02 | Manual/scheduled payout via 1Q1Pay. |
| FCX-STL-03 | GST-compliant invoice for platform fee/services. |

Excluded: automated daily settlement, TDS computation, e-invoicing/IRN.

## Group F · Operations, Admin & Support

Reporting, MIS & Analytics  [RPT]

Purpose: Give operators visibility into the business.

| Req ID | Requirement |
| --- | --- |
| FCX-RPT-01 | Core reports: jobs, revenue/commission, payouts, compliance status, professional performance. |
| FCX-RPT-02 | Export to CSV/Excel. |
| FCX-RPT-03 | Role-based dashboards (Admin/Ops). |

Excluded: custom report builder, scheduled emailed reports, BI drilldowns.

Notifications & Communications  [NOT]

Purpose: Keep users informed across the lifecycle.

| Req ID | Requirement |
| --- | --- |
| FCX-NOT-01 | Channels: SMS, email, in-app. |
| FCX-NOT-02 | Triggers: onboarding status, proposal/hire, milestone, payment, compliance reminder. |

Excluded: WhatsApp/push, template designer, marketing campaigns.

Admin Console & Configuration  [ADM]

Purpose: Central control panel for operators.

| Req ID | Requirement |
| --- | --- |
| FCX-ADM-01 | Dashboard; manage categories and compliance master data. |
| FCX-ADM-02 | User approvals and service/feature toggles. |
| FCX-ADM-03 | Dispute oversight and manual overrides. |

Excluded: granular multi-admin permissions, audit-config UI, feature-flag framework.

Audit, Security & Data Privacy  [AUD]

Purpose: Protect sensitive financial and KYC data.

| Req ID | Requirement |
| --- | --- |
| FCX-AUD-01 | Activity/audit logs for key actions (approvals, payments, document access). |
| FCX-AUD-02 | Encryption at rest and in transit; role-based access to sensitive data. |

Excluded: SIEM integration, full DLP, configurable retention.

Support, Ticketing & Helpdesk  [SUP]

Purpose: Resolve user issues and disputes.

| Req ID | Requirement |
| --- | --- |
| FCX-SUP-01 | Ticket creation by Client/Professional; Ops routing and resolution. |
| FCX-SUP-02 | States: Open, In Progress, Resolved, Closed. |
| FCX-SUP-03 | Links to dispute handling from RVW/JMG. |

Excluded: live chat/bot, SLA automation, knowledge base.

# 5. Phase 2 Scope — Fincomax Books (Bookkeeping & Accounting)

Fincomax Books is an in-house double-entry bookkeeping and accounting suite intended to serve both Fincomax marketplace professionals (managing their clients’ books) and external businesses as a standalone product. The modules below are recorded as Phase 2 scope. They are not part of the Phase 1, carry no committed timeline at this stage, and are deliberately omitted from the execution plan in Section 7. Inventory (Group E) and Payroll (Group G) are optional extensions within Phase 2.

Phase 2 module identifiers use the FBK-[Module] prefix to keep them distinct from Phase 1 (FCX-) modules.

## Group A · Setup & Configuration

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-ORG | Organisation / Company Setup | Multi-company books, profile, PAN/GSTIN, fiscal year, base currency. |
| FBK-COA | Chart of Accounts | Account groups, ledgers, Schedule III / standard CoA templates. |
| FBK-OPB | Opening Balances | Ledger opening balances, outstanding AR/AP, opening stock. |
| FBK-TXC | Tax Configuration | GST rates, TDS/TCS sections, HSN/SAC, place of supply. |
| FBK-PRD | Period & Fiscal Year Management | Accounting periods, locking, year setup. |
| FBK-ROL | Book-Level Users, Roles & Permissions | Owner, Accountant, Staff, Viewer. |

## Group B · Core Bookkeeping & Ledger

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-GL | General Ledger | Double-entry posting engine, ledger view, running balances. |
| FBK-JNL | Journals & Vouchers | Payment, receipt, contra, journal, sales, purchase vouchers. |
| FBK-BNK | Bank & Cash Management | Bank/cash accounts, transfers, cash book. |
| FBK-REC | Bank Reconciliation | Statement import, matching, reconciliation status. |
| FBK-ADJ | Adjustments & Closing Entries | Provisions, accruals, year-end adjustments. |

## Group C · Sales & Receivables

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-CUS | Customer Master | Customer ledgers, GSTIN, credit terms, contacts. |
| FBK-EST | Estimates / Quotations | Quotes, conversion to invoice. |
| FBK-INV | Sales Invoicing | GST-compliant & recurring invoices, multi-rate items. |
| FBK-CRN | Credit Notes & Sales Returns | Sales returns and credit notes. |
| FBK-RCT | Receipts & Collections | Allocate against invoices, advance receipts. |
| FBK-ARA | Receivables & Aging | Outstanding, aging buckets, reminders. |

## Group D · Purchases & Payables

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-VEN | Vendor / Supplier Master | Vendor ledgers, GSTIN, terms. |
| FBK-PO | Purchase Orders | POs, conversion to bill. |
| FBK-BIL | Bills / Purchase Invoices | Vendor bills, ITC eligibility, multi-rate. |
| FBK-DBN | Debit Notes & Purchase Returns | Purchase returns and debit notes. |
| FBK-EXP | Expenses & Expense Claims | Direct expenses, staff reimbursements. |
| FBK-PMT | Vendor Payments | Allocate against bills, advances. |
| FBK-APA | Payables & Aging | Outstanding, aging, payment scheduling. |

## Group E · Inventory (optional extension)

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-ITM | Item / Product & Service Master | Goods/services, HSN/SAC, units, rates. |
| FBK-STK | Stock & Inventory Tracking | Stock in/out, multi-warehouse, batch. |
| FBK-STA | Stock Adjustments & Valuation | FIFO / weighted-average valuation. |

## Group F · Tax & Statutory Compliance (India)

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-GST | GST Management | GSTR-1 / 3B / 2B prep, ITC reconciliation, summaries. |
| FBK-EINV | e-Invoicing & e-Way Bill | IRN generation, e-way bills. |
| FBK-TDS | TDS / TCS Management | Deduction, challans, 26Q/27Q prep, certificates. |
| FBK-TXR | Tax Reports & Return Workpapers | GST/TDS reports and reconciliations. |

## Group G · Payroll (optional extension)

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-EMP | Employee Master & Salary Structure | Employee records and salary structure. |
| FBK-PYR | Payroll Processing | Salary runs, attendance/LOP inputs. |
| FBK-STD | Statutory Deductions | PF, ESI, PT, TDS on salary. |
| FBK-PSL | Payslips & Statutory Outputs | Payslips, PF/ESI/PT outputs. |

## Group H · Fixed Assets

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-FAR | Fixed Asset Register | Asset master, capitalisation. |
| FBK-DEP | Depreciation | Companies Act / Income Tax schedules, posting. |

## Group I · Reports & Financial Statements

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-FIN | Financial Statements | Trial Balance, P&L, Balance Sheet, Cash Flow. |
| FBK-RPT | Operational & MIS Reports | Ledgers, day book, aging, tax, ratios, exports. |

## Group J · Documents, Audit & Period Close

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-DMS | Document Management | Attach source docs to transactions, per-book vault. |
| FBK-ATR | Audit Trail & Activity Log | Edit history (Indian audit-trail requirement). |
| FBK-CLS | Period & Year-End Close | Locking, closing, carry-forward. |

## Group K · Collaboration & Practice Management

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-PRAC | Practice / Accountant Console | One professional managing many client books, switch & tasks. |
| FBK-CLP | Client Portal | Clients view statements/invoices, upload docs, approve. |
| FBK-COL | Collaboration & Queries | Comments, queries, to-dos between accountant & client. |
| FBK-NOT | Notifications & Reminders | Invoice due, GST/TDS due, approvals. |

## Group L · Platform, Integration & Subscription

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-INT | Fincomax Integration | Link a book to a Fincomax client/entity; push to compliance (CTRK) & document vault (DOC); originate bookkeeping jobs. |
| FBK-1QP | 1Q1Pay Payments Integration | Collect on invoices (UPI/QR/links), pay bills/payouts. |
| FBK-BFI | Bank & Payment Feeds | Bank feeds, gateway integration. |
| FBK-IMP | Import / Export & Migration | Excel/CSV import, Tally migration, data export. |
| FBK-API | API & Integrations | REST API, webhooks, connectors. |
| FBK-SUB | Subscription & Licensing (external users) | Plans, billing, usage limits, license management. |
| FBK-ADM | System Admin & Settings | Org settings, backups, retention, security. |

Phase 2 total: 53 modules across 12 groups — no timeline committed.

# 6. Non-Functional Requirements

| Attribute | Requirement |
| --- | --- |
| Performance | Standard page loads within a few seconds on broadband; sized for Phase 1-scale concurrent users. |
| Security | TLS in transit, encryption at rest, RBAC, OTP login, audit logging of sensitive actions. |
| Availability | Standard cloud hosting uptime target; business-hours operational support. |
| Compliance | Indian GST-compliant invoicing; data privacy for KYC and financial documents. |
| Usability | Responsive web across desktop and mobile browsers. |
| Scalability | Modular architecture so Phase-2 features can be added without rework. |
| Maintainability | Single 1Q1Pay connector abstraction for all payment flows. |

Here's the full module superset for an in-house bookkeeping & accounting software inside Fincomax ("Fincomax Books") — sized to serve both your own marketplace professionals/clients and external businesses as a standalone product. This is the complete list; the Phase 1 cut comes after you confirm scope.

A · Setup & Configuration

- ORG — Organisation / Company Setup: multi-company books, company profile, PAN/GSTIN, fiscal year, base currency

- COA — Chart of Accounts: account groups, ledgers, Schedule III / standard CoA templates

- OPB — Opening Balances: ledger opening balances, outstanding AR/AP, opening stock

- TXC — Tax Configuration: GST rates, TDS/TCS sections, HSN/SAC, place of supply

- PRD — Period & Fiscal Year Management: accounting periods, locking, year setup

- ROL — Book-Level Users, Roles & Permissions: Owner, Accountant, Staff, Viewer

B · Core Bookkeeping & Ledger

- GL — General Ledger: double-entry posting engine, ledger view, running balances

- JNL — Journals & Vouchers: payment, receipt, contra, journal, sales, purchase vouchers

- BNK — Bank & Cash Management: bank/cash accounts, transfers, cash book

- REC — Bank Reconciliation: statement import, matching, reconciliation status

- ADJ — Adjustments & Closing Entries: provisions, accruals, year-end adjustments

C · Sales & Receivables

- CUS — Customer Master: customer ledgers, GSTIN, credit terms, contacts

- EST — Estimates / Quotations: quotes, conversion to invoice

- INV — Sales Invoicing: GST-compliant & recurring invoices, multi-rate items

- CRN — Credit Notes & Sales Returns

- RCT — Receipts & Collections: allocate against invoices, advance receipts

- ARA — Receivables & Aging: outstanding, aging buckets, reminders

D · Purchases & Payables

- VEN — Vendor / Supplier Master: vendor ledgers, GSTIN, terms

- PO — Purchase Orders: POs, conversion to bill

- BIL — Bills / Purchase Invoices: vendor bills, ITC eligibility

- DBN — Debit Notes & Purchase Returns

- EXP — Expenses & Expense Claims: direct expenses, staff reimbursements

- PMT — Vendor Payments: allocate against bills, advances

- APA — Payables & Aging: outstanding, aging, payment scheduling

E · Inventory (optional extension)

- ITM — Item / Product & Service Master: goods/services, HSN/SAC, units, rates

- STK — Stock & Inventory Tracking: stock in/out, multi-warehouse, batch

- STA — Stock Adjustments & Valuation: FIFO / weighted-average

F · Tax & Statutory Compliance (India)

- GST — GST Management: GSTR-1 / 3B / 2B prep, ITC reconciliation, summaries

- EINV — e-Invoicing & e-Way Bill: IRN generation, e-way bills

- TDS — TDS / TCS Management: deduction, challans, 26Q/27Q prep, certificates

- TXR — Tax Reports & Return Workpapers: GST/TDS reports & reconciliations

G · Payroll (optional extension)

- EMP — Employee Master & Salary Structure

- PYR — Payroll Processing: salary runs, attendance/LOP inputs

- STD — Statutory Deductions: PF, ESI, PT, TDS on salary

- PSL — Payslips & Statutory Outputs

H · Fixed Assets

- FAR — Fixed Asset Register: asset master, capitalisation

- DEP — Depreciation: Companies Act / Income Tax schedules, posting

I · Reports & Financial Statements

- FIN — Financial Statements: Trial Balance, P&L, Balance Sheet, Cash Flow

- RPT — Operational & MIS Reports: ledgers, day book, aging, tax, ratios, exports

J · Documents, Audit & Period Close

- DMS — Document Management: attach source docs to transactions, per-book vault

- ATR — Audit Trail & Activity Log: edit history (Indian audit-trail requirement)

- CLS — Period & Year-End Close: locking, closing, carry-forward

K · Collaboration & Practice Management (the Fincomax edge)

- PRAC — Practice / Accountant Console: one professional managing many client books, switch & task list

- CLP — Client Portal: clients view statements/invoices, upload docs, approve

- COL — Collaboration & Queries: comments, queries, to-dos between accountant & client

- NOT — Notifications & Reminders: invoice due, GST/TDS due, approvals

L · Platform, Integration & Subscription

- FCX — Fincomax Integration: link a book to a Fincomax client/entity; push items to compliance (CTRK) & document vault (DOC); originate bookkeeping jobs from the marketplace

- 1QP — 1Q1Pay Payments Integration: collect on invoices (UPI/QR/links), pay bills/payouts

- BFI — Bank & Payment Feeds: bank feeds, gateway integration

- IMP — Import / Export & Migration: Excel/CSV, Tally migration, data export

- API — API & Integrations: REST API, webhooks, connectors

- SUB — Subscription & Licensing (external users): plans, billing, usage limits

- ADM — System Admin & Settings: org settings, backups, retention, security

# SaaS for Enterprises

OMARA DIGITECH PVT. LTD.

One Ecosystem. Endless Possibilities.

SaaS ERP Platform

Software Requirements Specification (SRS)

Phase 1 — Core Modules

Document Version: 0.1 (Draft for Review)

Date: 21 June 2026

Status: For Client / PM / Tech Lead Review

CONFIDENTIAL — Property of Omara Digitech Pvt. Ltd.

# Document Control

## Revision History

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 0.1 | 21 Jun 2026 | Omara Digitech | Initial draft for review. |

# 1. Introduction

## 1.1 Purpose

This Software Requirements Specification (SRS) defines the functional and non-functional requirements for Phase 1 of the Omara Digitech SaaS ERP Platform. It serves as the agreed baseline for design, development, and stakeholder sign-off.

## 1.2 Scope

Phase 1 delivers a multi-tenant, web-based ERP offered as Software-as-a-Service. It comprises a SaaS Foundation Layer plus seven core business modules: LMS, CRM, HRMS, Inventory Management, Finance Management, Task Management, and Team Management. Each requirement is tagged MVP (first release) or Phase 2 (deferred). A broader Phase 2 module roadmap is summarized in Section 12.

## Phase 1 Module Details

1. LMS (Learning Management)

- Course builder: courses → modules → lessons (video, document, quiz content)

- Content library & uploads

- Enrollment: assign to employees/teams, self-enroll, mandatory training flags

- Progress tracking & completion status

- Assessments/quizzes with scoring

- Certificates on completion

- Reports: completion rates, scores by employee/team

2. CRM

- Contact & account management (individuals + companies)

- Lead capture: web forms, manual entry, bulk import

- Pipeline with custom stages; deals/opportunities

- Activities: calls, meetings, emails, tasks linked to contacts

- Follow-up reminders & interaction history

- Tags/segmentation

- Reports: pipeline value, conversion rate, activity log

3. HRMS

- Employee master (personal, job, documents)

- Attendance: check-in/out, regularization

- Leave management: types, requests, approvals, balances

- Payroll basics: salary structure, payslip generation, deductions (TDS/PF deferred to Phase 2)

- Onboarding / offboarding workflows

- Org structure & reporting lines

- Document store (offer letters, IDs)

- Employee self-service portal

4. Inventory Management

- Item/product master (SKU, category, unit, pricing)

- Stock levels (multi-location ready)

- Stock-in (receipts) / stock-out (issues) / adjustments

- Low-stock & reorder alerts

- Stock valuation

- Reports: stock summary, movement, valuation

- Batch/expiry tracking deferred to Phase 2

5. Finance Management

- GST-compliant sales invoicing

- Expense & bill tracking

- Chart of accounts / ledgers

- Receipts & payments, bank/cash accounts

- GST handling: tax rates, GSTIN, GST reports

- Financial reports: P&L, receivables/payables, outstanding

- Hooks: invoice-from-deal (CRM), COGS (Inventory)

6. Task Management

- Task creation: title, description, assignee, due date, priority

- Status workflow (custom) + Kanban/list views

- Subtasks & checklists

- Comments & attachments

- Linking to CRM deals, HR, projects, teams

- Reminders & overdue alerts

- Reports: workload, overdue, completion

7. Team Management

- Team creation & membership

- Hierarchy / reporting structure

- Role assignment within teams

- Member capacity & availability

- Team dashboards

Design note: Team Management overlaps heavily with HRMS org structure and the Foundation Layer's RBAC. My recommendation is to build it as a thin layer over those two rather than a standalone module with its own data — avoids duplicate org/role logic. Flag if you'd prefer it fully standalone.

Phase 2

### Phase 2 — Modules for the next phase from the detailed list

Operations & Supply Chain

- Purchase, Inventory (deepen), Warehouse, Logistics, Supply Chain, Procurement, Material Requirement Planning, Quality Control

Manufacturing / Production

- Production, New Product Development, Job Work (Outsource), Job Work (Insource), Maintenance, AMC

Sales & Distribution

- Sales Management, Sales Distribution, POS, E-commerce/Aggregator, Import-Export, Bid Management (Domestic & Intl)

Finance & Compliance

- Accounts, Finance (deepen), Legal & Compliances, Scheme/Cashback/Reward/Gift, Referral/Commission, Cash Management & Settlement (CMSS)

Customer & Support

- CRM (deepen), Complaint & Grievance, IVR/Call Center, SOS Services

Marketing & Content

- Digital Marketing, Social Media Management (Social ERP), Content Management (CMS)

Tracking & Security

- Barcode Management, Geo-Location & Tracking, OTP/MPIN Security

Management & Admin

- Asset/Admin-IT (deepen), Project Management, Operations, Data Management (DRAM), Task Management (deepen), LMS (deepen)

## 1.3 Definitions, Acronyms & Abbreviations

| Term | Meaning |
| --- | --- |
| SaaS | Software-as-a-Service. |
| Tenant | An isolated customer workspace within the multi-tenant platform. |
| MVP | Minimum Viable Product — the first release scope. |
| RBAC | Role-Based Access Control. |
| LMS | Learning Management System (see Assumption A-01). |
| CRM | Customer Relationship Management. |
| HRMS | Human Resource Management System. |
| GST | Goods and Services Tax (India). |
| MPIN | Mobile Personal Identification Number. |

## 1.4 References

• Omara Digitech product ecosystem materials (1Q1Pay, QmaxPay, Fincomax).

• SAAS ERP modular feature list (source for Phase 2 roadmap).

## 1.5 Overview

Section 2 describes the overall product context, users, constraints and assumptions. Sections 3–11 specify requirements for the Foundation Layer and each module. Section 12 lists deferred Phase 2 scope. Section 13 captures sign-off.

# 2. Overall Description

## 2.1 Product Perspective

The platform is a new, self-contained multi-tenant SaaS ERP. Businesses subscribe to a plan, provision their own workspace, and operate the modules independently with isolated data. It integrates with Omara's payment infrastructure for subscription billing.

## 2.2 Product Functions (Summary)

• Tenant onboarding, subscription and billing.

• Role-based access and platform administration.

• Learning, customer, HR, inventory, finance, task and team operations.

## 2.3 User Classes and Characteristics

| Role | Description |
| --- | --- |
| Platform Super-Admin | Omara Digitech operations team. Manages tenants, subscription plans, platform configuration and monitoring. |
| Tenant Owner | Primary subscriber. Full access within the tenant including billing and subscription. |
| Tenant Admin | Configures modules, manages users and roles within the tenant. |
| Manager | Department/team-level access; approves leave, tasks and reviews reports. |
| Staff / Employee | Operational module use and employee self-service. |

## 2.4 Operating Environment

• Cloud-hosted, multi-tenant web application.

• Accessed via modern desktop and mobile browsers (responsive).

## 2.5 Design and Implementation Constraints

• Web-only responsive platform for MVP (no native mobile apps).

• Indian GST compliance for Finance; English UI at MVP.

• Single integrated payment gateway for subscription billing.

## 2.6 Assumptions and Dependencies

Items marked “Requires sign-off” must be confirmed before design proceeds.

| Ref | Assumption / Dependency | Status |
| --- | --- | --- |
| A-01 | “LMS” is interpreted as Learning Management System (employee training). CRM owns lead/pipeline functions. | Requires sign-off |
| A-02 | Deployment model is multi-tenant SaaS — businesses subscribe to manage their own operations. | Requires sign-off |
| A-03 | MVP is a web-only responsive platform; native mobile apps are out of scope. | Assumption |
| A-04 | Subscription billing uses a single integrated payment gateway (QmaxPay / 1Q1Pay). | Assumption |
| A-05 | Compliance scope is Indian GST; English is the MVP UI language. | Assumption |
| A-06 | Team Management is implemented as a thin layer over HRMS org structure and platform RBAC, not a standalone data model. | Assumption |
| D-01 | Availability of QmaxPay / 1Q1Pay payment APIs, plus SMS and email gateways. | Dependency |

# 3. SaaS Foundation Layer Requirements

Cross-cutting platform capabilities required by all modules. These form mandatory groundwork for the MVP.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-FND-001 | Tenant self-service signup and automated workspace provisioning. | MVP |
| ERP-FND-002 | Tenant profile and workspace settings (name, logo, locale, timezone, currency). | MVP |
| ERP-FND-003 | Per-tenant data isolation enforced across all modules. | MVP |
| ERP-FND-004 | Tenant lifecycle management: suspend, reactivate, soft-delete. | MVP |
| ERP-FND-005 | Subscription plans/tiers with module- and feature-level gating per plan. | MVP |
| ERP-FND-006 | Free-trial provisioning with automatic expiry handling. | MVP |
| ERP-FND-007 | Online subscription payment collection via integrated gateway (QmaxPay / 1Q1Pay). | MVP |
| ERP-FND-008 | Subscription invoices and payment history. | MVP |
| ERP-FND-009 | Billing cycle changes, plan upgrades/downgrades with proration. | Phase 2 |
| ERP-FND-010 | Failed-payment dunning and grace-period handling. | Phase 2 |
| ERP-FND-011 | User invitation, activation and deactivation within a tenant. | MVP |
| ERP-FND-012 | Role-based access control (RBAC) with module-level permissions. | MVP |
| ERP-FND-013 | Predefined roles: Owner, Admin, Manager, Staff. | MVP |
| ERP-FND-014 | Custom role creation with granular permissions. | Phase 2 |
| ERP-FND-015 | Authentication via email/password. | MVP |
| ERP-FND-016 | OTP verification (email / SMS). | MVP |
| ERP-FND-017 | MPIN for quick and secure access. | MVP |
| ERP-FND-018 | Two-factor authentication (2FA). | Phase 2 |
| ERP-FND-019 | Session management with configurable timeout. | MVP |
| ERP-FND-020 | Password policy enforcement and reset flow. | MVP |
| ERP-FND-021 | Audit logging of key user and data actions. | MVP |
| ERP-FND-022 | Platform super-admin console: tenant oversight, plan management, usage monitoring. | MVP |
| ERP-FND-023 | Consent-based support impersonation with audit trail. | Phase 2 |
| ERP-FND-024 | Notifications engine: email, SMS, in-app. | MVP |
| ERP-FND-025 | Notification templates and per-user preferences. | Phase 2 |

# 4. Functional Requirements — Core Modules

## 4.1. LMS (Learning Management)

Employee training and course delivery. Note: interpretation of “LMS” is subject to Assumption A-01.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-LMS-001 | Course builder with structure: course → modules → lessons. | MVP |
| ERP-LMS-002 | Lesson content types: video, document/PDF, text, external link. | MVP |
| ERP-LMS-003 | Central content/media library with uploads. | MVP |
| ERP-LMS-004 | Enrollment: assign courses to individual employees or teams. | MVP |
| ERP-LMS-005 | Mandatory-training flags with due dates. | MVP |
| ERP-LMS-006 | Progress tracking and completion status per learner. | MVP |
| ERP-LMS-007 | Quizzes / assessments with scoring. | MVP |
| ERP-LMS-008 | Reports: completion rates and scores by employee/team. | MVP |
| ERP-LMS-009 | Self-enrollment and course catalogue. | Phase 2 |
| ERP-LMS-010 | Pass/fail criteria and retake handling. | Phase 2 |
| ERP-LMS-011 | Auto-generated completion certificates. | Phase 2 |

## 4.2. CRM (Customer Relationship Management)

Contact, lead and pipeline management with activity tracking and reporting.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-CRM-001 | Contact management for individuals. | MVP |
| ERP-CRM-002 | Account / company management. | MVP |
| ERP-CRM-003 | Lead capture via manual entry. | MVP |
| ERP-CRM-004 | Lead capture via web form and bulk import. | MVP |
| ERP-CRM-005 | Sales pipeline with configurable stages. | MVP |
| ERP-CRM-006 | Deals / opportunities with value and stage tracking. | MVP |
| ERP-CRM-007 | Activities (calls, meetings, emails, tasks) linked to records. | MVP |
| ERP-CRM-008 | Follow-up reminders. | MVP |
| ERP-CRM-009 | Interaction history / timeline per contact. | MVP |
| ERP-CRM-010 | Tags and segmentation. | MVP |
| ERP-CRM-011 | Lead assignment and ownership. | MVP |
| ERP-CRM-012 | Reports: pipeline value, conversion rate, activity. | MVP |
| ERP-CRM-013 | Two-way email integration (send/receive from CRM). | Phase 2 |

## 4.3. HRMS (Human Resource Management)

Employee records, attendance, leave, payroll basics, onboarding and self-service.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-HRM-001 | Employee master records (personal, job, contact details). | MVP |
| ERP-HRM-002 | Employee document store (offer letters, IDs, certificates). | MVP |
| ERP-HRM-003 | Attendance check-in / check-out. | MVP |
| ERP-HRM-004 | Leave types configuration. | MVP |
| ERP-HRM-005 | Leave requests, approvals and balances. | MVP |
| ERP-HRM-006 | Holiday calendar. | MVP |
| ERP-HRM-007 | Salary structure setup. | MVP |
| ERP-HRM-008 | Payslip generation with deductions. | MVP |
| ERP-HRM-009 | Onboarding workflow / checklist. | MVP |
| ERP-HRM-010 | Org structure and reporting lines. | MVP |
| ERP-HRM-011 | Employee self-service portal. | MVP |
| ERP-HRM-012 | Attendance regularization and approvals. | Phase 2 |
| ERP-HRM-013 | Statutory deductions (TDS / PF / ESI). | Phase 2 |
| ERP-HRM-014 | Offboarding workflow. | Phase 2 |

## 4.4. Inventory Management

Item master, stock movement, alerts and valuation reporting.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-INV-001 | Item / product master (SKU, category, unit, pricing). | MVP |
| ERP-INV-002 | Product categories and attributes. | MVP |
| ERP-INV-003 | Stock tracking (single location). | MVP |
| ERP-INV-004 | Stock-in (goods receipt). | MVP |
| ERP-INV-005 | Stock-out (issue / consumption). | MVP |
| ERP-INV-006 | Stock adjustments and write-offs. | MVP |
| ERP-INV-007 | Low-stock and reorder-level alerts. | MVP |
| ERP-INV-008 | Stock valuation (FIFO / weighted average). | MVP |
| ERP-INV-009 | Reports: stock summary, movement, valuation. | MVP |
| ERP-INV-010 | Multi-location / multi-warehouse stock. | Phase 2 |
| ERP-INV-011 | Batch and expiry tracking. | Phase 2 |

## 4.5. Finance Management

GST-compliant invoicing, expenses, ledgers and financial reporting.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-FIN-001 | GST-compliant sales invoicing. | MVP |
| ERP-FIN-002 | Expense and bill recording. | MVP |
| ERP-FIN-003 | Chart of accounts / ledgers. | MVP |
| ERP-FIN-004 | Receipts and payments entry. | MVP |
| ERP-FIN-005 | Bank and cash account management. | MVP |
| ERP-FIN-006 | GST configuration (rates, GSTIN, HSN/SAC). | MVP |
| ERP-FIN-007 | GST reports (GSTR-ready summaries). | MVP |
| ERP-FIN-008 | Receivables and payables tracking. | MVP |
| ERP-FIN-009 | Financial reports: P&L and outstanding statements. | MVP |
| ERP-FIN-010 | Invoice generation directly from a CRM deal. | Phase 2 |
| ERP-FIN-011 | COGS linkage with Inventory. | Phase 2 |
| ERP-FIN-012 | Multi-currency support. | Phase 2 |

## 4.6. Task Management

Task creation, boards, collaboration and progress reporting.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-TSK-001 | Task creation (title, description, assignee, due date, priority). | MVP |
| ERP-TSK-002 | Configurable status workflow. | MVP |
| ERP-TSK-003 | Kanban board and list views. | MVP |
| ERP-TSK-004 | Subtasks and checklists. | MVP |
| ERP-TSK-005 | Comments and attachments. | MVP |
| ERP-TSK-006 | Linking tasks to CRM, HR, projects and teams. | MVP |
| ERP-TSK-007 | Reminders and overdue alerts. | MVP |
| ERP-TSK-008 | Reports: workload, overdue, completion. | MVP |
| ERP-TSK-009 | Recurring tasks. | Phase 2 |

## 4.7. Team Management

Teams, hierarchy and role assignment. Implemented as a thin layer over HRMS org structure and RBAC (Assumption A-06).

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-TM-001 | Team creation and membership management. | MVP |
| ERP-TM-002 | Hierarchy / reporting structure. | MVP |
| ERP-TM-003 | Role assignment within teams. | MVP |
| ERP-TM-004 | Team dashboards. | MVP |
| ERP-TM-005 | Member capacity and availability. | Phase 2 |

# 5. Non-Functional Requirements

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-NFR-001 | Multi-tenant architecture supporting horizontal scaling. | MVP |
| ERP-NFR-002 | Typical page load under 3s; core API responses under 1s under nominal load. | MVP |
| ERP-NFR-003 | Data encryption in transit (TLS) and at rest. | MVP |
| ERP-NFR-004 | RBAC, audit logging and secure session handling. | MVP |
| ERP-NFR-005 | Automated data backup and recovery procedures. | MVP |
| ERP-NFR-006 | Responsive web UI (desktop and mobile browser). | MVP |
| ERP-NFR-007 | Support for current versions of Chrome, Edge, Firefox, Safari. | MVP |
| ERP-NFR-008 | Indian GST and statutory compliance for the Finance module. | MVP |
| ERP-NFR-009 | Target availability of 99.5% (MVP). | MVP |
| ERP-NFR-010 | Localization-ready architecture; English UI at MVP. | MVP |
| ERP-NFR-011 | Target availability of 99.9%. | Phase 2 |
| ERP-NFR-012 | Multi-language UI. | Phase 2 |

# 6. External Interface Requirements

• Payment Gateway: QmaxPay / 1Q1Pay for subscription billing.

• SMS Gateway: OTP and notifications.

• Email Service: transactional email and notifications.

• Future: accounting export and e-invoice / GSTN integration (Phase 2).

# 7. Phase 2 Scope (Deferred Roadmap)

The following modules, drawn from the consolidated ERP feature list, are deferred to Phase 2. Items extending Phase 1 modules are noted as “extended”.

| Cluster | Modules |
| --- | --- |
| Operations & Supply Chain | Purchase, Inventory (extended), Warehouse, Logistics, Supply Chain, Procurement, Material Requirement Planning, Quality Control. |
| Manufacturing & Production | Production, New Product Development, Job Work (Outsource), Job Work (Insource), Maintenance, AMC. |
| Sales & Distribution | Sales Management, Sales Distribution, POS, E-commerce / Aggregator, Import-Export, Bid Management (Domestic & International). |
| Finance & Compliance | Accounts, Finance (extended), Legal & Compliances, Scheme/Cashback/Reward/Gift, Referral & Commission, Cash Management & Settlement (CMSS). |
| Customer & Support | CRM (extended), Complaint & Grievance, IVR / Call Center, SOS Services. |
| Marketing & Content | Digital Marketing, Social Media Management (Social ERP), Content Management (CMS). |
| Tracking & Security | Barcode Management, Geo-Location & Tracking, OTP/MPIN Security (extended). |
| Management & Admin | HRMS / Asset / Admin-IT (extended), Project Management, Operations, Data Management (DRAM), Task Management (extended), LMS (extended). |

You asked me to proceed, so I've detailed all Phase 1 modules below. Two assumptions I'm running with (one-word correction if either is wrong):

- LMS = Learning Management System (employee training/courses, pairs with HRMS). I went this way because CRM already owns leads/pipeline, so Lead Management would be redundant. If you meant Lead Management or Loan Management, tell me and I'll swap that section.

- Multi-tenant SaaS (businesses subscribe to manage their ops) — this shaped the Foundation Layer below. Adjust if "B2C" means individual self-serve.

I've kept this at detailed sub-feature level (pre-Phase 1-cut). Requirement IDs get assigned at the formal-document stage, same as E-Store Mart and QmaxPay.

## SaaS Foundation Layer (mandatory groundwork)

Tenant Management

- Tenant signup & provisioning, workspace/subdomain creation

- Tenant profile & settings, per-tenant data isolation

- Suspend / reactivate / delete tenant

Subscription & Billing

- Plans/tiers with feature gating per plan

- Billing cycles, trials, upgrades/downgrades, proration

- Payment collection (natural hook into QmaxPay/1Q1Pay), invoices, dunning/failed-payment handling

User & Access Control

- User invite & lifecycle, RBAC with module-level permissions

- Predefined + custom roles

Authentication & Security

- Email/password, OTP, MPIN, optional 2FA

- Session management, password policies, audit logs

Platform Super-Admin

- Tenant oversight, plan management, usage monitoring, support impersonation

Notifications

- Email / SMS / in-app, templates, user preferences

# SOW

OMARA DIGITECH PVT. LTD. One Ecosystem. Endless Possibilities. STATEMENT OF WORK Design, Build & Delivery of the Omara Digitech Digital Ecosystem 6 Static Websites • QmaxPay • E-Mart • 1Q1Pay • Fincomax • ERP Suite

| Prepared by | 365 AI Tech Solutions (Delivery Partner) |
| --- | --- |
| Prepared for | Omara Digitech Pvt. Ltd. (Rudranjali Organics Group) |
| Engagement model | Fixed-price, milestone-based |
| Overall duration | 4–5 months from contract signing (incl. 2–3 week Requirement phase) |
| Document version | 1.0 — For Client Review & Sign-Off |
| Classification | Strictly Private & Confidential |
| Date of issue | 4 July 2026 |

# Table of Contents

# Document Control

| Field | Detail |
| --- | --- |
| Document title | Statement of Work — Omara Digitech Digital Ecosystem (Phase 1) |
| Prepared by | 365 AI Tech Solutions |
| Prepared for | Omara Digitech Pvt. Ltd. (Rudranjali Organics Group) |
| Engagement | Phase 1 build of 6 static websites and 5 software platforms |
| Commercial value | ₹12–14 Lakh + applicable GST — final value confirmed after Phase 0 discovery |
| Pricing model | Fixed-price, milestone-based |
| Overall duration | 4–5 months from contract signing (incl. 2–3 week requirement phase) |
| Version | 1.0 — initial Statement of Work |
| Status | For Client Review & Sign-Off |
| Classification | Strictly Private & Confidential |
| Date of issue | 4 July 2026 |

## Version History

| Version | Date | Author | Summary of Change |
| --- | --- | --- | --- |
| 1.0 | 04 Jul 2026 | 365 AI Tech Solutions | Initial Statement of Work consolidating the Project Execution Proposal and the QmaxPay, E-Mart, 1Q1Pay, Fincomax and ERP Suite SRS baselines into a single contractual scope document. |

## Basis of this Statement of Work

This Statement of Work (“SOW”) is issued under, and is to be read together with, the Master Services Agreement (“MSA”) to be executed between the parties. It converts the approved Project Execution Proposal and the five signed-off Software Requirements Specifications (SRS) — QmaxPay, E-Mart, 1Q1Pay, Fincomax and the ERP Suite — into a single, contractual scope, deliverable, timeline and acceptance baseline for the Phase 1 build. In the event of conflict between this SOW and the signed agreement, the signed agreement prevails.

# 1. Introduction & Purpose

Omara Digitech Pvt. Ltd. is establishing an integrated digital ecosystem spanning a corporate web presence, a B2B payment-API infrastructure, a retail fintech platform, a multi-tier e-commerce engine, a professional-services marketplace, and an internal operations ERP. This SOW defines the complete scope of work, deliverables, delivery approach, timeline, commercial terms, acceptance criteria and mutual responsibilities under which 365 AI Tech Solutions will design, build, test and go-live with the Phase 1 release of all of these in a single, coordinated programme.

The engagement is organised into seven workstreams delivered across three release waves, anchored by an upfront requirement gathering sprint (Phase 0) that locks requirements before any code is written. The programme is priced within a band of ₹12–14 Lakh plus applicable GST — the exact value is fixed at the close of Phase 0 and will, in all cases, fall within this range.

## 1.1 Scope Summary — What the Client Receives

• Six responsive, SEO-compatible static brand websites — delivered inside the first month.

• ERP suite, E-Mart multi-tier commerce platform and the Qmax API Panel — delivered within 2.5 - 3 months.

• 1Q1Pay fintech platform, Fincomax marketplace & compliance platform — delivered within 4 - 4.5 months, with integrated go-live and stabilisation by month 5.

• A locked, signed-off requirement baseline; a sprint-based build with fortnightly demos; full QA, UAT support, and a post-go-live warranty.

## 1.2 Ecosystem Structure & Ownership Map

The deliverables form a single connected ecosystem rather than seven independent products. Ownership and integration are distinct concerns, and the build sequence respects both.

| Entity | Type | Role in the Ecosystem |
| --- | --- | --- |
| Rudranjali Organics | Static website (corporate parent) | Group holding company; brand story, vision/mission, group structure. |
| Omara Digitech | Static website (tech subsidiary) | Technology arm; portfolio of the platforms below. |
| QmaxPay | Software — B2B API panel | Payment-API infrastructure; the engine that powers 1Q1Pay. |
| 1Q1Pay | Software — retail fintech | Aggregated retail payment/banking services over QmaxPay; powers payments for E-Mart & Fincomax. |
| E-Mart | Software — multi-tier e-commerce | Distributor → Wholesaler → Retailer → Customer chain; checkout via QmaxPay/1Q1Pay. |
| Fincomax | Software — marketplace + compliance | Upwork-style professional-services marketplace; payments routed through 1Q1Pay. |
| ERP Suite | Software — operations platform | HRMS, CRM, Finance, Task & Team, Inventory, LMS on a multi-tenant SaaS foundation. |

Integration is not ownership: QmaxPay feeds 1Q1Pay, and 1Q1Pay carries payments for E-Mart and Fincomax. This dependency chain drives the release sequencing in Section 7 — the payment rail (QmaxPay) is built first so the platforms that depend on it can integrate against a stable interface.

## 1.3 Definitions & Abbreviations

| Term | Meaning |
| --- | --- |
| SOW | This Statement of Work. |
| SRS | Software Requirements Specification — the signed-off requirement baseline per platform. |
| MVP / Phase 1 | Minimum Viable Product depth: every module present in thin, working, end-to-end form. |
| Phase 0 | Discovery, requirement-lock and readiness sprint preceding the build. |
| SPOC | Single Point of Contact — the client’s empowered decision-maker for the engagement. |
| UAT | User Acceptance Testing performed by the client against agreed acceptance criteria. |
| RBAC | Role-Based Access Control. |
| Rails | Live payment/banking services (AEPS, DMT, BBPS, recharge, UPI/QR, payment gateway). |
| CR | Change Request under the change-control process (Section 12). |
| Requirement ID | Traceable identifier per module, e.g. EM-UM-01, 1QP-KYC, QMX, FCX-, ERP-FND-001. |

# 2. Scope of Work — Summary

All software is delivered at Phase 1 (MVP) depth as defined in the approved Software Requirements Specifications. The table below summarises the seven workstreams; detailed, module-level scope follows in Section 3.

| # | Workstream | Phase 1 Size | Phase 1 Coverage |
| --- | --- | --- | --- |
| 1 | 6 Static Brand Websites | 6 sites | Responsive corporate/product marketing sites with shared design system, CMS-lite content, enquiry forms, SEO meta. |
| 2 | QmaxPay — API Panel | 17 modules | API catalog, single-provider routing, prepaid wallet, single-tier reseller panel, developer portal, ledger & reports. |
| 3 | E-Mart — Multi-Tier Commerce | 17 modules | Multi-tier sourcing, catalog, inventory, orders, single gateway + COD, GST billing, admin & support. |
| 4 | 1Q1Pay — Fintech Platform | 22 modules | AEPS/DMT/BBPS/recharge/UPI over QmaxPay, single-tier retailer channel, prepaid wallet, KYC, settlement & reports. |
| 5 | Fincomax — Marketplace & Compliance | ~20 modules | Job marketplace, proposals, hiring, engagement workspace, messaging, reviews, compliance catalog/tracking, document vault. |
| 6 | ERP Suite | 6 modules + foundation | LMS, CRM, HRMS, Inventory, Finance, Task & Team on a multi-tenant SaaS foundation (auth, RBAC, billing, super-admin). |
| 7 | Phase 0 — Discovery & Readiness | 1–2 weeks | Requirement lock, delivery planning, environment & access readiness, sign-off baseline. |

# 3. Detailed Scope of Work by Workstream

Each workstream below states its Phase 1 module coverage, the locked design decisions that bound it, the indicative sprint sequence, and the explicit exclusions that hold the scope boundary. Module and requirement IDs are carried from the signed SRS baselines to preserve traceability.

## 3.1 Workstream 1 — Six Static Brand Websites

Six responsive marketing/corporate sites built on a shared design system and component library for speed and visual consistency: Rudranjali Organics, Omara Digitech, QmaxPay, 1Q1Pay, Fincomax and E-Mart.

• Up to 6–8 content pages per site (home, about/vision-mission, products/services, ecosystem, news/announcements, careers where relevant, contact).

• Lightweight CMS for editable text/images/banners; contact & enquiry forms with email routing and spam protection.

• Responsive layouts, SEO meta, sitemap, analytics tag, and basic performance optimisation.

• Brand-aligned visuals from supplied logos / colour palette; client provides final copy, imagery and legal pages.

Excluded (Phase 2+): e-commerce / transactional features on the static sites, multi-language, blog editorial workflows, and bespoke per-page animations beyond the agreed design system.

## 3.2 Workstream 2 — QmaxPay API Panel (Phase 1)

A B2B API repository and panel with 17 functional modules built to the QmaxPay SRS guardrails. QmaxPay is the payment-API engine that powers 1Q1Pay and, through it, checkout for E-Mart and Fincomax; it is therefore delivered first.

### Locked Decisions

| Decision Area | Locked Choice |
| --- | --- |
| Routing model | Single provider per API — no routing, no failover, no least-cost logic. |
| Reseller model | Single-tier resellers under Super Admin — no sub-reseller cascades. |
| Billing model | Prepaid wallet only — no postpaid / credit. |
| Margins | Report-only — auto-credited, no payouts. |
| Documentation | Static docs — no live try-it console. |

### Phase 1 Modules (17)

| # | Module | Phase 1 Coverage |
| --- | --- | --- |
| 1 | User & Identity Management | Super Admin / Reseller / Developer-Merchant roles; approvals; no sub-users. |
| 2 | API Repository / Catalog | Catalog of payment, payout, recharge/BBPS, AEPS, KYC/verification APIs. |
| 3 | Provider / Upstream Aggregation | One provider bound per API; upstream credential config. |
| 4 | API Key & Credential Management | Key issuance, rotation, environment scoping. |
| 5 | Subscription, Plans & Pricing | Plan definition and per-plan API access. |
| 6 | Wallet, Credits & Billing | Prepaid wallet, credit top-up, usage debit, billing ledger. |
| 7 | Transaction & Routing Engine | Request execution against the bound provider; transaction log. |
| 8 | Reseller / White-Label Panel | Single-tier reseller onboarding, own markup, branded panel, own reports. |
| 9 | Settlement & Payout | Report-only margin settlement; no automated payouts. |
| 10 | Developer Portal & Documentation | Static docs, keys, wallet, usage & transactions. |
| 11 | Webhooks & Callbacks | Event callbacks to subscribers. |
| 12 | Rate Limiting, Quota & Throttling | Per-key limits and quota enforcement. |
| 13 | Reports & Analytics | Usage, transaction and revenue reporting. |
| 14 | Risk, Fraud & Compliance | Baseline risk controls and audit. |
| 15 | Notifications & Alerts | Fixed-trigger email/SMS/in-app alerts. |
| 16 | Admin Control Panel | Provider & pricing config, user approvals, settings. |
| 17 | Support & Ticketing | Merchant ticket queue and resolution. |

Guardrails: one provider per API, single-tier resellers, prepaid-only wallet, report-only margins, static documentation, fixed notification triggers. Provider go-live depends on client-supplied credentials and third-party approvals (Section 11).

Detailed scope breakdown is in Appendix

## 3.3 Workstream 3 — E-Mart Multi-Tier Commerce (Phase 1)

A single web admin application delivering one coherent end-to-end flow across the Distributor → Wholesaler/Master → Retailer → Customer chain, covering all 17 modules at Phase 1 depth (EM-UM through EM-ST).

### Constraints (Locked)

• Web-based responsive platform (desktop + mobile browser); no native apps in Phase 1.

• Single payment gateway (QmaxPay / 1Q1Pay) plus Cash on Delivery.

• Indian tax regime — GST (CGST / SGST / IGST); manual admin verification of B2B documents.

• Sourcing logic is a per-product / region Strict / Flexible toggle, not a rules-priority engine.

### Phase 1 Modules (17) & Requirement Sets

| ID | Module | Phase 1 Coverage |
| --- | --- | --- |
| EM-UM | User & Identity Management | Five roles; customer self-activation; B2B pending-approval; manual PAN/GST review; OTP login. |
| EM-HS | Multi-Tier Hierarchy & Sourcing | Manual tier mapping; per-product/region Strict or Flexible sourcing; no auto-fallback. |
| EM-PC | Product Catalog | Two-level categories; SKU/HSN/variants; form or Excel import; admin approval. |
| EM-PR | Pricing & Margin | One price per tier; quantity slab; optional region price; immediate edits. |
| EM-IN | Inventory & Warehouse | Per-tier stock; manual inward/outward; reservation on order; low-stock alerts. |
| EM-SF | Storefront / Customer | Search, browse, filters; product page; cart; registered-user checkout; reorder. |
| EM-OM | Order Management | B2C + B2B orders; tier auto-routing; stock/credit checks; GST invoice; lifecycle to Delivered. |
| EM-PO | Procurement / Purchase | Tier-to-upstream PO; manual fulfilment; PO close. |
| EM-PM | Payment & Wallet | Online gateway + COD; per-tier credit ledger & limit; manual refunds. |
| EM-LD | Logistics & Delivery | Pin-code serviceability; flat/zone delivery charge; manual status; self-pickup. |
| EM-CM | Commission & Settlement | Per-tier commission (flat/%); report-only earnings. |
| EM-PT | Promotions & Marketing | Coupon codes; homepage banner management. |
| EM-RP | Reports & Analytics | Role-scoped dashboards; sales/inventory/GST/commission reports; Excel export. |
| EM-TX | Tax & Compliance | GST config; CGST/SGST vs IGST auto-split; HSN; GST invoice. |
| EM-NT | Notifications | Order & B2B-approval triggers over email / SMS / in-app. |
| EM-AD | Admin Control Panel | Master settings, roles, user management, CMS pages, audit log. |
| EM-ST | Support & Ticketing | Raise ticket; admin queue, threaded replies, open/close. |

Excluded (Phase 2+): native mobile apps, partner API gateway, loyalty/rewards, AI forecasting, multi-language/currency, courier APIs, returns flow, partial shipments, sub-users, 2FA, automated KYC.

### Indicative Sprint Sequence (8 sprints, ~2 weeks each)

| Sprint | Focus | Modules / Requirement Sets |
| --- | --- | --- |
| Sprint 0 | Foundation | Project setup, architecture, DB schema, hosting, auth scaffolding. |
| Sprint 1 | Identity & Hierarchy | EM-UM, EM-HS, EM-AD (core admin: users, roles, settings). |
| Sprint 2 | Catalog, Pricing & Stock | EM-PC, EM-PR, EM-IN. |
| Sprint 3 | Storefront & Orders | EM-SF, EM-OM. |
| Sprint 4 | B2B Flow & Money | EM-PO, EM-PM, EM-TX. |
| Sprint 5 | Fulfilment & Comms | EM-LD, EM-NT. |
| Sprint 6 | Revenue & Reporting | EM-CM, EM-PT, EM-RP. |
| Sprint 7 | Support & Hardening | EM-ST, UAT, bug-fix, acceptance demo & sign-off. |

Detailed scope breakdown is in Appendix

## 3.4 Workstream 4 — 1Q1Pay Fintech Platform (Phase 1)

A fintech and payment-services platform aggregating retail banking transactions through QmaxPay and delivering them via a single-tier retailer network — 22 MVP modules across five groups (Requirement IDs 1QP-[Module]-[Number]).

### Locked Decisions

| Decision Area | Resolution |
| --- | --- |
| Fintech provider connectivity | Consume QmaxPay APIs — fintech modules are an orchestration / UX / margin layer; no direct provider integration in Phase 1. |
| Channel model | Single-tier: Retailer → Customer. Distributor tier and multi-level overrides deferred to Phase 2. |
| Wallet model | Prepaid, retailer-funded — retailer wallet, walk-in customers. Customer wallet deferred to Phase 2. |
| Dependency constraint | 1Q1Pay fintech availability is bounded by QmaxPay; reconciliation is against a single counterparty. |

### Phase 1 Module Groups

| Group | Modules |
| --- | --- |
| A · Core Platform & Access | User/Role & Access (USR), Onboarding & KYC (KYC), Retailer Management (RET), Wallet & Balance (WAL). |
| B · Fintech & Payment Services (over QmaxPay) | QmaxPay Integration Layer (QMX), AEPS & Micro-ATM (AEP), Domestic Money Transfer (DMT), BBPS & Bill Payments (BBP), Recharge (RCH), UPI & QR Acceptance (UPI), Identity & Utility Services (IDV). |
| C · Commercial, Settlement & Operations | Pricing, Commission & Margin Engine (PRC), Settlement & Payout (STL), Reporting, MIS & Analytics (RPT), Notifications & Communications (NOT). |
| D · Administration, Compliance & Support | Admin Console & Platform Config (ADM), Compliance, Audit & Security (CMP), Support, Ticketing & Helpdesk (SUP). |

Deferred to Phase 2: Travel Services (TRV), PAN Card Services (PAN), Insurance Services (INS), Loan & Credit Services (LON), plus deferred features within Phase 1 modules.

### Indicative Sprint Sequence (8 sprints)

| Sprint | Focus | Modules |
| --- | --- | --- |
| 1 | Foundation | USR, ADM (base), CMP (security & audit baseline). |
| 2 | Onboarding & Wallet | KYC, RET, WAL. |
| 3 | QmaxPay integration & first rails | QMX, RCH, BBP. |
| 4 | Money movement & identity | DMT, UPI, IDV (e-KYC, PAN verify). |
| 5 | AEPS | AEP (+ biometric device certification). |
| 6 | Money-out & pricing | STL, PRC. |
| 7 | Visibility & support | RPT, NOT, SUP. |
| 8 | Hardening, UAT, compliance review, go-live | All — stabilisation. |

Note: AEPS (Sprint 5) carries an external dependency on biometric device certification; if certification slips, AEP can be decoupled and shipped as a fast-follow without blocking the remaining sprints. Live rails (AEPS, DMT, BBPS, UPI) require sponsor-bank / aggregator agreements, sandbox access and regulatory clearances obtained by the client (Section 11).

Detailed scope breakdown is in Appendix

## 3.5 Workstream 5 — Fincomax Marketplace & Compliance (Phase 1)

A web-based professional-services marketplace connecting clients with verified professionals (CA, CS, Lawyer, Accountant, Bookkeeper, CFA, CFO), with a lean compliance-management layer — approximately 20 modules across six groups (Requirement IDs FCX-). Payments are routed through 1Q1Pay.

### Locked Decisions

| Decision | Resolution |
| --- | --- |
| Product identity | Professional-services marketplace (Upwork-style) with a lean compliance layer. Retail/POS out of scope. |
| Marketplace model | Open job posting plus proposal/bidding; client awards each job to a single professional. |
| Engagement model | Milestone-based engagement with escrow; payment released on client approval. |
| Payments | All collections and payouts routed through 1Q1Pay via a single connector. No direct PSP or bank integration. |
| Compliance scope | Tracking-and-document layer only (catalog, calendar, vault). No government-portal integration or auto-filing. |
| Platform | Web-only responsive; single wallet currency (INR); Indian GST compliance. |
| Verification | Manual Ops review for onboarding; PAN / e-KYC performed via 1Q1Pay. |

### Phase 1 Module Groups

| Group | Coverage |
| --- | --- |
| A · Core Platform & Access | Roles, onboarding & KYC, wallet/billing account. |
| B · Marketplace Front-End & Profiles | Storefront, search & discovery, professional and client profiles. |
| C · Job Marketplace & Engagement | Job posting, proposals/bidding, hiring & contracts, engagement workspace with milestones, messaging, ratings & reviews. |
| D · Compliance Services | Compliance catalog & applicability, tracking & calendar, document collection & vault. |
| E · Payments, Pricing & Settlement | Escrow funding, milestone release, pricing, commission, settlement — all via 1Q1Pay. |
| F · Operations, Admin & Support | Admin console, dispute handling, support, oversight of settlements and payouts. |

Excluded (Phase 2+): Fincomax Books (Phase 2 · 53-module bookkeeping suite, FBK- prefix), automated/third-party/video KYC, e-signature, government-portal integration, auto-filing, penalty calculators, native mobile apps.

Detailed scope breakdown is in Appendix

## 3.6 Workstream 6 — ERP Suite (Phase 1)

A multi-tenant SaaS operations platform with six Phase 1 functional modules on a shared foundation layer (Requirement IDs ERP-[Module]-[NNN]). Team Management is delivered as a thin layer over the HRMS org structure and RBAC rather than as a standalone data model.

### SaaS Foundation Layer (mandatory MVP groundwork)

| Area | MVP Requirements |
| --- | --- |
| Tenancy | Self-service signup & automated provisioning; tenant profile/settings; per-tenant data isolation; lifecycle (suspend/reactivate/soft-delete). |
| Subscription & Billing | Plans/tiers with module- & feature-level gating; free-trial with auto-expiry; online collection via QmaxPay/1Q1Pay; invoices & payment history. |
| Users & Access | User invite/activate/deactivate; module-level RBAC; predefined roles (Owner, Admin, Manager, Staff). |
| Authentication | Email/password; OTP (email/SMS); MPIN; session timeout; password policy & reset. |
| Platform & Ops | Audit logging; super-admin console (tenant oversight, plan management, usage monitoring); notifications engine (email/SMS/in-app). |

Phase 2 foundation items (deferred): plan upgrade/downgrade proration, dunning & grace period, custom roles with granular permissions, 2FA, support impersonation, notification templates & per-user preferences.

### Phase 1 Functional Modules (6)

| # | Module | Phase 1 Coverage |
| --- | --- | --- |
| 1 | LMS (Learning Management) | Course builder (courses→modules→lessons), content library, enrolment, progress tracking, quizzes & scoring, certificates, completion reports. |
| 2 | CRM | Contact/account management, lead capture, pipeline & deals, activities, follow-up reminders, tags/segmentation, pipeline & conversion reports. |
| 3 | HRMS | Employee master, attendance, leave, payroll basics (payslip; TDS/PF deferred), onboarding/offboarding, org structure, document store, self-service. |
| 4 | Inventory Management | Item master, stock levels (multi-location ready), stock-in/out/adjustments, low-stock alerts, valuation, reports (batch/expiry deferred). |
| 5 | Finance Management | GST-compliant sales invoicing, expense/bill tracking, chart of accounts, receipts & payments, GST reports, P&L / receivables / payables; CRM & Inventory hooks. |
| 6 | Task & Team Management | Tasks with status workflow & Kanban/list, subtasks/checklists, comments/attachments, linking, reminders; team creation/membership as a thin layer over HRMS & RBAC. |

### Non-Functional Baseline

• Multi-tenant scaling; TLS in transit + at-rest encryption; audit logging; automated backup; responsive web; 99.5% target availability.

Open assumptions confirmed at Phase 0 sign-off: A-01 LMS = Learning Management (not Lead/Loan Management); A-02 multi-tenant SaaS for businesses (not individual consumers). Phase 2 (~43 modules: operations, supply chain, manufacturing, sales, marketing) is excluded.

Detailed scope breakdown is in Appendix

## 3.7 Workstream 7 — Phase 0 Discovery, Requirement Lock & Readiness

Before any build begins, a rigorous discovery sprint (2–3 weeks) converts the existing SRS baselines into a locked, signed delivery plan. This phase is the single most important protection against downstream rework.

• Requirement walkthrough and confirmation of every module’s Phase 1 depth and exclusions, per platform.

• Confirmation of open assumptions (e.g. ERP A-01/A-02) and architectural decisions.

• Integration mapping: QmaxPay → 1Q1Pay → E-Mart / Fincomax payment contracts and shared identity/wallet behaviour.

• Environment & access readiness checklist: cloud/hosting, repositories, domains, third-party sandbox credentials, content and brand assets.

• Detailed sprint plan, UAT plan, acceptance criteria and the signed requirement baseline.

Deliverable: a signed Delivery Plan & Requirement Baseline, together with the confirmed contract value fixed within the ₹12–14 Lakh band. The build clock for each workstream starts only against this baseline; subsequent changes follow the change-control process in Section 12.

# 4. Deliverables Register

The following are the contractual deliverables of the engagement. Acceptance of each is governed by Section 8 (Acceptance, Warranty & Support).

| Ref | Deliverable | Form | Milestone |
| --- | --- | --- | --- |
| D-0 | Signed Delivery Plan & Requirement Baseline (incl. confirmed contract value) | Document + sign-off | M1 |
| D-1 | Six responsive static brand websites, live | Deployed web + CMS | M2 |
| D-2 | QmaxPay API Panel (17 modules) | Deployed web app | M3 |
| D-3 | E-Mart Multi-Tier Commerce (17 modules) | Deployed web app | M3 |
| D-4 | 1Q1Pay Fintech Platform (22 modules) | Deployed web app | M4 |
| D-5 | Fincomax Marketplace & Compliance (~20 modules) | Deployed web app | M4 |
| D-6 | ERP Suite (6 modules + SaaS foundation) | Deployed multi-tenant app | M4 |
| D-7 | Integrated go-live, stabilisation & project closure | Production release + handover | M5 |
| D-8 | QA artefacts, UAT support, source/IP transfer & warranty | Repos + documentation | M5 |

# 5. Out of Scope (Phase 2 and Beyond)

The following are explicitly excluded from this engagement and recorded to prevent scope creep. They can be quoted as future phases under change control.

• Native mobile applications for any platform (Phase 1 is responsive web).

• QmaxPay: smart/least-cost routing, multi-provider failover, sub-reseller cascades, automated payouts & reconciliation, postpaid/credit billing, interactive API console & SDKs, public status/SLA monitoring, third-party publisher marketplace.

• E-Mart: partner API gateway, loyalty/rewards, AI forecasting & auto-replenishment, multi-language/multi-currency, courier APIs & live tracking, returns and partial-shipment flows.

• 1Q1Pay: Travel, PAN, Insurance, Loan & Credit services; distributor tier / multi-level overrides; customer wallet.

• Fincomax: Fincomax Books (53-module bookkeeping suite), automated/third-party/video KYC, e-signature, government-portal integration, auto-filing, penalty calculators.

• ERP: the ~43 Phase 2 modules (operations, supply chain, manufacturing, sales, marketing, project management, CMS, etc.) and any extensions to Phase 1 modules.

• Cross-cutting: data migration from legacy systems, third-party licensing, content authoring/copywriting, paid marketing, ongoing managed hosting/support beyond the warranty period, and any statutory licensing or legal/regulatory advisory.

Detailed scope breakdown is in Appendix

# 6. Delivery Approach & Methodology

## 6.1 Phase 0 — Discovery, Requirement Lock & Readiness (2–3 weeks)

As detailed in Section 3.7, discovery locks scope and produces the signed baseline before the build clock starts. Deliverable: signed Delivery Plan & Requirement Baseline with the confirmed contract value fixed within the ₹12–14 Lakh band.

## 6.2 Agile, Sprint-Based Build

Each platform is built on its already-defined sprint sequence (the E-Mart and 1Q1Pay 8-sprint plans, the Fincomax sprint plan, the ERP build-sprint sequence). Two-week sprints run with a working demo at each sprint close, so progress is visible and course-corrections are cheap.

• Fortnightly sprint demos and a shared progress dashboard.

• Continuous integration with code review; staged environments (dev → staging → UAT).

• Release waves sequenced by dependency: static sites first, then QmaxPay + E-Mart, then 1Q1Pay + Fincomax + ERP.

## 6.3 Quality Assurance

• Test cases derived from the requirement IDs in each SRS, ensuring traceability from requirement to test.

• Functional, integration, regression, cross-browser and responsive testing; security smoke testing on auth, RBAC and payment flows.

• Defect triage by severity (Sev-1 to Sev-4); Sev-1/Sev-2 are gating for UAT sign-off.

## 6.4 Security & Data Protection Posture

• TLS in transit and encryption at rest; role-based access control and secure session handling across platforms.

• Secrets/credential management for third-party API keys; audit logging of key actions.

• Least-privilege access to environments; PII handled per the data-protection clause in Section 15.

## 6.5 Governance & Communication

| Cadence | Forum | Participants & Purpose |
| --- | --- | --- |
| Daily | Internal stand-up | Delivery team — progress, blockers. |
| Weekly | Status report + call | Client SPOC — RAG status, risks, decisions needed. |
| Fortnightly | Sprint demo | Stakeholders — working software review & feedback. |
| Per milestone | Acceptance review | Client sign-off against acceptance criteria. |

A single Client SPOC with decision authority is required to keep the cadence and timeline intact.

# 7. Project Timeline & Milestones

The programme runs over 4–5 months from contract signing. Release waves overlap where dependencies allow, so the static sites and the QmaxPay/E-Mart wave are well underway before the final wave begins.

## 7.1 Release Schedule

| Wave | Deliverable | Window | Target Completion |
| --- | --- | --- | --- |
| Phase 0 | Discovery, requirement lock & readiness | Weeks 2–3 | End of Week 3 |
| Wave 1 | 6 Static Brand Websites — live | Weeks 2–4 | End of Month 1 |
| Wave 2 | QmaxPay API Panel + E-Mart — UAT Offer | Weeks 3–10 | Month 2.5 |
| Wave 3 | 1Q1Pay + Fincomax + ERP Suite — UAT Offer | Weeks 5–16 | Month 4.5 |
| Closeout | Integrated UAT, stabilisation & go-live | Weeks 16–20 | Month 5 |

## 7.2 Payment-Linked Milestones

| Milestone | Trigger | Target | % of Fee |
| --- | --- | --- | --- |
| M0 — Mobilisation | Contract signing & kickoff | Week 0 | 15% |
| M1 — Baseline locked | Phase 0 requirement & delivery-plan Offer | End Week 3 | 10% |
| M2 — Websites live | 6 static websites accepted | End Month 1 | 10% |
| M3 — Wave 2 accepted | QmaxPay + E-Mart UAT sign-off + ERP UAT Offer | Month 2.5 | 30% |
| M4 — Wave 3 accepted | 1Q1Pay + Fincomax Offer | Month 4.5 | 25% |
| M5 — Go-live & closure | Integrated go-live & project closure | Month 5 | 10% |

Timelines assume on-time milestone sign-offs, timely provision of third-party credentials/approvals, and a continuously available Client SPOC. Client-side delays pause the affected workstream clock (Sections 10, 13).

# 8. Acceptance, Warranty & Support

## 8.1 Acceptance & Deemed Acceptance

• Each milestone is delivered with acceptance criteria agreed at Phase 0. The client tests within a 7-10 business-day UAT window per milestone.

• Sign-off is given when no open Sev-1/Sev-2 defects remain. Sev-3/Sev-4 items are scheduled within warranty and do not block acceptance.

## 8.2 Platform Acceptance Gates

The following demonstrable, end-to-end flows constitute the sign-off gate for the key platforms:

### E-Mart — Phase 1 sign-off gate

1. A Distributor is onboarded and approved, and lists a product with tier pricing and stock.

2. A Retailer (mapped, under a sourcing toggle) raises an order/PO and it routes to the correct upstream seller.

3. A Customer places and pays for an order; a GST-compliant invoice is generated with correct tax breakup.

4. Stock decrements, the credit ledger updates, and order status moves through the full lifecycle to Delivered.

5. Notifications fire on the defined triggers, and the admin can view orders, sales, inventory, and commission reports.

### 1Q1Pay / QmaxPay — Phase 1 sign-off gate

• A retailer is KYC-onboarded, funds a prepaid wallet, and successfully executes a transaction on each enabled rail (recharge/BBPS, and any live rails whose credentials the client has supplied) routed through QmaxPay, with the wallet debited, margin recorded, and the transaction visible in reports and settlement.

### Fincomax — Phase 1 sign-off gate

• A client posts a job, a verified professional bids and is hired, escrow is funded via 1Q1Pay, a milestone is delivered and approved, payout is released, and a compliance item is tracked with a document stored in the vault.

### ERP Suite — Phase 1 sign-off gate

• A tenant self-signs-up and is provisioned in isolation, subscribes and pays via QmaxPay/1Q1Pay, invites users under RBAC roles, and exercises a core flow in each of the six modules (e.g. LMS enrolment→certificate, CRM lead→deal, HRMS leave request→approval, Inventory stock-in→report, Finance GST invoice, Task create→complete).

## 8.3 Defect Severity

| Severity | Definition | Handling |
| --- | --- | --- |
| Sev-1 Critical | Core flow unusable; no workaround. | Gating; fixed before sign-off. |
| Sev-2 Major | Significant function impaired; workaround exists. | Gating; fixed before sign-off. |
| Sev-3 Minor | Limited impact, minor defect. | Scheduled within warranty. |
| Sev-4 Cosmetic | Cosmetic / UI nicety. | Best-effort / backlog. |

## 8.4 Warranty

A 60-day warranty from each go-live covers Sev-1/Sev-2 defects against the signed baseline at no charge. The warranty excludes new requirements, enhancements, third-party/provider faults, issues from client-side configuration or data, and changes made outside the delivery partner’s control.

## 8.5 Post-Warranty Support

Ongoing support, maintenance, managed hosting and Phase 2 enhancements are available under a separate Annual Maintenance/Support agreement, quoted on request.

# 9. Team, Roles & Responsibilities

## 9.1 Delivery Team

A dedicated, cross-functional pod delivers the programme, scaled across the three waves. Roles may be shared across workstreams to maintain consistency and cost efficiency.

| Role | Responsibility |
| --- | --- |
| Engagement / Delivery Manager | Single accountable owner; governance, milestones, risk and client communication. |
| Solution Architect | Cross-platform architecture, integration contracts (QmaxPay ↔ 1Q1Pay ↔ E-Mart/Fincomax), tech standards. |
| Backend Engineers | APIs, business logic, data models, third-party integrations, multi-tenant foundation. |
| Frontend Engineers | Admin panels, storefronts, retailer/customer touchpoints, responsive UI. |
| Web / UI Developer | Static websites, shared design system, brand-aligned templates. |
| QA Engineer(s) | Test design from requirement IDs, functional/regression/integration testing, defect triage. |
| DevOps (Not as part of this Phase) | Environments, CI/CD, deployments, backups, monitoring. |

## 9.2 Responsibility Matrix (RACI)

R = Responsible · A = Accountable · C = Consulted · I = Informed. “Partner” denotes 365 AI Tech Solutions; “Client” denotes Omara Digitech.

| Activity | Partner | Client |
| --- | --- | --- |
| Requirement lock & baseline sign-off (Phase 0) | R | A |
| Architecture & integration contract design | A / R | C |
| Sprint build, QA & staged deployment | A / R | I |
| Provision of third-party credentials & sandbox/prod access | C | A / R |
| Regulatory licences, sponsor-bank & aggregator agreements | I | A / R |
| Content, brand assets, copy & legal pages | C | A / R |
| UAT execution & milestone sign-off | C | A / R |
| Go-live, stabilisation & handover | A / R | C |
| Change-request assessment & pricing | A / R | A |
| Milestone invoicing & payment | R | A / R |

Engagement model: fixed-price, milestone-based. The delivery partner retains delivery management and quality ownership end-to-end.

# 10. Client Responsibilities & Dependencies

Timely fulfilment of the following is essential to the timeline. Delay in any item pauses the clock on the affected workstream, and resulting schedule slippage is not attributable to the delivery partner.

• Nominate an empowered SPOC and make stakeholders available for discovery, demos and acceptance within the agreed windows.

• Provide all content, copy, logos, brand assets, legal/policy pages and product data for the websites and platforms.

• Procure and hand over all third-party accounts and credentials: cloud/hosting, domains, SSL, repositories, SMS/email gateways.

• Obtain and provide fintech enablement: payment-aggregator/PG merchant accounts, sponsor-bank/AEPS/DMT/BBPS/UPI agreements, sandbox and production credentials, and any KYC-vendor contracts.

• Secure all statutory licences, registrations and regulatory approvals required to operate the fintech and compliance services.

• Provide UAT resources and complete acceptance testing within each milestone’s UAT window.

• Settle milestone invoices within the agreed credit period.

# 11. Third-Party, Regulatory & Compliance Dependencies

Several capabilities — particularly within QmaxPay, 1Q1Pay and Fincomax — depend on external parties and regulatory clearances outside the delivery partner’s control. This section is a material protection and is read together with Sections 10, 13 and 15.

## 11.1 Third-Party Integration Dependency

Live payment and banking rails (AEPS, DMT, BBPS, recharge, UPI/QR, payment gateway) depend on the availability, behaviour, sandbox access and production approval of external aggregators, banks and providers. The delivery partner delivers software ready to integrate against documented interfaces; activation of any live rail is contingent on the client supplying working credentials and the provider granting go-live. Live-rail enablement timelines are estimates and may shift with provider lead times.

## 11.2 Regulatory & Licensing Dependency

The delivery partner delivers software capability only. Obtaining and maintaining all licences, registrations and statutory approvals — including any payment-aggregator/payment-gateway authorisation, NBFC/lending permissions, AEPS sponsorship, GST e-invoicing enablement and professional-services compliance obligations — is solely the client’s responsibility. The delivery partner does not provide legal, financial, tax or regulatory advice, and is not liable for the client’s regulatory standing.

## 11.3 Compliance-Engine Disclaimer (Fincomax)

The Fincomax compliance catalog, tracking and calendar are administrative tools maintained from client-supplied data. They do not constitute legal or statutory advice, do not auto-file with any authority, and do not guarantee compliance outcomes. Responsibility for the accuracy and statutory correctness of any filing rests with the client and the engaged professionals.

# 12. Commercial Proposal

Indicative Commercial Range: ₹12–14 Lakh + applicable GST This is an indicative range. The exact contract value is fixed at the close of the Phase 0 detailed requirement-gathering and delivery-planning stage, once module depth and integration scope are confirmed against the signed baseline. In every case the final value will fall between ₹12 Lakh and ₹14 Lakh.

## 12.1 Payment Schedule

Payments are milestone-based per the percentage split below, raised on milestone achievement (Section 7.2) and payable within the agreed credit period (Section 15). The rupee value of each milestone is the stated percentage of the final confirmed contract value; the last two columns show the value at each end of the ₹12–14 Lakh band.

| Milestone | % of Fee | At ₹12L (₹) | At ₹14L (₹) |
| --- | --- | --- | --- |
| M0 — Mobilisation (on signing) | 15% | 1,80,000 | 2,10,000 |
| M1 — Requirement baseline sign-off | 10% | 1,20,000 | 1,40,000 |
| M2 — Static websites accepted | 10% | 1,20,000 | 1,40,000 |
| M3 — QmaxPay + E-Mart UAT sign-off | 30% | 3,60,000 | 4,20,000 |
| M4 — 1Q1Pay + Fincomax + ERP UAT sign-off | 25% | 3,00,000 | 3,50,000 |
| M5 — Go-live & project closure | 10% | 1,20,000 | 1,40,000 |
| Total | 100% | 12,00,000 | 14,00,000 |

## 12.2 Commercial Notes

• The contract value is confirmed at the close of Phase 0 and will be between ₹12 Lakh and ₹14 Lakh; the milestone percentages above then apply to that confirmed value.

• All amounts are in Indian Rupees and exclusive of GST and any other applicable statutory taxes/levies, charged at actuals.

• Third-party costs are excluded and billed at actuals or borne directly by the client: cloud/hosting, domains, SSL, SMS/email gateways, payment-aggregator/AEPS/BBPS/UPI charges, KYC vendor fees, and any paid licences.

• This SOW is valid for 30 days from the date of issue.

• Scope changes are handled through the change-control process (Section 13) and priced separately.

# 13. Change Management & Scope Control

The signed requirement baseline (Phase 0) defines what is in scope. Any addition, removal or material modification is managed through a written Change Request (CR) and is not absorbed silently.

1. The client raises a CR, or the delivery partner raises one where a request exceeds the baseline.

2. The delivery partner assesses impact on scope, effort, cost and timeline and issues a written estimate.

3. Work on the CR begins only after the client approves it in writing; cost and schedule are adjusted accordingly.

4. Minor clarifications consistent with the baseline are handled within sprints at no charge; anything that changes module depth, adds modules, or pulls Phase 2 items forward is a chargeable CR.

Repeated or cumulative changes that materially affect the critical path may shift downstream milestone dates. The fixed price is valid against the locked baseline only.

# 14. Assumptions

This SOW is prepared on the following assumptions. If any prove incorrect at Phase 0, scope, cost and/or timeline will be revisited through change control.

1. All software is delivered at Phase 1 (MVP) depth as defined in the approved SRS documents; every module is present in thin, working form.

2. Static websites are informational/marketing sites with CMS-lite editing; they are not transactional.

3. QmaxPay operates one provider per API, prepaid-only wallets, single-tier resellers and report-only margins.

4. 1Q1Pay uses a single-tier retailer→customer channel and retailer-funded prepaid wallets; live rails depend on client-provided agreements/credentials.

5. E-Mart is web-only (no native mobile apps), single payment gateway plus COD, manual B2B onboarding verification.

6. Fincomax routes payments through 1Q1Pay; KYC review is manual; Fincomax Books (Phase 2) is excluded.

7. ERP is a multi-tenant SaaS for businesses; LMS denotes Learning Management; English UI at MVP.

8. The client provides timely sign-offs, content/brand assets, and all third-party accounts, credentials and sandbox/production approvals.

9. Hosting, infrastructure and third-party service fees are outside the quoted fee.

10. One empowered Client SPOC is available throughout the engagement.

# 15. Commercial Terms & Conditions

## 15.1 Payment Terms

• Milestone invoices are payable within 7 days of invoice date unless otherwise agreed in the contract.

## 15.2 Intellectual Property

• On receipt of full payment, IP in the bespoke deliverables created for the client transfers to the client.

• Pre-existing tools, frameworks, libraries, reusable components and know-how remain the property of the delivery partner and are licensed to the client for use within the deliverables.

• Third-party/open-source components remain under their respective licences.

## 15.3 Confidentiality & Data Protection

• Each party keeps the other’s confidential information secure and uses it only for the engagement.

• The delivery partner handles client and end-user data under applicable Indian data-protection law and the agreed security posture; the client remains the data controller and is responsible for lawful collection and consent.

## 15.4 Limitation of Liability

• Aggregate liability under the engagement is capped at the total fees actually paid for the affected workstream.

• Neither party is liable for indirect, incidental, consequential, or loss-of-profit/data damages.

• The delivery partner is not liable for losses arising from third-party services, provider outages, the client’s regulatory standing, or client-supplied data/configuration.

## 15.5 Timeline Contingencies & Force Majeure

• Dates assume on-time sign-offs, credentials and payments; client-side delay shifts the affected schedule by at least the delay period.

• Neither party is liable for delays caused by events beyond reasonable control (force majeure).

## 15.6 Termination

• Either party may terminate for material, uncured breach on 15 days’ written notice.

• On termination, the client pays for all work completed and in-progress to the termination date, including the current milestone pro-rata; accepted deliverables and their IP follow the payment terms above.

## 15.7 General

• This SOW forms the basis of a definitive agreement; in any conflict, the signed agreement prevails.

• Governing law and jurisdiction to be specified in the definitive agreement.

# 16. Risk Management

| Risk | Mitigation |
| --- | --- |
| Scope creep across seven workstreams | Locked Phase 0 baseline + formal change control (Sections 13, 14). |
| Third-party / provider sandbox or go-live delays | Software built to documented interfaces; client procures credentials early; clock pauses on dependency (Sections 10, 11). |
| Regulatory/licensing delays affecting fintech go-live | Clear delineation that licensing is client-owned; software delivered ready-to-integrate (Section 11). |
| Late sign-offs / SPOC unavailability | Defined cadence, UAT windows and deemed-acceptance (Sections 6, 8). |
| Aggressive timeline vs. broad scope | Phase 1 MVP depth, dependency-sequenced waves, reusable design system, parallel streams (Sections 3, 7). |
| Integration risk (QmaxPay ↔ 1Q1Pay ↔ E-Mart/Fincomax) | QmaxPay built first; integration contracts fixed at Phase 0; staged environments. |

# 17. Acceptance & Sign-Off

By signing below, the parties confirm agreement to the scope, deliverables, timeline, commercial terms and mutual responsibilities set out in this Statement of Work. This SOW is executed under, and subject to, the Master Services Agreement between the parties.

| For 365 AI Tech Solutions Name: Designation: Signature: Date: | For Omara Digitech Pvt. Ltd. Name: Designation: Signature: Date: | Witness Name: Designation: Signature: Date: |
| --- | --- | --- |

Strictly Private & Confidential — Omara Digitech Pvt. Ltd.

### Appendix 1 - QmaxPay — Detailed Scope

Phase 1 Functional Module

1. User & Identity Management

· Three roles only: Super Admin, Reseller, Developer/Merchant

· Self-registration form: name, business name, mobile, email, PAN, GSTIN

· New B2B accounts land in Pending; admin reviews uploaded PAN/GST → marks Active or Rejected

· Login via mobile/email + OTP

· Profile holds business name, contact, GSTIN, one address

· Account states limited to: Pending, Active, Rejected

· No sub-users, no staff accounts, no automated KYC validation, no 2FA

2. API Repository / Catalog Management

· Admin-maintained list of APIs, each with: name, category, description, status (Live/Inactive)

· One production endpoint URL per API

· A linked documentation reference per API (points to the doc page in Module 10)

· Merchants browse only Live APIs they're entitled to

· No versioning, no beta/deprecated states, no self-service publishing

3. Provider / Upstream Aggregation Engine

· Each API mapped to exactly one upstream provider

· Admin stores provider credentials and the base (cost) price per API

· Manual enable/disable toggle per API-provider mapping

· Requests pass straight through to the mapped provider — no routing, failover, or health checks

4. API Key & Credential Management

· One production key + one sandbox key generated per merchant

· View, regenerate, and revoke keys from the panel

· Basic IP whitelist per key (list of allowed IPs)

· No scopes, no scheduled rotation, no per-API key permissions

5. Subscription, Plans & Pricing

· Admin sets a single per-call price per API

· One flat markup % defined per reseller tier, applied over base price

· One default plan applies to all merchants

· No subscription/slab/volume pricing, no custom enterprise quotes, no bundles

6. Wallet, Credits & Billing

· Prepaid wallet per merchant/reseller

· Each successful API call auto-debits the per-call price from the wallet

· Manual top-up via QmaxPay/1Q1Pay; balance updates on confirmation

· Running ledger of credits and debits

· Basic invoice generated per top-up

· Calls are blocked when balance is insufficient

· No postpaid/credit limits, no auto-debit, no billing cycles, no GST e-invoicing

7. Transaction & Routing Engine

· Receives merchant request, validates key + balance + rate limit

· Forwards to the single mapped provider, receives response

· Returns a normalized response to the merchant

· Idempotency key prevents duplicate processing

· Every request/response logged with timestamp, status, and amount debited

· No retries, no multi-provider normalization, no async queue

8. Reseller / White-Label Panel

· Single tier of resellers, each created under Super Admin

· Reseller onboards its own merchants

· Reseller sets its own markup over the base/admin price

· Branded login: reseller logo + name on the panel

· No sub-reseller chains, no custom domains, no multi-level commission cascade

9. Settlement & Payout

· On each transaction, the reseller's margin (sell price − base price) is auto-credited to the reseller's wallet

· Margins shown as a settlement report only

· No outbound payout run, no provider-statement reconciliation, no hold/release

10. Developer Portal & Documentation

· Static documentation page per API: endpoint, parameters, sample request, sample response

· Sandbox key available for testing

· Copy-paste cURL samples

· No interactive "try-it" console, no SDKs, no auto-generated docs, no changelog

11. Webhooks & Callbacks

· Merchant configures one callback URL

· System POSTs transaction status to that URL after completion

· Delivery attempt is logged

· No multi-event subscriptions, no retry/backoff, no signature-verification UI

12. Rate Limiting, Quota & Throttling

· Fixed rate limit per key (requests/second)

· Hard daily call cap per key

· Requests over the limit are rejected with a standard error

· No per-plan quotas, no overage billing, no configurable rules

13. Reports & Analytics

· Per-role dashboard: wallet balance, today's call count, success/fail counts

· API-wise usage report (calls, success rate, amount spent)

· Full transaction log, filterable by date

· Excel export

· No provider-wise analytics, no revenue trends, no scheduled reports

14. Risk, Fraud & Compliance

· Audit log of key actions (approvals, price changes, key revocations)

· Complete transaction trail

· Basic velocity check — flags/blocks abnormal call spikes

· KYC gate: merchant must be Approved before any production key works

· No fraud-rules engine, no AML scoring, no PCI-DSS tooling

15. Notifications & Alerts

· Email + SMS triggers: low wallet balance, account approved/rejected, provider-down (admin-flagged)

· Matching in-app alert

· Fixed templates

· No webhook alerts, no quota-breach triggers, no template editor, no preferences

16. Admin Control Panel

· Provider/API configuration (credentials, base price, enable/disable)

· Pricing & markup configuration per reseller tier

· User management (approve, suspend, edit)

· Role configuration

· Master settings

· Audit log

· No feature toggles, no system-health view, no backup UI

17. Support & Ticketing

· Merchant/reseller raises a ticket (subject, category, message)

· Admin sees the queue and replies in a thread

· Status limited to Open/Closed

· No SLA timers, no escalation, no assignment routing, no knowledge base

# 2. Key Decisions Locked

| Decision Area | Locked Choice |
| --- | --- |
| Routing model | Single provider per API — no routing, no failover, no least-cost logic |
| Reseller model | Single-tier resellers under Super Admin — no sub-reseller cascades |
| Billing model | Prepaid wallet only — no postpaid/credit |
| Margins | Report-only — auto-credited, no payouts |
| Documentation | Static docs — no live try-it console |

# 3. User Roles (Phase 1)

| Role | Responsibilities |
| --- | --- |
| Super Admin | Full platform control, provider & pricing config, user approvals, reports, settings |
| Reseller | Onboards own merchants, sets own markup, branded panel, views own reports |
| Developer / Merchant | Consumes APIs via keys, manages wallet, views usage & transactions, raises tickets |

No sub-users or staff accounts in Phase 1.

# 4. Functional Requirements by Module

## 4.1  User & Identity Management

• Three roles only: Super Admin, Reseller, Developer/Merchant.

• Self-registration form: name, business name, mobile, email, PAN, GSTIN.

• New B2B accounts land in Pending; admin reviews uploaded PAN/GST and marks Active or Rejected.

• Login via mobile/email + OTP.

• Profile holds business name, contact, GSTIN, one address.

• Account states limited to: Pending, Active, Rejected.

• Excluded: sub-users, staff accounts, automated KYC validation, 2FA.

## 4.2  API Repository / Catalog Management

• Admin-maintained list of APIs; each has name, category, description, status (Live/Inactive).

• One production endpoint URL per API.

• A linked documentation reference per API (points to 4.10).

• Merchants browse only Live APIs they are entitled to.

• Excluded: versioning, beta/deprecated states, self-service publishing.

## 4.3  Provider / Upstream Aggregation Engine

• Each API mapped to exactly one upstream provider.

• Admin stores provider credentials and base (cost) price per API.

• Manual enable/disable toggle per API-provider mapping.

• Requests pass straight through to the mapped provider.

• Excluded: multi-provider, failover, least-cost routing, health checks, hot-swap.

## 4.4  API Key & Credential Management

• One production key + one sandbox key generated per merchant.

• View, regenerate, and revoke keys from the panel.

• Basic IP whitelist per key (list of allowed IPs).

• Excluded: scopes, scheduled rotation, per-API key permissions.

## 4.5  Subscription, Plans & Pricing

• Admin sets a single per-call price per API.

• One flat markup % per reseller tier, applied over base price.

• One default plan applies to all merchants.

• Excluded: subscription/slab/volume pricing, custom enterprise quotes, bundles.

## 4.6  Wallet, Credits & Billing

• Prepaid wallet per merchant/reseller.

• Each successful API call auto-debits the per-call price.

• Manual top-up via QmaxPay/1Q1Pay; balance updates on confirmation.

• Running ledger of credits and debits.

• Basic invoice generated per top-up.

• Calls blocked when balance is insufficient.

• Excluded: postpaid/credit limits, auto-debit, billing cycles, GST e-invoicing.

## 4.7  Transaction & Routing Engine

• Receives merchant request; validates key + balance + rate limit.

• Forwards to the single mapped provider; receives response.

• Returns a normalized response to the merchant.

• Idempotency key prevents duplicate processing.

• Every request/response logged with timestamp, status, and amount debited.

• Excluded: retries, multi-provider normalization, async queue.

## 4.8  Reseller / White-Label Panel

• Single tier of resellers, each created under Super Admin.

• Reseller onboards its own merchants.

• Reseller sets its own markup over the base/admin price.

• Branded login: reseller logo + name on the panel.

• Excluded: sub-reseller chains, custom domains, multi-level commission cascade.

## 4.9  Settlement & Payout

• On each transaction, the reseller margin (sell − base) is auto-credited to the reseller wallet.

• Margins shown as a settlement report only.

• Excluded: outbound payout run, provider-statement reconciliation, hold/release.

## 4.10  Developer Portal & Documentation

• Static documentation page per API: endpoint, parameters, sample request, sample response.

• Sandbox key available for testing.

• Copy-paste cURL samples.

• Excluded: interactive try-it console, SDKs, auto-generated docs, changelog.

## 4.11  Webhooks & Callbacks

• Merchant configures one callback URL.

• System POSTs transaction status to that URL after completion.

• Delivery attempt is logged.

• Excluded: multi-event subscriptions, retry/backoff, signature-verification UI.

## 4.12  Rate Limiting, Quota & Throttling

• Fixed rate limit per key (requests/second).

• Hard daily call cap per key.

• Requests over the limit rejected with a standard error.

• Excluded: per-plan quotas, overage billing, configurable rules.

## 4.13  Reports & Analytics

• Per-role dashboard: wallet balance, today's call count, success/fail counts.

• API-wise usage report (calls, success rate, amount spent).

• Full transaction log, filterable by date.

• Excel export.

• Excluded: provider-wise analytics, revenue trends, scheduled reports.

## 4.14  Risk, Fraud & Compliance

• Audit log of key actions (approvals, price changes, key revocations).

• Complete transaction trail.

• Basic velocity check — flags/blocks abnormal call spikes.

• KYC gate: merchant must be Approved before any production key works.

• Excluded: fraud-rules engine, AML scoring, PCI-DSS tooling.

## 4.15  Notifications & Alerts

• Email + SMS triggers: low wallet balance, account approved/rejected, provider-down (admin-flagged).

• Matching in-app alert.

• Fixed templates.

• Excluded: webhook alerts, quota-breach triggers, template editor, preferences.

## 4.16  Admin Control Panel

• Provider/API configuration (credentials, base price, enable/disable).

• Pricing & markup configuration per reseller tier.

• User management (approve, suspend, edit).

• Role configuration.

• Master settings.

• Audit log.

• Excluded: feature toggles, system-health view, backup UI.

## 4.17  Support & Ticketing

• Merchant/reseller raises a ticket (subject, category, message).

• Admin sees the queue and replies in a thread.

• Status limited to Open/Closed.

• Excluded: SLA timers, escalation, assignment routing, knowledge base.

# 5. Out of Scope (Phase 2+)

• Mobile apps (reseller + merchant)

• Smart / least-cost routing and multi-provider failover

• Public status page & SLA monitoring

• Third-party API publisher marketplace

• Sub-reseller cascades

• Automated payouts & provider reconciliation

• Postpaid/credit billing and GST e-invoicing

• Interactive API console and SDKs

# 6. Cross-Cutting Simplifications (Scope Guardrails)

• One provider per API (no routing engine).

• Single-tier resellers (no cascades).

• Prepaid-only wallet (no credit).

• Report-only margins (no payouts).

• Static documentation (no live console).

• Fixed notification triggers and templates.

### Appendix 2 Detailed Scope - Fincomax

## Fincomax — Phase 1 Functional Modules

### A · Core Platform & Access

1. USR — User, Role & Access Management

· Four fixed roles: Admin, Ops, Professional, Client

· Self-registration for Professional & Client; Admin/Ops created internally

· Login via email/mobile + OTP

· RBAC — menus and actions gated by role

· Basic profile + session management

· Excluded: sub-roles, team accounts under a professional, 2FA, social login

2. ONB — Onboarding & KYC

· Separate guided flows for Client and Professional

· Document upload (ID/PAN; membership certificate for professionals)

· Ops review queue → Approve / Reject with reason

· Account states: Pending, Active, Rejected

· Excluded: automated/third-party KYC, video KYC, re-KYC cycles

3. WAL — Wallet & Billing Account

· Prepaid wallet per Client; payout balance per Professional

· Manual top-up via 1Q1Pay; balance updates on confirmation

· Running ledger of credits/debits

· Excluded: postpaid/credit limits, auto-debit, multi-currency

### B · Marketplace Front-End & Profiles

4. WEB — Marketplace Front-End / Storefront

· Public landing with category entry points

· Browse open jobs and browse professionals (talent)

· Category / sub-category pages

· Responsive web (desktop + mobile browser)

· Excluded: native mobile app, multi-language, CMS/blog

5. SRCH — Search & Discovery

· Keyword search across jobs and professionals

· Filters: category, skill, rating, budget/rate

· Sort by recent / rating

· Excluded: AI recommendations, saved searches, alerts

6. PRF — Professional Profile & Portfolio

· Profile: name, headline, professional type, skills, bio

· Rate (hourly/fixed), availability flag

· Portfolio samples + on-platform work history

· Credential/membership number captured at onboarding, shown as "verified"

· Excluded: skill tests, video intro, profile analytics

7. CPRF — Client / Business Profile

· Client profile: name, contact, business name

· Entity & registration details: PAN, GSTIN, CIN (for invoicing/compliance)

· Posting and hire history

· Excluded: multiple entities per client, org sub-accounts

### C · Job Marketplace & Engagement

8. JOB — Job Posting Platform

· Post a job: title, scope, category, budget (fixed/hourly), deadline, attachments

· Job states: Draft, Open, In Progress, Delivered, Closed, Cancelled

· Ops can view all postings

· Excluded: job templates, repost automation, featured/promoted listings

9. PROP — Proposals & Bidding

· Professional submits proposal: cover note, quoted price, timeline

· One proposal per professional per job

· Client views all proposals on a job

· Excluded: client invites/headhunting, proposal credits, counter-offer threads

10. HIRE — Hiring & Contracts

· Client shortlists and awards to one professional

· System generates a contract record (scope, price, timeline, parties)

· Both parties accept to activate the engagement

· Excluded: multi-hire per job, e-signature integration, custom contract templates

11. JMG — Job & Engagement Management

· Engagement workspace tied to the awarded job

· Milestones/deliverables with status (pending → submitted → approved)

· Professional submits deliverables; Client approves or requests changes

· Lifecycle transitions drive payment release (links to PAY)

· Excluded: time-tracking/timesheets, sub-tasks, scheduling/Gantt

12. MSG — Messaging & Collaboration

· In-app 1:1 messaging within an engagement

· File/attachment exchange

· Excluded: group chat, calls/video, presence, external email threads

13. RVW — Ratings & Reviews

· Two-way review (Client ↔ Professional) on job closure

· Star rating + comment, aggregated onto profiles

· Excluded: moderation workflow, response-to-review, weighted scoring

### D · Compliance Services

14. CMP — Compliance Catalog & Applicability

· Admin-maintained master (ROC, GST, Income Tax, TDS, PF/ESI, etc.)

· Each item: name, category, frequency, applicable entity type

· Map applicable compliances to a client by entity type

· Excluded: auto-applicability rules engine, statutory law text, region variants

15. CTRK — Compliance Tracking & Calendar

· Per-client list of applicable compliances with due dates

· Status: Upcoming, Due, Filed, Overdue

· Reminders/escalations via NOT

· Excluded: government-portal integration, auto-filing, penalty calculators

16. DOC — Document Collection & Vault

· Checklist-driven document requests per compliance/job

· Secure client upload, stored in per-client vault

· Professional/Ops access for the engagement

· Excluded: OCR/extraction, version history, e-sign, retention policies

### E · Payments, Pricing & Settlement

17. 1QP — 1Q1Pay Integration Layer

· Single shared connector to 1Q1Pay for collections and payouts

· Request/response handling + basic transaction reconciliation

· Excluded: multiple PSPs, failover/routing, direct bank integration

18. PAY — Payments, Escrow & Milestone Release

· Client funds job amount upfront into escrow (escrow ledger)

· Release to professional on milestone/job approval

· UPI/QR collection via 1Q1Pay; receipts

· Excluded: auto refunds beyond manual, chargebacks, card vaulting

19. IDV — PAN & e-KYC / Identity Services

· PAN and basic e-KYC verification calls (via 1Q1Pay) at onboarding

· Verification result flagged on profile

· Excluded: DSC issuance, Aadhaar offline XML, bank-account verification

20. PRC — Pricing, Commission & Fees

· Admin sets platform commission % on job value

· Optional flat service fee on compliance packages

· Commission computed at settlement, shown in reports

· Excluded: tiered/slab commission, coupons, professional subscriptions

21. STL — Settlement, Payout & GST Invoicing

· On completion: deduct commission, credit professional payout balance

· Manual/scheduled payout via 1Q1Pay

· GST-compliant invoice for platform fee/services

· Excluded: automated daily settlement, TDS computation, e-invoicing/IRN

### F · Operations, Admin & Support

22. RPT — Reporting, MIS & Analytics

· Core reports: jobs (posted/active/closed), revenue/commission, payouts, compliance status, professional performance

· Export to CSV/Excel

· Role-based dashboards (Admin/Ops)

· Excluded: custom report builder, scheduled emailed reports, BI drilldowns

23. NOT — Notifications & Communications

· Channels: SMS, email, in-app

· Triggers: onboarding status, proposal/hire, milestone, payment, compliance reminder

· Excluded: WhatsApp/push, template designer, marketing campaigns

24. ADM — Admin Console & Configuration

· Dashboard; manage categories & compliance master data

· User approvals, service/feature toggles

· Dispute oversight and manual overrides

· Excluded: granular multi-admin permissions, audit-config UI, feature-flag framework

25. AUD — Audit, Security & Data Privacy

· Activity/audit logs for key actions (approvals, payments, document access)

· Encryption at rest/in transit; role-based access to sensitive data

· Excluded: SIEM integration, full DLP, configurable retention

26. SUP — Support, Ticketing & Helpdesk

· Ticket creation by Client/Professional; Ops routing & resolution

· States: Open, In Progress, Resolved, Closed

· Links to dispute handling from RVW/JMG

Excluded: live chat/bot, SLA automation, knowledge base

# 4. Functional Requirements by Module (Phase 1)

All requirements below are Phase 1. Module code shown in brackets is used as the ID prefix.

## Group A · Core Platform & Access

User, Role & Access Management  [USR]

Purpose: Single identity and access-control foundation for all roles.

| Req ID | Requirement |
| --- | --- |
| FCX-USR-01 | Four fixed roles: Admin, Ops, Professional, Client. |
| FCX-USR-02 | Self-registration for Professional and Client; Admin/Ops created internally. |
| FCX-USR-03 | Login via email/mobile with OTP. |
| FCX-USR-04 | Role-based access control gating menus and actions. |
| FCX-USR-05 | Basic profile and session management. |

Excluded: sub-roles, team accounts under a professional, 2FA, social login.

Onboarding & KYC  [ONB]

Purpose: Verify and activate clients and professionals before they transact.

| Req ID | Requirement |
| --- | --- |
| FCX-ONB-01 | Separate guided onboarding flows for Client and Professional. |
| FCX-ONB-02 | Document upload (ID/PAN; membership certificate for professionals). |
| FCX-ONB-03 | Ops review queue with Approve / Reject and reason. |
| FCX-ONB-04 | Account states: Pending, Active, Rejected. |

Excluded: automated/third-party KYC, video KYC, re-KYC cycles.

Wallet & Billing Account  [WAL]

Purpose: Hold prepaid client funds and professional payout balances.

| Req ID | Requirement |
| --- | --- |
| FCX-WAL-01 | Prepaid wallet per Client; payout balance per Professional. |
| FCX-WAL-02 | Manual top-up via 1Q1Pay; balance updates on confirmation. |
| FCX-WAL-03 | Running ledger of credits and debits. |

Excluded: postpaid/credit limits, auto-debit, multi-currency.

## Group B · Marketplace Front-End & Profiles

Marketplace Front-End / Storefront  [WEB]

Purpose: Public-facing entry point to browse jobs and talent.

| Req ID | Requirement |
| --- | --- |
| FCX-WEB-01 | Public landing page with category entry points. |
| FCX-WEB-02 | Browse open jobs and browse professionals (talent). |
| FCX-WEB-03 | Category and sub-category pages. |
| FCX-WEB-04 | Responsive web (desktop and mobile browser). |

Excluded: native mobile app, multi-language, CMS/blog.

Search & Discovery  [SRCH]

Purpose: Help clients and professionals find relevant jobs and talent.

| Req ID | Requirement |
| --- | --- |
| FCX-SRCH-01 | Keyword search across jobs and professionals. |
| FCX-SRCH-02 | Filters: category, skill, rating, budget/rate. |
| FCX-SRCH-03 | Sort by recent or rating. |

Excluded: AI recommendations, saved searches, alerts.

Professional Profile & Portfolio  [PRF]

Purpose: Represent a professional's identity, skills and track record.

| Req ID | Requirement |
| --- | --- |
| FCX-PRF-01 | Profile: name, headline, professional type, skills, bio. |
| FCX-PRF-02 | Rate (hourly/fixed) and availability flag. |
| FCX-PRF-03 | Portfolio samples and on-platform work history. |
| FCX-PRF-04 | Credential/membership number captured at onboarding, shown as verified. |

Excluded: skill tests, video intro, profile analytics.

Client / Business Profile  [CPRF]

Purpose: Capture client and legal-entity details for hiring and invoicing.

| Req ID | Requirement |
| --- | --- |
| FCX-CPRF-01 | Client profile: name, contact, business name. |
| FCX-CPRF-02 | Entity and registration details: PAN, GSTIN, CIN. |
| FCX-CPRF-03 | Posting and hire history. |

Excluded: multiple entities per client, organisation sub-accounts.

## Group C · Job Marketplace & Engagement

Job Posting Platform  [JOB]

Purpose: Let clients publish work for professionals to bid on.

| Req ID | Requirement |
| --- | --- |
| FCX-JOB-01 | Post a job: title, scope, category, budget (fixed/hourly), deadline, attachments. |
| FCX-JOB-02 | Job states: Draft, Open, In Progress, Delivered, Closed, Cancelled. |
| FCX-JOB-03 | Ops visibility over all postings. |

Excluded: job templates, repost automation, featured/promoted listings.

Proposals & Bidding  [PROP]

Purpose: Let professionals respond to jobs with a quote and plan.

| Req ID | Requirement |
| --- | --- |
| FCX-PROP-01 | Professional submits a proposal: cover note, quoted price, timeline. |
| FCX-PROP-02 | One proposal per professional per job. |
| FCX-PROP-03 | Client views all proposals on a job. |

Excluded: client invites/headhunting, proposal credits, counter-offer threads.

Hiring & Contracts  [HIRE]

Purpose: Convert an accepted proposal into a binding engagement.

| Req ID | Requirement |
| --- | --- |
| FCX-HIRE-01 | Client shortlists and awards the job to one professional. |
| FCX-HIRE-02 | System generates a contract record (scope, price, timeline, parties). |
| FCX-HIRE-03 | Both parties accept to activate the engagement. |

Excluded: multi-hire per job, e-signature integration, custom contract templates.

Job & Engagement Management  [JMG]

Purpose: Run the active engagement from start to delivery.

| Req ID | Requirement |
| --- | --- |
| FCX-JMG-01 | Engagement workspace tied to the awarded job. |
| FCX-JMG-02 | Milestones/deliverables with status (pending, submitted, approved). |
| FCX-JMG-03 | Professional submits deliverables; Client approves or requests changes. |
| FCX-JMG-04 | Lifecycle transitions trigger payment release (links to PAY). |

Excluded: time-tracking/timesheets, sub-tasks, scheduling/Gantt.

Messaging & Collaboration  [MSG]

Purpose: Enable direct communication within an engagement.

| Req ID | Requirement |
| --- | --- |
| FCX-MSG-01 | In-app 1:1 messaging within an engagement. |
| FCX-MSG-02 | File / attachment exchange. |

Excluded: group chat, calls/video, presence, external email threads.

Ratings & Reviews  [RVW]

Purpose: Build trust through post-engagement feedback.

| Req ID | Requirement |
| --- | --- |
| FCX-RVW-01 | Two-way review (Client and Professional) on job closure. |
| FCX-RVW-02 | Star rating and comment, aggregated onto profiles. |

Excluded: moderation workflow, response-to-review, weighted scoring.

## Group D · Compliance Services

Compliance Catalog & Applicability  [CMP]

Purpose: Maintain the master of compliances and map them to clients.

| Req ID | Requirement |
| --- | --- |
| FCX-CMP-01 | Admin-maintained compliance master (ROC, GST, Income Tax, TDS, PF/ESI, etc.). |
| FCX-CMP-02 | Each item: name, category, frequency, applicable entity type. |
| FCX-CMP-03 | Map applicable compliances to a client by entity type. |

Excluded: auto-applicability rules engine, statutory law text, region variants.

Compliance Tracking & Calendar  [CTRK]

Purpose: Track due dates and filing status per client.

| Req ID | Requirement |
| --- | --- |
| FCX-CTRK-01 | Per-client list of applicable compliances with due dates. |
| FCX-CTRK-02 | Status: Upcoming, Due, Filed, Overdue. |
| FCX-CTRK-03 | Reminders and escalations via NOT. |

Excluded: government-portal integration, auto-filing, penalty calculators.

Document Collection & Vault  [DOC]

Purpose: Collect and securely store client documents.

| Req ID | Requirement |
| --- | --- |
| FCX-DOC-01 | Checklist-driven document requests per compliance/job. |
| FCX-DOC-02 | Secure client upload stored in a per-client vault. |
| FCX-DOC-03 | Professional / Ops access for the engagement. |

Excluded: OCR/extraction, version history, e-sign, retention policies.

## Group E · Payments, Pricing & Settlement

1Q1Pay Integration Layer  [1QP]

Purpose: Single abstraction over 1Q1Pay for all money movement.

| Req ID | Requirement |
| --- | --- |
| FCX-1QP-01 | Single shared connector to 1Q1Pay for collections and payouts. |
| FCX-1QP-02 | Request/response handling with basic transaction reconciliation. |

Excluded: multiple PSPs, failover/routing, direct bank integration.

Payments, Escrow & Milestone Release  [PAY]

Purpose: Secure client funds and release them on approved work.

| Req ID | Requirement |
| --- | --- |
| FCX-PAY-01 | Client funds the job amount upfront into escrow (escrow ledger). |
| FCX-PAY-02 | Release to professional on milestone/job approval. |
| FCX-PAY-03 | UPI/QR collection via 1Q1Pay with receipts. |

Excluded: auto refunds beyond manual, chargebacks, card vaulting.

PAN & e-KYC / Identity Services  [IDV]

Purpose: Verify identity during onboarding.

| Req ID | Requirement |
| --- | --- |
| FCX-IDV-01 | PAN and basic e-KYC verification calls (via 1Q1Pay) at onboarding. |
| FCX-IDV-02 | Verification result flagged on profile. |

Excluded: DSC issuance, Aadhaar offline XML, bank-account verification.

Pricing, Commission & Fees  [PRC]

Purpose: Define how the platform earns on jobs and packages.

| Req ID | Requirement |
| --- | --- |
| FCX-PRC-01 | Admin sets platform commission % on job value. |
| FCX-PRC-02 | Optional flat service fee on compliance packages. |
| FCX-PRC-03 | Commission computed at settlement and shown in reports. |

Excluded: tiered/slab commission, coupons, professional subscriptions.

Settlement, Payout & GST Invoicing  [STL]

Purpose: Close out engagements financially and bill compliantly.

| Req ID | Requirement |
| --- | --- |
| FCX-STL-01 | On completion: deduct commission and credit professional payout balance. |
| FCX-STL-02 | Manual/scheduled payout via 1Q1Pay. |
| FCX-STL-03 | GST-compliant invoice for platform fee/services. |

Excluded: automated daily settlement, TDS computation, e-invoicing/IRN.

## Group F · Operations, Admin & Support

Reporting, MIS & Analytics  [RPT]

Purpose: Give operators visibility into the business.

| Req ID | Requirement |
| --- | --- |
| FCX-RPT-01 | Core reports: jobs, revenue/commission, payouts, compliance status, professional performance. |
| FCX-RPT-02 | Export to CSV/Excel. |
| FCX-RPT-03 | Role-based dashboards (Admin/Ops). |

Excluded: custom report builder, scheduled emailed reports, BI drilldowns.

Notifications & Communications  [NOT]

Purpose: Keep users informed across the lifecycle.

| Req ID | Requirement |
| --- | --- |
| FCX-NOT-01 | Channels: SMS, email, in-app. |
| FCX-NOT-02 | Triggers: onboarding status, proposal/hire, milestone, payment, compliance reminder. |

Excluded: WhatsApp/push, template designer, marketing campaigns.

Admin Console & Configuration  [ADM]

Purpose: Central control panel for operators.

| Req ID | Requirement |
| --- | --- |
| FCX-ADM-01 | Dashboard; manage categories and compliance master data. |
| FCX-ADM-02 | User approvals and service/feature toggles. |
| FCX-ADM-03 | Dispute oversight and manual overrides. |

Excluded: granular multi-admin permissions, audit-config UI, feature-flag framework.

Audit, Security & Data Privacy  [AUD]

Purpose: Protect sensitive financial and KYC data.

| Req ID | Requirement |
| --- | --- |
| FCX-AUD-01 | Activity/audit logs for key actions (approvals, payments, document access). |
| FCX-AUD-02 | Encryption at rest and in transit; role-based access to sensitive data. |

Excluded: SIEM integration, full DLP, configurable retention.

Support, Ticketing & Helpdesk  [SUP]

Purpose: Resolve user issues and disputes.

| Req ID | Requirement |
| --- | --- |
| FCX-SUP-01 | Ticket creation by Client/Professional; Ops routing and resolution. |
| FCX-SUP-02 | States: Open, In Progress, Resolved, Closed. |
| FCX-SUP-03 | Links to dispute handling from RVW/JMG. |

Excluded: live chat/bot, SLA automation, knowledge base.

# 5. Phase 2 Scope — Fincomax Books (Bookkeeping & Accounting) - This is not part of scope of this engagement

Fincomax Books is an in-house double-entry bookkeeping and accounting suite intended to serve both Fincomax marketplace professionals (managing their clients’ books) and external businesses as a standalone product. The modules below are recorded as Phase 2 scope. They are not part of the Phase 1, carry no committed timeline at this stage, and are deliberately omitted from the execution plan in Section 7. Inventory (Group E) and Payroll (Group G) are optional extensions within Phase 2.

Phase 2 module identifiers use the FBK-[Module] prefix to keep them distinct from Phase 1 (FCX-) modules.

## Group A · Setup & Configuration

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-ORG | Organisation / Company Setup | Multi-company books, profile, PAN/GSTIN, fiscal year, base currency. |
| FBK-COA | Chart of Accounts | Account groups, ledgers, Schedule III / standard CoA templates. |
| FBK-OPB | Opening Balances | Ledger opening balances, outstanding AR/AP, opening stock. |
| FBK-TXC | Tax Configuration | GST rates, TDS/TCS sections, HSN/SAC, place of supply. |
| FBK-PRD | Period & Fiscal Year Management | Accounting periods, locking, year setup. |
| FBK-ROL | Book-Level Users, Roles & Permissions | Owner, Accountant, Staff, Viewer. |

## Group B · Core Bookkeeping & Ledger

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-GL | General Ledger | Double-entry posting engine, ledger view, running balances. |
| FBK-JNL | Journals & Vouchers | Payment, receipt, contra, journal, sales, purchase vouchers. |
| FBK-BNK | Bank & Cash Management | Bank/cash accounts, transfers, cash book. |
| FBK-REC | Bank Reconciliation | Statement import, matching, reconciliation status. |
| FBK-ADJ | Adjustments & Closing Entries | Provisions, accruals, year-end adjustments. |

## Group C · Sales & Receivables

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-CUS | Customer Master | Customer ledgers, GSTIN, credit terms, contacts. |
| FBK-EST | Estimates / Quotations | Quotes, conversion to invoice. |
| FBK-INV | Sales Invoicing | GST-compliant & recurring invoices, multi-rate items. |
| FBK-CRN | Credit Notes & Sales Returns | Sales returns and credit notes. |
| FBK-RCT | Receipts & Collections | Allocate against invoices, advance receipts. |
| FBK-ARA | Receivables & Aging | Outstanding, aging buckets, reminders. |

## Group D · Purchases & Payables

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-VEN | Vendor / Supplier Master | Vendor ledgers, GSTIN, terms. |
| FBK-PO | Purchase Orders | POs, conversion to bill. |
| FBK-BIL | Bills / Purchase Invoices | Vendor bills, ITC eligibility, multi-rate. |
| FBK-DBN | Debit Notes & Purchase Returns | Purchase returns and debit notes. |
| FBK-EXP | Expenses & Expense Claims | Direct expenses, staff reimbursements. |
| FBK-PMT | Vendor Payments | Allocate against bills, advances. |
| FBK-APA | Payables & Aging | Outstanding, aging, payment scheduling. |

## Group E · Inventory (optional extension)

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-ITM | Item / Product & Service Master | Goods/services, HSN/SAC, units, rates. |
| FBK-STK | Stock & Inventory Tracking | Stock in/out, multi-warehouse, batch. |
| FBK-STA | Stock Adjustments & Valuation | FIFO / weighted-average valuation. |

## Group F · Tax & Statutory Compliance (India)

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-GST | GST Management | GSTR-1 / 3B / 2B prep, ITC reconciliation, summaries. |
| FBK-EINV | e-Invoicing & e-Way Bill | IRN generation, e-way bills. |
| FBK-TDS | TDS / TCS Management | Deduction, challans, 26Q/27Q prep, certificates. |
| FBK-TXR | Tax Reports & Return Workpapers | GST/TDS reports and reconciliations. |

## Group G · Payroll (optional extension)

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-EMP | Employee Master & Salary Structure | Employee records and salary structure. |
| FBK-PYR | Payroll Processing | Salary runs, attendance/LOP inputs. |
| FBK-STD | Statutory Deductions | PF, ESI, PT, TDS on salary. |
| FBK-PSL | Payslips & Statutory Outputs | Payslips, PF/ESI/PT outputs. |

## Group H · Fixed Assets

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-FAR | Fixed Asset Register | Asset master, capitalisation. |
| FBK-DEP | Depreciation | Companies Act / Income Tax schedules, posting. |

## Group I · Reports & Financial Statements

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-FIN | Financial Statements | Trial Balance, P&L, Balance Sheet, Cash Flow. |
| FBK-RPT | Operational & MIS Reports | Ledgers, day book, aging, tax, ratios, exports. |

## Group J · Documents, Audit & Period Close

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-DMS | Document Management | Attach source docs to transactions, per-book vault. |
| FBK-ATR | Audit Trail & Activity Log | Edit history (Indian audit-trail requirement). |
| FBK-CLS | Period & Year-End Close | Locking, closing, carry-forward. |

## Group K · Collaboration & Practice Management

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-PRAC | Practice / Accountant Console | One professional managing many client books, switch & tasks. |
| FBK-CLP | Client Portal | Clients view statements/invoices, upload docs, approve. |
| FBK-COL | Collaboration & Queries | Comments, queries, to-dos between accountant & client. |
| FBK-NOT | Notifications & Reminders | Invoice due, GST/TDS due, approvals. |

## Group L · Platform, Integration & Subscription

| Module ID | Module | Description |
| --- | --- | --- |
| FBK-INT | Fincomax Integration | Link a book to a Fincomax client/entity; push to compliance (CTRK) & document vault (DOC); originate bookkeeping jobs. |
| FBK-1QP | 1Q1Pay Payments Integration | Collect on invoices (UPI/QR/links), pay bills/payouts. |
| FBK-BFI | Bank & Payment Feeds | Bank feeds, gateway integration. |
| FBK-IMP | Import / Export & Migration | Excel/CSV import, Tally migration, data export. |
| FBK-API | API & Integrations | REST API, webhooks, connectors. |
| FBK-SUB | Subscription & Licensing (external users) | Plans, billing, usage limits, license management. |
| FBK-ADM | System Admin & Settings | Org settings, backups, retention, security. |

Phase 2 total: 53 modules across 12 groups — no timeline committed.

### Appendix 3 Detailed Scope - 1Q1Pay

## 1.3  Scope (Phase 1)

## A · Core Platform & Access

USR · User, Role & Access Management — identity and permission backbone for every actor.

- Role model: Super Admin, Platform Ops, Retailer, Customer, Service Provider, each with a distinct permission set

- Registration & login via mobile/email + OTP; password/PIN credentials

- RBAC enforced at module and action level (a Retailer can transact but not configure pricing)

- Per-role profile management (business details for retailers/providers, basic for customers)

- Session handling across devices with timeout and forced-logout

- Self-service password/PIN reset & recovery

KYC · Onboarding & KYC — verify and activate every retailer, provider, and regulated-txn customer.

- Retailer onboarding: application → document upload → verification → activation

- Customer KYC captured only where a regulated service (AEPS/DMT) requires it

- Provider credential verification — professional membership/registration numbers + certificates

- Document upload with format/expiry validation (PAN, Aadhaar, shop & bank proof)

- KYC status tracking with re-KYC triggers on expiry or data change

- Central admin review/approval queue with accept/reject + reason

RET · Retailer Management — manage the retailer base directly under the platform (single-tier).

- Searchable retailer directory with KYC status

- Lifecycle controls: activate / suspend / deactivate

- Wallet linkage and per-retailer transaction limits

- Commission-plan assignment

- Basic performance dashboard (volume, earnings)

WAL · Wallet & Balance Management — prepaid balance engine funding all retailer fintech transactions.

- One prepaid wallet per retailer

- Top-up via admin credit, payment gateway, or bank transfer (with approval)

- Double-entry ledger with running balance and full trail

- Hold/release for in-flight transactions (funds locked until confirmation/refund)

- Low-balance alerts and thresholds

- Statement with export

## B · Fintech & Payment Services (orchestrated over QmaxPay)

QMX · QmaxPay Integration Layer — the single rail every fintech module uses to reach providers.

- QmaxPay API authentication & key/credential management

- Unified request/response handler shared by all Group B modules

- Timeout, retry and failure handling with consistent error semantics

- Transaction ID mapping (1Q1Pay ↔ QmaxPay) for end-to-end traceability

- Response normalization into common status codes

- Reconciliation feed against QmaxPay as the single counterparty

- Dependency: every fintech service's availability is bounded by this layer

AEP · AEPS & Micro ATM — Aadhaar-authenticated cash services at the retailer counter.

- AEPS authentication via Aadhaar + biometric capture

- Cash withdrawal, balance enquiry, mini statement

- Receipt and status display

- Daily limit enforcement

- Dependency: biometric device certification

DMT · Domestic Money Transfer — send money to any bank account from the counter.

- Beneficiary registration with penny-drop validation

- IMPS/NEFT transfer execution

- Real-time status tracking

- Refund/failure handling with wallet reversal

- Sender KYC and limit checks

- Receipt generation

BBP · BBPS & Bill Payments — pay utility and recurring bills across BBPS billers.

- Biller category and biller fetch

- Bill fetch and amount validation

- Bill payment execution

- Status and receipt

- BBPS complaint/dispute raising

RCH · Recharge — prepaid recharges across telecom and allied services.

- Operator and circle auto-detection

- Mobile and DTH recharge

- FASTag recharge

- Plan browsing

- Status and receipt

UPI · UPI & QR Acceptance — let retailers collect digital payments into their wallet.

- Static and dynamic QR generation

- UPI collect requests

- Payment status callback handling

- Settlement of collected funds to the retailer wallet

- Transaction history

IDV · Identity & Utility Services — verification utilities supporting onboarding and regulated txns.

- e-KYC / Aadhaar verification

- PAN verification

- Verification result logging for audit

- DSC issuance request → Phase 2

TRV · Travel Services (Phase 2) — flight/bus/train/hotel search, booking & ticketing, cancellation/refund, booking history.

PAN · PAN Card Services (Phase 2) — new PAN application, correction/reprint, status tracking.

INS · Insurance Services (Phase 2) — motor/health/life product catalog, quote & purchase, policy retrieval.

LON · Loan & Credit Services (Phase 2) — product listing & eligibility, lead capture, application status.

## D · Commercial, Settlement & Operations

PRC · Pricing, Commission & Margin Engine — define what things cost and who earns what.

- Fintech retail pricing as a markup over QmaxPay wholesale cost

- Retailer commission plans per service

- Marketplace commission % configuration

- Slab/tier and effective-dated pricing → Phase 2

STL · Settlement & Payout — move money out to retailers and providers.

- Retailer commission accrual and disbursement

- Provider payout processing

- Settlement reports and cycles

- Failed-payout handling and retry

RPT · Reporting, MIS & Analytics — visibility across both engines.

- Transaction reports by service, retailer, date

- Revenue and commission reports

- Marketplace engagement reports

- Export to PDF/Excel

- Performance MIS → Phase 2

NOT · Notifications & Communications — keep all actors informed.

- SMS (transaction, OTP, status)

- Email

- In-app notifications

- Template management → Phase 2

## E · Administration, Compliance & Support

ADM · Admin Console & Platform Configuration — the control room for operators.

- Central admin dashboard

- Service enable/disable toggles

- Master data and configuration management

- User/role administration

CMP · Compliance, Audit & Security — keep the platform within regulatory and security bounds.

- Transaction limits and velocity checks

- AML/KYC enforcement

- Audit logs of critical actions

- Data security and encryption

- Regulatory reporting hooks → Phase 2

SUP · Support, Ticketing & Helpdesk — resolve user issues.

- Ticket creation and tracking

- Category/priority routing

- SLA & escalation, knowledge base → Phase 2

distributor tier, and advanced operations features are deferred to Phase 2

1.4  Definitions & Abbreviations

| Term | Meaning |
| --- | --- |
| AEPS | Aadhaar Enabled Payment System |
| DMT | Domestic Money Transfer |
| BBPS | Bharat Bill Payment System |
| IMPS / NEFT | Immediate Payment Service / National Electronic Funds Transfer |
| UPI | Unified Payments Interface |
| e-KYC / KYC | Electronic / Know Your Customer verification |
| DSC | Digital Signature Certificate |
| AML | Anti-Money Laundering |
| RBAC | Role-Based Access Control |
| MIS | Management Information System |

# 2.  Architectural Decisions

The following decisions are locked for Phase 1 and govern the requirements in this document.

| Decision Area | Resolution |
| --- | --- |
| Fintech provider connectivity | Consume QmaxPay APIs — fintech modules are an orchestration / UX / margin layer; no direct provider integration in Phase 1. |
| Channel model | Single-tier: Retailer → Customer. Distributor tier and multi-level overrides deferred to Phase 2. |
| Wallet model | Prepaid. Fintech is retailer-funded — retailer wallet, walk-in customers. Customer wallet deferred to Phase 2. |
| Requirement ID convention | 1QP-[Module]-[Number]. |
| Dependency constraint | 1Q1Pay fintech availability is bounded by QmaxPay; reconciliation is against a single counterparty. |

# 3.  User Roles

| Role | Description |
| --- | --- |
| Super Admin | Full platform control (Omara Digitech) — configuration, oversight, master data. |
| Platform Ops | Day-to-day operations — KYC approvals and support. |
| Retailer | Outlet operator; offers fintech services to walk-in customers via a prepaid wallet. |
| Customer | End user; consumes fintech services through a retailer. |

### Appendix 4 Detailed Scope - Emart

## Softwares - 1 Admin (Web App).

## 1. User & Identity Management

- Five roles, each with a fixed admin-defined permission set

- Customers self-register and are active immediately

- B2B accounts (Distributor/Wholesaler/Retailer) self-register → land in "Pending Approval"

- Admin manually reviews uploaded PAN/GST docs → marks Approved or Rejected

- Login via mobile/email + OTP

- Profile holds business name, contact, GSTIN, one or more addresses

- Account states limited to: Pending, Active, Rejected

- No sub-users, no automated document validation

## 2. Multi-Tier Hierarchy & Sourcing

- Admin manually links each tier to its parent (R1 → W1 → D1)

- Each product (or region group) carries one setting: Strict or Flexible

- Strict = buy only from mapped parent; Flexible = buy from any eligible upstream

- This single toggle is what makes the platform "hybrid"

- No priority ordering, no auto-fallback if mapped seller is out of stock

- Mapping and toggle both managed from simple admin screens

## 3. Product Catalog

- Two-level category tree

- Each product: name, description, basic variant(s), SKU, HSN, price link, images

- Created via form or imported through a fixed-format Excel template

- Tier-submitted products stay inactive until admin approves; admin can create directly

- Product status: Active or Inactive only (Inactive = hidden from store/ordering)

- No per-tier visibility filtering beyond the sourcing toggle

## 4. Pricing & Margin

- One price per tier: Distributor, Wholesaler, Retailer, Customer (MRP/selling)

- Basic quantity slab supported (e.g. 10+ units = lower price)

- Optional region flag for a manual alternate price set

- No future-dated pricing, no approval step — edits take effect immediately

- Margin is implicit in the gap between tier prices

## 5. Inventory & Warehouse

- Single quantity figure held per tier/location

- Two manual actions: inward (add received stock) and outward (deduct on dispatch)

- Stock reserved on order placement; released on cancellation

- Low-stock alert (in-app + email) at an admin-set per-product threshold

- No inter-warehouse transfers, batch/expiry, or formal reconciliation

- Corrections via direct stock adjustment entry

## 6. Storefront / Customer

- Keyword search, category browse, basic filters (category, price, brand)

- Product detail page: variants, price, images, add-to-cart

- Cart with quantity change and removal

- Checkout for registered users only (address + coupon + payment + confirm)

- Order history with one-click reorder

- No wishlist, reviews, or guest checkout

## 7. Order Management

- Orders from customers (B2C) or B2B tiers buying upstream

- Auto-routed to correct seller per tier mapping + Strict/Flexible toggle

- Stock and (for B2B) credit checked; seller confirms or rejects

- Fixed status lifecycle: Placed → Confirmed → Shipped → Delivered (manual transitions)

- GST-compliant invoice generated on confirmation

- Cancellation allowed before shipping → releases reserved stock

- No partial shipments or returns flow

## 8. Procurement / Purchase

- B2B buy-up as a purchase order (Retailer → Wholesaler, Wholesaler → Distributor)

- Upstream seller sees the PO and fulfills manually

- PO records intent and gets marked fulfilled

- No auto-reorder, goods-receipt note, or purchase returns

## 9. Payment & Wallet

- Two checkout methods: single online gateway (QmaxPay/1Q1Pay) + COD

- Each B2B tier has a credit ledger with a static admin-set credit limit

- B2B orders draw against available credit; blocked if limit exceeded

- Refunds processed manually by admin, recorded as ledger entry

- No automated settlement cycle, aging engine, or second gateway

## 10. Logistics & Delivery

- Pin-code serviceability check at checkout

- Flat or zone-based delivery charge (pre-configured by admin)

- Manual status update as shipped/delivered

- Self-pickup option

- No courier API, live tracking, or delivery-proof capture

## 11. Commission, Incentives & Settlement

- Simple per-tier commission (flat or percentage, admin-defined)

- Surfaced as a report of earnings per period

- Informational only — nothing auto-paid, no settlement statement

## 12. Promotions & Marketing

- Coupon codes (flat or %, with validity window, applied at checkout)

- Homepage banner upload/swap by admin

- No scheme builder, campaigns, or outbound marketing

## 13. Reports & Analytics

- Role-scoped dashboard (orders, sales, outstanding totals)

- Four core reports: sales by tier/product, inventory, GST summary, commission

- Date-filterable, Excel export

- No trend charts, slow-mover analysis, or scheduled delivery

## 14. Tax & Compliance

- Admin configures GST rates

- Auto CGST/SGST (intra-state) vs IGST (inter-state) based on buyer/seller state

- HSN code per product; GST-compliant invoice on confirmed orders

- No e-invoice/e-way bill or TCS/TDS handling

## 15. Notifications

- Fixed triggers: order placed, confirmed, shipped, and B2B account approved/rejected

- Channels: email + SMS + in-app alert

- Fixed templates, no WhatsApp/push, no user preferences

## 16. Admin Control Panel

- Master settings (GST rates, delivery zones, thresholds)

- Role/permission configuration

- Full user management (approve, suspend, edit)

- CMS for static policy pages (Terms, Privacy, About, FAQ)

- Basic audit log of key actions

- No feature toggles, system-health view, or backup UI

## 17. Support & Ticketing

- Raise ticket with subject, category, message

- Admin sees queue, replies in thread, marks Open/Closed

- No SLA, escalation, assignment routing, or knowledge base

# 3. Assumptions & Constraints

• Web-based responsive platform (desktop + mobile browser); no native apps in Phase 1.

• Single payment gateway (QmaxPay / 1Q1Pay) plus Cash on Delivery.

• Indian tax regime — GST (CGST / SGST / IGST).

• B2B onboarding involves manual admin verification of documents.

• Sourcing logic is a per-product/region toggle, not a rules-priority engine.

• Notifications limited to email, SMS, and in-app.

# 4. Functional Requirements

Requirement IDs follow the pattern EM-[Module]-[Number].

## 4.1 User & Identity Management (EM-UM)

• EM-UM-01 — System shall support five roles: Super Admin, Distributor, Wholesaler/Master, Retailer, Customer.

• EM-UM-02 — Customers self-register and are activated immediately.

• EM-UM-03 — B2B accounts self-register into a Pending Approval state.

• EM-UM-04 — Admin shall manually review uploaded PAN/GST documents and Approve or Reject.

• EM-UM-05 — Login via mobile/email with OTP.

• EM-UM-06 — Profile stores business name, contact, GSTIN, and one or more addresses.

• EM-UM-07 — Account states limited to Pending, Active, Rejected.

• Excluded (Phase 2+): sub-users, 2FA, automated KYC validation.

## 4.2 Multi-Tier Hierarchy & Sourcing (EM-HS)

• EM-HS-01 — Admin shall manually map each tier to its parent.

• EM-HS-02 — Each product or region group carries a single sourcing setting: Strict or Flexible.

• EM-HS-03 — Strict restricts purchasing to the mapped parent; Flexible permits any eligible upstream.

• EM-HS-04 — No auto-fallback on stock-out; unavailable items simply show no availability.

• Excluded (Phase 2+): rules-priority engine, tree visualization, bulk re-mapping.

## 4.3 Product Catalog (EM-PC)

• EM-PC-01 — Two-level category tree.

• EM-PC-02 — Product attributes: name, description, basic variant(s), SKU, HSN, price link, images.

• EM-PC-03 — Product creation via form or fixed-format Excel import.

• EM-PC-04 — Tier-submitted products remain inactive pending admin approval; admin may create directly.

• EM-PC-05 — Product status: Active or Inactive (Inactive hidden from store/ordering).

• Excluded (Phase 2+): per-tier visibility rules, advanced attributes, draft workflows.

## 4.4 Pricing & Margin (EM-PR)

• EM-PR-01 — One price per tier (Distributor, Wholesaler, Retailer, Customer/MRP).

• EM-PR-02 — Basic quantity slab supported.

• EM-PR-03 — Optional region flag for a manual alternate price set.

• EM-PR-04 — Price edits take effect immediately (no approval/scheduling).

• Excluded (Phase 2+): future-dated pricing, margin-rule automation, change history.

## 4.5 Inventory & Warehouse (EM-IN)

• EM-IN-01 — Single stock quantity per tier/location.

• EM-IN-02 — Manual inward and outward stock actions.

• EM-IN-03 — Stock reserved on order; released on cancellation.

• EM-IN-04 — Low-stock alert (in-app + email) at admin-set threshold.

• EM-IN-05 — Corrections via direct stock adjustment entry.

• Excluded (Phase 2+): multi-warehouse transfer, batch/expiry, serial tracking, reconciliation logs.

## 4.6 Storefront / Customer (EM-SF)

• EM-SF-01 — Keyword search, category browse, basic filters (category, price, brand).

• EM-SF-02 — Product detail page with variants, price, images, add-to-cart.

• EM-SF-03 — Cart with quantity change and removal.

• EM-SF-04 — Checkout for registered users (address + coupon + payment + confirm).

• EM-SF-05 — Order history with one-click reorder.

• Excluded (Phase 2+): wishlist, reviews, guest checkout.

## 4.7 Order Management (EM-OM)

• EM-OM-01 — Orders from customers (B2C) and B2B tiers buying upstream.

• EM-OM-02 — Auto-routing to correct seller per tier mapping + sourcing toggle.

• EM-OM-03 — Stock and B2B credit checked before confirmation.

• EM-OM-04 — Seller confirms or rejects order.

• EM-OM-05 — Status lifecycle: Placed → Confirmed → Shipped → Delivered (manual transitions).

• EM-OM-06 — GST-compliant invoice generated on confirmation.

• EM-OM-07 — Cancellation allowed before shipping; releases reserved stock.

• Excluded (Phase 2+): partial/split fulfillment, returns/replacement.

## 4.8 Procurement / Purchase (EM-PO)

• EM-PO-01 — B2B purchase order from a tier to its upstream parent.

• EM-PO-02 — Upstream seller views PO and fulfills manually.

• EM-PO-03 — PO marked fulfilled on completion.

• Excluded (Phase 2+): auto-reorder, goods-receipt note, purchase returns.

## 4.9 Payment & Wallet (EM-PM)

• EM-PM-01 — Online gateway (QmaxPay / 1Q1Pay) and COD at checkout.

• EM-PM-02 — Credit ledger per B2B tier with static admin-set credit limit.

• EM-PM-03 — B2B orders draw on available credit; blocked when limit exceeded.

• EM-PM-04 — Refunds processed manually and recorded as ledger entries.

• Excluded (Phase 2+): automated settlement, aging engine, multi-gateway.

## 4.10 Logistics & Delivery (EM-LD)

• EM-LD-01 — Pin-code serviceability check at checkout.

• EM-LD-02 — Flat or zone-based delivery charge (admin pre-configured).

• EM-LD-03 — Manual shipped/delivered status update.

• EM-LD-04 — Self-pickup option.

• Excluded (Phase 2+): courier API, live tracking, delivery-proof capture.

## 4.11 Commission, Incentives & Settlement (EM-CM)

• EM-CM-01 — Per-tier commission (flat or percentage, admin-defined).

• EM-CM-02 — Earnings surfaced as a period report.

• EM-CM-03 — Informational only; no auto-payout or settlement statement.

• Excluded (Phase 2+): target incentives, payout generation, hold/release.

## 4.12 Promotions & Marketing (EM-PT)

• EM-PT-01 — Coupon codes (flat or %, validity window, applied at checkout).

• EM-PT-02 — Homepage banner upload/swap.

• Excluded (Phase 2+): scheme builder, campaigns, outbound marketing.

## 4.13 Reports & Analytics (EM-RP)

• EM-RP-01 — Role-scoped dashboard (orders, sales, outstanding totals).

• EM-RP-02 — Core reports: sales by tier/product, inventory, GST summary, commission.

• EM-RP-03 — Date-filterable with Excel export.

• Excluded (Phase 2+): trend analytics, slow-mover detection, scheduled reports.

## 4.14 Tax & Compliance (EM-TX)

• EM-TX-01 — Admin configures GST rates.

• EM-TX-02 — Auto CGST/SGST (intra-state) vs IGST (inter-state) by buyer/seller state.

• EM-TX-03 — HSN per product; GST-compliant invoice on confirmed orders.

• Excluded (Phase 2+): e-invoice/e-way bill, TCS/TDS.

## 4.15 Notifications (EM-NT)

• EM-NT-01 — Triggers: order placed, confirmed, shipped, B2B account approved/rejected.

• EM-NT-02 — Channels: email, SMS, in-app.

• Excluded (Phase 2+): WhatsApp/push, template editor, user preferences.

## 4.16 Admin Control Panel (EM-AD)

• EM-AD-01 — Master settings (GST rates, delivery zones, thresholds).

• EM-AD-02 — Role/permission configuration.

• EM-AD-03 — User management (approve, suspend, edit).

• EM-AD-04 — CMS for static policy pages (Terms, Privacy, About, FAQ).

• EM-AD-05 — Basic audit log of key actions.

• Excluded (Phase 2+): feature toggles, system-health view, backup UI.

## 4.17 Support & Ticketing (EM-ST)

• EM-ST-01 — Raise ticket (subject, category, message).

• EM-ST-02 — Admin views queue, replies in thread, marks Open/Closed.

• Excluded (Phase 2+): SLA, escalation, assignment routing, knowledge base.

# 5. Non-Functional Requirements

• NFR-01 Platform: Responsive web (desktop + mobile browser).

• NFR-02 Security: OTP authentication, RBAC, encrypted credentials, secure payment handling.

• NFR-03 Performance: Catalog/listing pages load within acceptable web norms under expected Phase 1 load.

• NFR-04 Availability: Single-region hosting; routine backups.

• NFR-05 Compliance: GST-compliant invoicing; PCI handled via the payment gateway.

• NFR-06 Auditability: Key admin actions logged.

• NFR-07 Usability: Role-appropriate dashboards; consistent UI.

# 6. Acceptance Criteria (Phase 1 Sign-off Gate)

Phase 1 is accepted when a single end-to-end flow is demonstrable:

1. A Distributor is onboarded and approved, and lists a product with tier pricing and stock.

2. A Retailer (mapped, under a sourcing toggle) raises an order/PO and it routes to the correct upstream seller.

3. A Customer places and pays for an order; a GST-compliant invoice is generated with correct tax breakup.

4. Stock decrements, the credit ledger updates, and order status moves through the full lifecycle to Delivered.

5. Notifications fire on the defined triggers, and the admin can view orders, sales, inventory, and commission reports.

# 7. Build Sprint Sequencing

The Phase 1 is sequenced into eight sprints ordered by dependency — each builds on what the previous delivered, ending in a sign-off demo. Sprint length is a delivery decision (typically 2 weeks each).

| Sprint | Focus | Modules / Requirement Sets |
| --- | --- | --- |
| Sprint 0 | Foundation | Project setup, architecture, DB schema, hosting, auth scaffolding |
| Sprint 1 | Identity & Hierarchy | EM-UM, EM-HS, EM-AD (core admin: users, roles, settings) |
| Sprint 2 | Catalog, Pricing & Stock | EM-PC, EM-PR, EM-IN |
| Sprint 3 | Storefront & Orders | EM-SF, EM-OM |
| Sprint 4 | B2B Flow & Money | EM-PO, EM-PM, EM-TX |
| Sprint 5 | Fulfillment & Comms | EM-LD, EM-NT |
| Sprint 6 | Revenue & Reporting | EM-CM, EM-PT, EM-RP |
| Sprint 7 | Support & Hardening | EM-ST, UAT, bug-fix, acceptance demo & sign-off |

Dependency logic: identity and hierarchy must exist before catalog/pricing can be tier-scoped; catalog and stock must exist before orders; orders must exist before B2B procurement, payment, and tax; fulfillment and notifications layer onto confirmed orders; commission, promotions, and reporting consume completed transaction data; support and hardening close the Phase 1.

### Appendix 5 Detailed Scope - SaaS for Enterprises

# 1. Introduction

## 1.1 Purpose

This Software Requirements Specification (SRS) defines the functional and non-functional requirements for Phase 1 of the Omara Digitech SaaS ERP Platform. It serves as the agreed baseline for design, development, and stakeholder sign-off.

## 1.2 Scope

Phase 1 delivers a multi-tenant, web-based ERP offered as Software-as-a-Service. It comprises a SaaS Foundation Layer plus seven core business modules: LMS, CRM, HRMS, Inventory Management, Finance Management, Task Management, and Team Management. Each requirement is tagged MVP (first release) or Phase 2 (deferred). A broader Phase 2 module roadmap is summarized in Section 12.

## Phase 1 Module Details

1. LMS (Learning Management)

- Course builder: courses → modules → lessons (video, document, quiz content)

- Content library & uploads

- Enrollment: assign to employees/teams, self-enroll, mandatory training flags

- Progress tracking & completion status

- Assessments/quizzes with scoring

- Certificates on completion

- Reports: completion rates, scores by employee/team

2. CRM

- Contact & account management (individuals + companies)

- Lead capture: web forms, manual entry, bulk import

- Pipeline with custom stages; deals/opportunities

- Activities: calls, meetings, emails, tasks linked to contacts

- Follow-up reminders & interaction history

- Tags/segmentation

- Reports: pipeline value, conversion rate, activity log

3. HRMS

- Employee master (personal, job, documents)

- Attendance: check-in/out, regularization

- Leave management: types, requests, approvals, balances

- Payroll basics: salary structure, payslip generation, deductions (TDS/PF deferred to Phase 2)

- Onboarding / offboarding workflows

- Org structure & reporting lines

- Document store (offer letters, IDs)

- Employee self-service portal

4. Inventory Management

- Item/product master (SKU, category, unit, pricing)

- Stock levels (multi-location ready)

- Stock-in (receipts) / stock-out (issues) / adjustments

- Low-stock & reorder alerts

- Stock valuation

- Reports: stock summary, movement, valuation

- Batch/expiry tracking deferred to Phase 2

5. Finance Management

- GST-compliant sales invoicing

- Expense & bill tracking

- Chart of accounts / ledgers

- Receipts & payments, bank/cash accounts

- GST handling: tax rates, GSTIN, GST reports

- Financial reports: P&L, receivables/payables, outstanding

- Hooks: invoice-from-deal (CRM), COGS (Inventory)

6. Task Management

- Task creation: title, description, assignee, due date, priority

- Status workflow (custom) + Kanban/list views

- Subtasks & checklists

- Comments & attachments

- Linking to CRM deals, HR, projects, teams

- Reminders & overdue alerts

- Reports: workload, overdue, completion

7. Team Management

- Team creation & membership

- Hierarchy / reporting structure

- Role assignment within teams

- Member capacity & availability

- Team dashboards

Design note: Team Management overlaps heavily with HRMS org structure and the Foundation Layer's RBAC. My recommendation is to build it as a thin layer over those two rather than a standalone module with its own data — avoids duplicate org/role logic. Flag if you'd prefer it fully standalone.

Phase 2

### Phase 2 — Modules for the next phase from the detailed list

Operations & Supply Chain

- Purchase, Inventory (deepen), Warehouse, Logistics, Supply Chain, Procurement, Material Requirement Planning, Quality Control

Manufacturing / Production

- Production, New Product Development, Job Work (Outsource), Job Work (Insource), Maintenance, AMC

Sales & Distribution

- Sales Management, Sales Distribution, POS, E-commerce/Aggregator, Import-Export, Bid Management (Domestic & Intl)

Finance & Compliance

- Accounts, Finance (deepen), Legal & Compliances, Scheme/Cashback/Reward/Gift, Referral/Commission, Cash Management & Settlement (CMSS)

Customer & Support

- CRM (deepen), Complaint & Grievance, IVR/Call Center, SOS Services

Marketing & Content

- Digital Marketing, Social Media Management (Social ERP), Content Management (CMS)

Tracking & Security

- Barcode Management, Geo-Location & Tracking, OTP/MPIN Security

Management & Admin

- Asset/Admin-IT (deepen), Project Management, Operations, Data Management (DRAM), Task Management (deepen), LMS (deepen)

## 1.3 Definitions, Acronyms & Abbreviations

| Term | Meaning |
| --- | --- |
| SaaS | Software-as-a-Service. |
| Tenant | An isolated customer workspace within the multi-tenant platform. |
| MVP | Minimum Viable Product — the first release scope. |
| RBAC | Role-Based Access Control. |
| LMS | Learning Management System (see Assumption A-01). |
| CRM | Customer Relationship Management. |
| HRMS | Human Resource Management System. |
| GST | Goods and Services Tax (India). |
| MPIN | Mobile Personal Identification Number. |

## 1.4 References

• Omara Digitech product ecosystem materials (1Q1Pay, QmaxPay, Fincomax).

• SAAS ERP modular feature list (source for Phase 2 roadmap).

## 1.5 Overview

Section 2 describes the overall product context, users, constraints and assumptions. Sections 3–11 specify requirements for the Foundation Layer and each module. Section 12 lists deferred Phase 2 scope. Section 13 captures sign-off.

# 2. Overall Description

## 2.1 Product Perspective

The platform is a new, self-contained multi-tenant SaaS ERP. Businesses subscribe to a plan, provision their own workspace, and operate the modules independently with isolated data. It integrates with Omara's payment infrastructure for subscription billing.

## 2.2 Product Functions (Summary)

• Tenant onboarding, subscription and billing.

• Role-based access and platform administration.

• Learning, customer, HR, inventory, finance, task and team operations.

## 2.3 User Classes and Characteristics

| Role | Description |
| --- | --- |
| Platform Super-Admin | Omara Digitech operations team. Manages tenants, subscription plans, platform configuration and monitoring. |
| Tenant Owner | Primary subscriber. Full access within the tenant including billing and subscription. |
| Tenant Admin | Configures modules, manages users and roles within the tenant. |
| Manager | Department/team-level access; approves leave, tasks and reviews reports. |
| Staff / Employee | Operational module use and employee self-service. |

## 2.4 Operating Environment

• Cloud-hosted, multi-tenant web application.

• Accessed via modern desktop and mobile browsers (responsive).

## 2.5 Design and Implementation Constraints

• Web-only responsive platform for MVP (no native mobile apps).

• Indian GST compliance for Finance; English UI at MVP.

• Single integrated payment gateway for subscription billing.

## 2.6 Assumptions and Dependencies

Items marked “Requires sign-off” must be confirmed before design proceeds.

| Ref | Assumption / Dependency | Status |
| --- | --- | --- |
| A-01 | “LMS” is interpreted as Learning Management System (employee training). CRM owns lead/pipeline functions. | Requires sign-off |
| A-02 | Deployment model is multi-tenant SaaS — businesses subscribe to manage their own operations. | Requires sign-off |
| A-03 | MVP is a web-only responsive platform; native mobile apps are out of scope. | Assumption |
| A-04 | Subscription billing uses a single integrated payment gateway (QmaxPay / 1Q1Pay). | Assumption |
| A-05 | Compliance scope is Indian GST; English is the MVP UI language. | Assumption |
| A-06 | Team Management is implemented as a thin layer over HRMS org structure and platform RBAC, not a standalone data model. | Assumption |
| D-01 | Availability of QmaxPay / 1Q1Pay payment APIs, plus SMS and email gateways. | Dependency |

# 3. SaaS Foundation Layer Requirements

Cross-cutting platform capabilities required by all modules. These form mandatory groundwork for the MVP.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-FND-001 | Tenant self-service signup and automated workspace provisioning. | MVP |
| ERP-FND-002 | Tenant profile and workspace settings (name, logo, locale, timezone, currency). | MVP |
| ERP-FND-003 | Per-tenant data isolation enforced across all modules. | MVP |
| ERP-FND-004 | Tenant lifecycle management: suspend, reactivate, soft-delete. | MVP |
| ERP-FND-005 | Subscription plans/tiers with module- and feature-level gating per plan. | MVP |
| ERP-FND-006 | Free-trial provisioning with automatic expiry handling. | MVP |
| ERP-FND-007 | Online subscription payment collection via integrated gateway (QmaxPay / 1Q1Pay). | MVP |
| ERP-FND-008 | Subscription invoices and payment history. | MVP |
| ERP-FND-009 | Billing cycle changes, plan upgrades/downgrades with proration. | Phase 2 |
| ERP-FND-010 | Failed-payment dunning and grace-period handling. | Phase 2 |
| ERP-FND-011 | User invitation, activation and deactivation within a tenant. | MVP |
| ERP-FND-012 | Role-based access control (RBAC) with module-level permissions. | MVP |
| ERP-FND-013 | Predefined roles: Owner, Admin, Manager, Staff. | MVP |
| ERP-FND-014 | Custom role creation with granular permissions. | Phase 2 |
| ERP-FND-015 | Authentication via email/password. | MVP |
| ERP-FND-016 | OTP verification (email / SMS). | MVP |
| ERP-FND-017 | MPIN for quick and secure access. | MVP |
| ERP-FND-018 | Two-factor authentication (2FA). | Phase 2 |
| ERP-FND-019 | Session management with configurable timeout. | MVP |
| ERP-FND-020 | Password policy enforcement and reset flow. | MVP |
| ERP-FND-021 | Audit logging of key user and data actions. | MVP |
| ERP-FND-022 | Platform super-admin console: tenant oversight, plan management, usage monitoring. | MVP |
| ERP-FND-023 | Consent-based support impersonation with audit trail. | Phase 2 |
| ERP-FND-024 | Notifications engine: email, SMS, in-app. | MVP |
| ERP-FND-025 | Notification templates and per-user preferences. | Phase 2 |

# 4. Functional Requirements — Core Modules

## 4.1. LMS (Learning Management)

Employee training and course delivery. Note: interpretation of “LMS” is subject to Assumption A-01.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-LMS-001 | Course builder with structure: course → modules → lessons. | MVP |
| ERP-LMS-002 | Lesson content types: video, document/PDF, text, external link. | MVP |
| ERP-LMS-003 | Central content/media library with uploads. | MVP |
| ERP-LMS-004 | Enrollment: assign courses to individual employees or teams. | MVP |
| ERP-LMS-005 | Mandatory-training flags with due dates. | MVP |
| ERP-LMS-006 | Progress tracking and completion status per learner. | MVP |
| ERP-LMS-007 | Quizzes / assessments with scoring. | MVP |
| ERP-LMS-008 | Reports: completion rates and scores by employee/team. | MVP |
| ERP-LMS-009 | Self-enrollment and course catalogue. | Phase 2 |
| ERP-LMS-010 | Pass/fail criteria and retake handling. | Phase 2 |
| ERP-LMS-011 | Auto-generated completion certificates. | Phase 2 |

## 4.2. CRM (Customer Relationship Management)

Contact, lead and pipeline management with activity tracking and reporting.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-CRM-001 | Contact management for individuals. | MVP |
| ERP-CRM-002 | Account / company management. | MVP |
| ERP-CRM-003 | Lead capture via manual entry. | MVP |
| ERP-CRM-004 | Lead capture via web form and bulk import. | MVP |
| ERP-CRM-005 | Sales pipeline with configurable stages. | MVP |
| ERP-CRM-006 | Deals / opportunities with value and stage tracking. | MVP |
| ERP-CRM-007 | Activities (calls, meetings, emails, tasks) linked to records. | MVP |
| ERP-CRM-008 | Follow-up reminders. | MVP |
| ERP-CRM-009 | Interaction history / timeline per contact. | MVP |
| ERP-CRM-010 | Tags and segmentation. | MVP |
| ERP-CRM-011 | Lead assignment and ownership. | MVP |
| ERP-CRM-012 | Reports: pipeline value, conversion rate, activity. | MVP |
| ERP-CRM-013 | Two-way email integration (send/receive from CRM). | Phase 2 |

## 4.3. HRMS (Human Resource Management)

Employee records, attendance, leave, payroll basics, onboarding and self-service.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-HRM-001 | Employee master records (personal, job, contact details). | MVP |
| ERP-HRM-002 | Employee document store (offer letters, IDs, certificates). | MVP |
| ERP-HRM-003 | Attendance check-in / check-out. | MVP |
| ERP-HRM-004 | Leave types configuration. | MVP |
| ERP-HRM-005 | Leave requests, approvals and balances. | MVP |
| ERP-HRM-006 | Holiday calendar. | MVP |
| ERP-HRM-007 | Salary structure setup. | MVP |
| ERP-HRM-008 | Payslip generation with deductions. | MVP |
| ERP-HRM-009 | Onboarding workflow / checklist. | MVP |
| ERP-HRM-010 | Org structure and reporting lines. | MVP |
| ERP-HRM-011 | Employee self-service portal. | MVP |
| ERP-HRM-012 | Attendance regularization and approvals. | Phase 2 |
| ERP-HRM-013 | Statutory deductions (TDS / PF / ESI). | Phase 2 |
| ERP-HRM-014 | Offboarding workflow. | Phase 2 |

## 4.4. Inventory Management

Item master, stock movement, alerts and valuation reporting.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-INV-001 | Item / product master (SKU, category, unit, pricing). | MVP |
| ERP-INV-002 | Product categories and attributes. | MVP |
| ERP-INV-003 | Stock tracking (single location). | MVP |
| ERP-INV-004 | Stock-in (goods receipt). | MVP |
| ERP-INV-005 | Stock-out (issue / consumption). | MVP |
| ERP-INV-006 | Stock adjustments and write-offs. | MVP |
| ERP-INV-007 | Low-stock and reorder-level alerts. | MVP |
| ERP-INV-008 | Stock valuation (FIFO / weighted average). | MVP |
| ERP-INV-009 | Reports: stock summary, movement, valuation. | MVP |
| ERP-INV-010 | Multi-location / multi-warehouse stock. | Phase 2 |
| ERP-INV-011 | Batch and expiry tracking. | Phase 2 |

## 4.5. Finance Management

GST-compliant invoicing, expenses, ledgers and financial reporting.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-FIN-001 | GST-compliant sales invoicing. | MVP |
| ERP-FIN-002 | Expense and bill recording. | MVP |
| ERP-FIN-003 | Chart of accounts / ledgers. | MVP |
| ERP-FIN-004 | Receipts and payments entry. | MVP |
| ERP-FIN-005 | Bank and cash account management. | MVP |
| ERP-FIN-006 | GST configuration (rates, GSTIN, HSN/SAC). | MVP |
| ERP-FIN-007 | GST reports (GSTR-ready summaries). | MVP |
| ERP-FIN-008 | Receivables and payables tracking. | MVP |
| ERP-FIN-009 | Financial reports: P&L and outstanding statements. | MVP |
| ERP-FIN-010 | Invoice generation directly from a CRM deal. | Phase 2 |
| ERP-FIN-011 | COGS linkage with Inventory. | Phase 2 |
| ERP-FIN-012 | Multi-currency support. | Phase 2 |

## 4.6. Task Management

Task creation, boards, collaboration and progress reporting.

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-TSK-001 | Task creation (title, description, assignee, due date, priority). | MVP |
| ERP-TSK-002 | Configurable status workflow. | MVP |
| ERP-TSK-003 | Kanban board and list views. | MVP |
| ERP-TSK-004 | Subtasks and checklists. | MVP |
| ERP-TSK-005 | Comments and attachments. | MVP |
| ERP-TSK-006 | Linking tasks to CRM, HR, projects and teams. | MVP |
| ERP-TSK-007 | Reminders and overdue alerts. | MVP |
| ERP-TSK-008 | Reports: workload, overdue, completion. | MVP |
| ERP-TSK-009 | Recurring tasks. | Phase 2 |

## 4.7. Team Management

Teams, hierarchy and role assignment. Implemented as a thin layer over HRMS org structure and RBAC (Assumption A-06).

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-TM-001 | Team creation and membership management. | MVP |
| ERP-TM-002 | Hierarchy / reporting structure. | MVP |
| ERP-TM-003 | Role assignment within teams. | MVP |
| ERP-TM-004 | Team dashboards. | MVP |
| ERP-TM-005 | Member capacity and availability. | Phase 2 |

# 5. Non-Functional Requirements

| Req. ID | Requirement | Priority |
| --- | --- | --- |
| ERP-NFR-001 | Multi-tenant architecture supporting horizontal scaling. | MVP |
| ERP-NFR-002 | Typical page load under 3s; core API responses under 1s under nominal load. | MVP |
| ERP-NFR-003 | Data encryption in transit (TLS) and at rest. | MVP |
| ERP-NFR-004 | RBAC, audit logging and secure session handling. | MVP |
| ERP-NFR-005 | Automated data backup and recovery procedures. | MVP |
| ERP-NFR-006 | Responsive web UI (desktop and mobile browser). | MVP |
| ERP-NFR-007 | Support for current versions of Chrome, Edge, Firefox, Safari. | MVP |
| ERP-NFR-008 | Indian GST and statutory compliance for the Finance module. | MVP |
| ERP-NFR-009 | Target availability of 99.5% (MVP). | MVP |
| ERP-NFR-010 | Localization-ready architecture; English UI at MVP. | MVP |
| ERP-NFR-011 | Target availability of 99.9%. | Phase 2 |
| ERP-NFR-012 | Multi-language UI. | Phase 2 |

# 6. External Interface Requirements

• Payment Gateway: QmaxPay / 1Q1Pay for subscription billing.

• SMS Gateway: OTP and notifications.

• Email Service: transactional email and notifications.

• Future: accounting export and e-invoice / GSTN integration (Phase 2).

# 7. Phase 2 Scope (Deferred Roadmap)

The following modules, drawn from the consolidated ERP feature list, are deferred to Phase 2. Items extending Phase 1 modules are noted as “extended”.

| Cluster | Modules |
| --- | --- |
| Operations & Supply Chain | Purchase, Inventory (extended), Warehouse, Logistics, Supply Chain, Procurement, Material Requirement Planning, Quality Control. |
| Manufacturing & Production | Production, New Product Development, Job Work (Outsource), Job Work (Insource), Maintenance, AMC. |
| Sales & Distribution | Sales Management, Sales Distribution, POS, E-commerce / Aggregator, Import-Export, Bid Management (Domestic & International). |
| Finance & Compliance | Accounts, Finance (extended), Legal & Compliances, Scheme/Cashback/Reward/Gift, Referral & Commission, Cash Management & Settlement (CMSS). |
| Customer & Support | CRM (extended), Complaint & Grievance, IVR / Call Center, SOS Services. |
| Marketing & Content | Digital Marketing, Social Media Management (Social ERP), Content Management (CMS). |
| Tracking & Security | Barcode Management, Geo-Location & Tracking, OTP/MPIN Security (extended). |
| Management & Admin | HRMS / Asset / Admin-IT (extended), Project Management, Operations, Data Management (DRAM), Task Management (extended), LMS (extended). |

You asked me to proceed, so I've detailed all Phase 1 modules below. Two assumptions I'm running with (one-word correction if either is wrong):

- LMS = Learning Management System (employee training/courses, pairs with HRMS). I went this way because CRM already owns leads/pipeline, so Lead Management would be redundant. If you meant Lead Management or Loan Management, tell me and I'll swap that section.

- Multi-tenant SaaS (businesses subscribe to manage their ops) — this shaped the Foundation Layer below. Adjust if "B2C" means individual self-serve.

I've kept this at a detailed sub-feature level (pre-Phase 1-cut). Requirement IDs get assigned at the formal-document stage, same as E-Store Mart and QmaxPay.

# Commercial Proposal

OMARA DIGITECH PVT. LTD. One Ecosystem. Endless Possibilities. COMMERCIAL PROPOSAL Design, Build & Delivery of the Omara Digitech Digital Ecosystem (Phase 1) 6 Static Websites • QmaxPay • E-Mart • 1Q1Pay • Fincomax • ERP Suite

| Field | Detail |
| --- | --- |
| Prepared by | 365 AI Tech Solutions (Delivery Partner) |
| Prepared for | Omara Digitech Pvt. Ltd. (Rudranjali Organics Group) |
| Commercial range | ₹12–14 Lakh + applicable GST (fixed at Phase 0, within band) |
| Model & duration | Fixed-price, milestone-based · ~20 weeks (4–5 months) |
| Version / Status | 1.0 — For Client Review & Sign-Off |
| Date · Validity | 4 July 2026 · valid 30 days from issue |

# 1. The Engagement

Omara Digitech is building a single, connected digital ecosystem — a corporate web presence, a B2B payment-API engine, a retail fin-tech platform, a multi-tier commerce engine, a professional-services marketplace, and an internal operations ERP. This proposal sets out a fixed-price plan to design, build, test and go-live with the Phase 1 (MVP) release of all of these in one coordinated programme, sequenced so the payment rail is built first and every dependent platform integrates against a stable interface.

# 2. What We Deliver

| # | Workstream | Size | Phase 1 Coverage |
| --- | --- | --- | --- |
| 1 | 6 Static Brand Websites | 6 sites | Responsive corporate/product sites; shared design system, CMS-lite, enquiry forms, SEO. |
| 2 | QmaxPay — API Panel | 17 modules | B2B payment-API engine: catalog, prepaid wallet, single-tier reseller panel, developer portal, ledger. |
| 3 | E-Mart — Commerce | 17 modules | Distributor → Retailer → Customer chain; catalog, orders, single gateway + COD, GST billing. |
| 4 | 1Q1Pay — Fintech | 22 modules | AEPS/DMT/BBPS/recharge/UPI over QmaxPay; single-tier retailer channel, prepaid wallet, KYC, settlement. |
| 5 | Fincomax — Marketplace | ~20 modules | Professional-services marketplace + compliance tracking; payments routed via 1Q1Pay. |
| 6 | ERP Suite | 6 modules + foundation | LMS, CRM, HRMS, Inventory, Finance, Task & Team on a multi-tenant SaaS foundation. |
| 7 | Phase 0 — Discovery | 2–3 weeks | Requirement lock, delivery planning, signed baseline and confirmed contract value. |

Each platform is delivered at Phase 1 depth per its signed SRS, with a sprint-based build, fortnightly demos, full QA, UAT support, integrated go-live, and a 60-day post-go-live warranty.

# 3. Commercial Summary

Total Investment: ₹12–14 Lakh + applicable GST Fixed-price and milestone-based. The exact value is confirmed at the close of the Phase 0 requirement-gathering stage, once module depth and integration scope are locked against the signed baseline — and will, in every case, fall within this band.

3.1  Investment & Payment Schedule

Payments are milestone-based, raised on achievement and payable within 7 days of invoice. The rupee columns show the value at each end of the band.

| Milestone | Trigger | % Fee | At ₹12L (₹) | At ₹14L (₹) |
| --- | --- | --- | --- | --- |
| M0 — Mobilisation | On contract signing & kickoff | 15% | 1,80,000 | 2,10,000 |
| M1 — Baseline locked | Phase 0 requirement & delivery-plan sign-off | 10% | 1,20,000 | 1,40,000 |
| M2 — Websites live | 6 static websites accepted | 10% | 1,20,000 | 1,40,000 |
| M3 — Wave 2 accepted | QmaxPay + E-Mart UAT sign-off | 30% | 3,60,000 | 4,20,000 |
| M4 — Wave 3 accepted | 1Q1Pay + Fincomax + ERP UAT sign-off | 25% | 3,00,000 | 3,50,000 |
| M5 — Go-live & closure | Integrated go-live & project closure | 10% | 1,20,000 | 1,40,000 |
| Total |  | 100% | 12,00,000 | 14,00,000 |

3.2  What’s Included / Excluded

| Included in the fee | Excluded (client-borne / at actuals) |
| --- | --- |
| Discovery, design, build, QA & UAT support | GST and any statutory taxes/levies |
| Integrated go-live & stabilisation | AWS, Cloud/hosting, domains, SSL, repositories |
| 60-day warranty (Sev-1/Sev-2 defects) | SMS/email gateways; KYC-vendor fees |
| Source code & bespoke-IP transfer on full payment | Payment-aggregator / AEPS / BBPS / UPI charges |
| Fortnightly demos & milestone acceptance | Paid third-party licences; regulatory/legal fees |
| Shared Hosting Infra till 3 months of Go-Live for running the applications |  |

# 4. Delivery at a Glance

A ~20-week programme across three dependency-sequenced release waves, so value ships early and predictably.

| Stage | Deliverable | Target |
| --- | --- | --- |
| Phase 0 | Discovery, requirement lock — signed baseline | End Week 3 |
| Wave 1 | 6 Static Brand Websites — live | Month 1 |
| Wave 2 | QmaxPay API Panel + E-Mart — UAT sign-off | Month 2.5 |
| Wave 3 | 1Q1Pay + Fincomax + ERP Suite — UAT sign-off | Month 4.5 |
| Closeout | Integrated UAT, stabilisation & go-live | Month 5 |

A detailed week-by-week schedule and Gantt are provided in the accompanying Delivery Timeline Plan.

# 5. Key Commercial Terms

• Value & taxes. Amounts in INR, exclusive of GST and statutory levies (charged at actuals). Final value fixed within ₹12–14 Lakh at Phase 0 close.

• Change control. Scope is defined by the signed Phase 0 baseline; additions are priced separately via written change request.

• IP. Bespoke deliverable IP transfers on full payment; pre-existing frameworks/components remain the partner’s and are licensed for use within the deliverables.

• Warranty. 60-day warranty from each go-live on Sev-1/Sev-2 defects against the signed baseline. Ongoing support available under a separate AMC.

• Dependencies. Live fintech rails and all licences/approvals are client-procured; software is delivered ready-to-integrate. This proposal is read together with the Statement of Work and the Master Services Agreement.

# 6. Acceptance

To proceed, please countersign below. This confirms acceptance of the scope, commercials and terms of this proposal, subject to the definitive Statement of Work and Master Services Agreement.

| For 365 AI Tech Solutions Name: Designation: Signature: Date: | For Omara Digitech Pvt. Ltd. Name: Designation: Signature: Date: |
| --- | --- |

Strictly Private & Confidential — Omara Digitech Pvt. Ltd.

# Project Timeline

OMARA DIGITECH PVT. LTD. One Ecosystem. Endless Possibilities. DELIVERY TIMELINE PLAN Phase 1 Build — 6 Static Websites • QmaxPay • E-Mart • 1Q1Pay • Fincomax • ERP Suite 20-Week Programme • Dependency-Sequenced Waves • Milestone-Linked

| Field | Detail |
| --- | --- |
| Prepared by | 365 AI Tech Solutions (Delivery Partner) |
| Prepared for | Omara Digitech Pvt. Ltd. (Rudranjali Organics Group) |
| Basis | Statement of Work v1.0 — Omara Digitech Digital Ecosystem (Phase 1) |
| Programme duration | 20 weeks (~4.6 months) from contract signing, within the SOW 4–5 month band |
| Delivery model | Fixed-price, milestone-based; agile sprints; three dependency-sequenced release waves |
| Version / Status | 1.0 — For Client Review & Sign-Off |
| Date of issue | 4 July 2026 |

# 1. Scheduling Basis & Assumptions

This plan converts the approved Statement of Work into a week-by-week delivery schedule. The programme runs over 20 weeks (~4.6 months), inside the SOW’s 4–5 month band, and is sequenced by the ecosystem’s dependency chain so that each platform integrates against a stable upstream interface.

|  | Month 1 (W1–4) |  |  |  | Month 2 (W5–8) |  |  |  | Month 3 (W9–13) |  |  |  |  | Month 4 (W14–17) |  |  |  | Month 5 (W18–20) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Workstream / Platform | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 |
| Phase 0 — Discovery & Req. Lock |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wave 1 — 6 Static Websites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wave 2 — QmaxPay API Panel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wave 2 — E-Mart Commerce |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wave 2 — ERP Suite |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wave 3 — 1Q1Pay Fintech |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Wave 3 — Fincomax Marketplace |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Closeout — Integration & Go-Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ◆ Payment Milestones | M0 |  | M1 | M2 |  |  |  |  |  | M3 |  |  |  |  |  |  |  | M4 |  | M5 |

| ■ Phase 0 | ■ Websites | ■ QmaxPay / 1Q1Pay | ■ E-Mart | ■ ERP Suite | ■ Fincomax | ■ Closeout | ■ Milestone |
| --- | --- | --- | --- | --- | --- | --- | --- |

# 3. Release Wave Schedule

| Wave | Deliverable(s) | Window | Target | Milestone |
| --- | --- | --- | --- | --- |
| Phase 0 | Discovery, requirement lock & readiness — signed baseline | Weeks 1–3 | End Week 3 | M1 |
| Wave 1 | 6 Static Brand Websites — live | Weeks 2–4 | End Month 1 | M2 |
| Wave 2 | QmaxPay API Panel + E-Mart + ERP Suite — UAT | Weeks 3–10 | Month 2.5 | M3 |
| Wave 3 | 1Q1Pay + Fincomax — UAT | Weeks 8–18 | Month 4.5 | M4 |
| Closeout | Integrated UAT, stabilisation & go-live | Weeks 16–20 | Month 5 | M5 |

# 7. Governance & Reporting Cadence

| Cadence | Forum | Purpose |
| --- | --- | --- |
| Daily | Internal stand-up | Delivery squads — progress, blockers. |
| Fortnightly | Sprint demo | Stakeholders — working software review at each sprint close. |
| Per milestone | Acceptance review | Client sign-off against agreed acceptance criteria (M1–M5). |

A single empowered Client SPOC is required throughout to keep the cadence and the 20-week schedule intact.

# 8. Schedule Risks & Contingencies

| Risk to schedule | Contingency / Mitigation |
| --- | --- |
| Aggressive wave windows vs. 8-sprint plans | Parallel squads per platform; focused sprint cadence; scope held at Phase 1 MVP depth; non-critical-path platforms (E-Mart, ERP) absorb float. |
| Live-rail credential / certification delays | Software delivered ready-to-integrate; AEPS decoupled as fast-follow; clock pauses only on the dependent rail, not the platform. |
| Late UAT sign-offs | Defined 7–10 day UAT windows with deemed-acceptance; weekly decision log keeps approvals moving. |
| Scope creep across seven workstreams | Locked Phase 0 baseline + written change control; anything beyond baseline is a chargeable CR and re-baselines affected dates. |
| Integration risk (QmaxPay ↔ 1Q1Pay ↔ E-Mart/Fincomax) | Integration contracts fixed at Phase 0; QmaxPay built first; staged dev → staging → UAT environments; dedicated closeout window (W16–20). |

# 9. Acceptance of Delivery Plan

By signing below, the parties confirm agreement to this delivery timeline, its milestones, dependencies and cadence, as read together with the Statement of Work and the Master Services Agreement.

| For 365 AI Tech Solutions Name: Designation: Signature: Date: | For Omara Digitech Pvt. Ltd. Name: Designation: Signature: Date: | Witness Name: Designation: Signature: Date: |
| --- | --- | --- |

# MSA-Master Services Agreement

OMARA DIGITECH PVT. LTD. One Ecosystem. Endless Possibilities. MASTER SERVICES AGREEMENT Omara Digitech Digital Ecosystem Engagement

This Master Services Agreement (“Agreement”) is made on [Effective Date] (“Effective Date”) between:

| SERVICE PROVIDER | CLIENT |
| --- | --- |
| 365 AI Tech Solutions Faridabad, Haryana, India GSTIN: 06ACFPK0631A1ZF · PAN: ACFPK0631A MSME: UDYAM-HR-03-0044534 (“Service Provider”) | Omara Digitech Pvt. Ltd. (Rudranjali Organics Group) CIN: [Client CIN] GSTIN: [Client GSTIN] Regd. Office: [Client address] (“Client”) |

The Service Provider and the Client are each a “Party” and together the “Parties”.

| Agreement reference | MSA — Omara Digitech Digital Ecosystem Engagement |
| --- | --- |
| Version / Status | 1.0 — For Review & Execution |
| Classification | Strictly Private & Confidential |
| Date of issue | 04 July 2026 |

# Background

A.  The Client wishes to procure software design, build, testing and delivery services for its digital ecosystem, and the Service Provider has agreed to provide such services.

B.  This Agreement sets out the framework terms governing the relationship. The specific scope, deliverables, timeline and commercials for each engagement are set out in one or more Statements of Work (each a “SOW”) issued under, and incorporating, this Agreement.

C.  The first SOW under this Agreement is the Statement of Work v1.0 for the Omara Digitech Digital Ecosystem (Phase 1), dated 04 July 2026.

# 1. Definitions & Interpretation

| Term | Meaning |
| --- | --- |
| SOW | A Statement of Work issued under this Agreement defining scope, deliverables, timeline, fees and acceptance for a specific engagement. |
| Deliverables | The software, documents and other outputs to be provided under a SOW. |
| Services | The services performed by the Service Provider under a SOW. |
| Confidential Information | Non-public information of a Party disclosed in connection with this Agreement. |
| Background IP | Tools, frameworks, libraries, components and know-how existing before, or developed outside, an engagement. |
| Change Request | A written request to vary the scope, fees or timeline of a SOW. |

1.1  Clause headings are for convenience only. References to a SOW include its schedules. “Including” means “including without limitation”.

# 2. Structure & Order of Precedence

2.1  This Agreement governs all Services. No SOW takes effect until signed by both Parties; each SOW incorporates the terms of this Agreement.

2.2  In the event of conflict, the order of precedence is: this Agreement → the applicable SOW → the applicable Purchase Order → the Commercial Proposal; save that a SOW may expressly override a specific clause of this Agreement for that engagement only.

# 3. Term

3.1  This Agreement commences on the Effective Date and continues until all SOWs are completed and all obligations (including warranty) are discharged, unless terminated earlier under Clause 14.

# 4. Services & Standards

4.1  The Service Provider shall perform the Services with reasonable skill and care, by suitably qualified personnel, in a professional manner and in accordance with the applicable SOW.

4.2  Development follows OWASP-aligned secure-development practices; testing (unit, integration and user-acceptance) is performed as set out in the applicable SOW. The Service Provider retains delivery management and quality ownership end-to-end.

# 5. Fees, Invoicing & Payment

5.1  All fees are exclusive of GST and other statutory taxes/levies, which are charged at actuals. Third-party costs (including cloud/hosting, domains, SSL, SMS/email gateways, payment-aggregator/AEPS/BBPS/UPI charges, KYC-vendor fees and paid licences) are excluded and borne by the Client.

# 6. Change Control

6.1  Any variation to a SOW is managed by written Change Request. The Service Provider assesses impact on scope, effort, fees and timeline; no change is binding until agreed in writing by both Parties. The fixed price is valid against the signed baseline only.

# 7. Client Responsibilities & Dependencies

7.1  The Client shall: nominate an empowered single point of contact; provide content, brand assets, data and access; procure all third-party accounts, credentials and environments; obtain all licences, sponsor-bank/aggregator agreements and regulatory approvals; and give timely sign-offs and UAT.

7.2  Delay by the Client in any dependency pauses the clock on the affected workstream, and resulting slippage is not attributable to the Service Provider.

# 8. Acceptance & Warranty

8.1  Deliverables are accepted against the acceptance criteria and UAT windows in the applicable SOW. Where the Client does not sign off or log qualifying defects within the UAT window, the Deliverable is deemed accepted.

8.2  Each Deliverable carries the warranty stated in the applicable SOW (for the current SOW: sixty (60) days from go-live against Severity-1/Severity-2 defects). The warranty excludes new requirements, enhancements, third-party/provider faults, and issues arising from Client-side configuration or data.

# 9. Intellectual Property

9.1  On receipt of full payment for the relevant Deliverable, intellectual property in the bespoke Deliverables created for the Client transfers to the Client.

9.2  Background IP remains the property of the Service Provider and is licensed to the Client on a non-exclusive, perpetual basis for use within the Deliverables. Third-party and open-source components remain under their respective licences.

# 10. Confidentiality

10.1  Each Party shall keep the other's Confidential Information secure and use it only for the purposes of this Agreement. This obligation survives termination for three (3) years and does not apply to information that is public, independently developed, or lawfully received from a third party.

# 11. Data Protection

11.1  The Parties shall comply with applicable Indian data-protection law, including the Digital Personal Data Protection Act, 2023. The Client is the data fiduciary/controller and is responsible for lawful collection and consent; the Service Provider processes personal data on the Client's documented instructions and applies the security posture agreed in the SOW.

# 12. Third-Party, Regulatory & Licensing Dependencies

12.1  The Service Provider delivers software capability ready to integrate against documented interfaces. Live payment/banking rails and all licences, registrations and statutory approvals are the Client's sole responsibility. The Service Provider provides no legal, financial, tax or regulatory advice and is not liable for the Client's regulatory standing.

12.2  Any compliance catalog, tracking or calendar tools are administrative aids maintained from Client-supplied data; they do not constitute statutory advice, do not auto-file, and do not guarantee compliance outcomes.

# 13. Limitation of Liability

13.1  Subject to Clause 13.3, each Party's aggregate liability arising out of or in connection with this Agreement is limited to the total fees paid under the applicable SOW in the twelve (12) months preceding the event giving rise to the claim.  [Default per Open Decision OD-2 — confirm at execution]

13.2  Neither Party is liable for indirect, incidental, consequential, or loss-of-profit/data damages, or for losses arising from third-party services, provider outages, the Client's regulatory standing, or Client-supplied data/configuration.

# 14. Termination

14.1  Either Party may terminate this Agreement or any SOW for material breach not cured within thirty (30) days of written notice, or immediately on the other Party's insolvency.

14.2  On termination, the Client shall pay for all Services completed and in progress to the termination date, including the current milestone pro-rata. Accepted Deliverables and their IP follow the payment terms above. Clauses 9–13, 16 and 17 survive termination.

# 15. Indemnity

15.1  The Service Provider shall indemnify the Client against third-party claims that the bespoke Deliverables infringe that third party's intellectual property, subject to the cap in Clause 13. The Client shall indemnify the Service Provider against claims arising from Client-supplied content, data, or the Client's regulatory or licensing position.

# 16. Force Majeure

16.1  Neither Party is liable for delay or failure caused by events beyond its reasonable control. The affected Party shall notify the other and use reasonable efforts to mitigate; timelines are extended by the period of the event.

# 17. Governing Law & Dispute Resolution

17.1  This Agreement is governed by the laws of India. The Parties shall first attempt to resolve any dispute by good-faith escalation between senior representatives.

17.2  Failing resolution within thirty (30) days, the dispute shall be referred to arbitration by a sole arbitrator under the Arbitration and Conciliation Act, 1996; the seat and venue shall be Faridabad, Haryana, and the language English. Courts at Faridabad have exclusive jurisdiction for interim relief.  [Default per Open Decision OD-1 — confirm at execution]

# 18. General

18.1  Notices. Notices shall be in writing to the Parties' registered addresses or nominated email, and deemed received on delivery.

18.2  Assignment. Neither Party may assign this Agreement without the other's prior written consent, not to be unreasonably withheld.

18.3  Independent contractors. The Parties are independent contractors; nothing creates a partnership, agency or employment relationship.

18.4  Non-solicitation. During the term and for six (6) months after, neither Party shall knowingly solicit for employment the other's personnel directly engaged in the Services.

18.5  Entire agreement; amendment; severability; waiver. This Agreement and its SOWs are the entire agreement and supersede prior discussions. Amendments must be in writing and signed. If any provision is unenforceable, the remainder stands. No waiver is implied by delay. This Agreement may be executed in counterparts.

# Execution

Agreed and executed by the duly authorised representatives of the Parties as of the Effective Date.

| For 365 AI Tech Solutions Name: Designation: Signature: Date: Witness: | For Omara Digitech Pvt. Ltd. Name: Designation: Signature: Date: Witness: |
| --- | --- |

Placeholder Register  (complete before execution): Effective Date · Client CIN · Client GSTIN · Client registered address · signatory names & designations. Open Decisions: OD-1 jurisdiction (Faridabad arbitration) and OD-2 liability cap (12-month fees) are set to their default positions — confirm at execution.

# Purchase Order (PO)

OMARA DIGITECH PVT. LTD. One Ecosystem. Endless Possibilities. PURCHASE ORDER

| PO Number PO/2026-27/01 | PO Date 04 July 2026 | Currency INR (₹) | Status For Issue |
| --- | --- | --- | --- |

| BUYER (Issued by) | SUPPLIER (Issued to) |
| --- | --- |
| Omara Digitech Pvt. Ltd. (Rudranjali Organics Group) Address: [Buyer registered address] GSTIN: [Buyer GSTIN] Contact: Mr. Manish Fozdar, Director | 365 AI Tech Solutions Faridabad, Haryana GSTIN: 06ACFPK0631A1ZF Contact: info@365aitech.com |

| Subject | Design, Build & Delivery of the Omara Digitech Digital Ecosystem — Phase 1 |
| --- | --- |
| Governing documents | Master Services Agreement (MSA) and Statement of Work v1.0 (SOW) dated 04 Jul 2026; Commercial Proposal v1.0. |
| Order of precedence | MSA → SOW → this Purchase Order → Commercial Proposal. |

# Order Line Items

Milestone-based, per SOW §7.2 / §12.1. Amounts below are shown at the Not-to-Exceed (NTE) ceiling of ₹14,00,000; the confirmed contract value is fixed at Phase 0 close within the ₹12–14 Lakh band and milestone invoices are raised against that confirmed value.

| # | Description (Deliverable / Milestone) | Milestone | % | NTE Amount (₹) |
| --- | --- | --- | --- | --- |
| 1 | Mobilisation & kickoff | M0 | 15% | 2,10,000 |
| 2 | Phase 0 requirement baseline & delivery-plan sign-off | M1 | 10% | 1,40,000 |
| 3 | 6 Static brand websites accepted (live) | M2 | 10% | 1,40,000 |
| 4 | QmaxPay API Panel + E-Mart — UAT sign-off | M3 | 30% | 4,20,000 |
| 5 | 1Q1Pay + Fincomax + ERP Suite — UAT sign-off | M4 | 25% | 3,50,000 |
| 6 | Integrated go-live & project closure | M5 | 10% | 1,40,000 |

| Sub-Total (NTE, exclusive of GST) | ₹ 14,00,000 |
| --- | --- |
| GST @ 18% (CGST 9% + SGST 9%, or IGST 18% if inter-state)* | ₹ 2,52,000 |
| Grand Total (NTE, inclusive of GST) | ₹ 16,52,000 |

*Place of supply and CGST/SGST vs IGST split to be applied on the tax invoice per the buyer’s GST registration state. GST and any statutory levies are charged at actuals.

# Delivery & Payment

| Delivery model | Services delivered per the SOW timeline — ~20-week programme across three release waves; integrated go-live by Month 5. |
| --- | --- |
| Delivery location | Remote delivery; deployment to buyer-owned cloud/hosting environment. |
| Invoicing | One tax invoice per milestone on achievement/acceptance, at the Phase 0-confirmed contract value. |

# Purchase Order Terms & Conditions

• Governing terms. This PO is issued under and governed by the MSA and SOW. In any conflict, the order of precedence is MSA → SOW → this PO → Commercial Proposal.

• Not-to-exceed value. This PO authorises expenditure up to the NTE ceiling of ₹14,00,000 + GST. The confirmed contract value is fixed at Phase 0 close within ₹12–14 Lakh; invoices are raised at that confirmed value and shall not exceed the ceiling without a revised PO.

• Taxes & third-party costs. Amounts are exclusive of GST/statutory levies (at actuals). Third-party costs — cloud/hosting, domains, SSL, SMS/email gateways, payment-aggregator/AEPS/BBPS/UPI charges, KYC-vendor fees and paid licences — are excluded and borne by the buyer.

• Acceptance. Each milestone is accepted per the acceptance criteria and UAT windows in the SOW; deemed acceptance applies where UAT is not actioned within the window.

• Change control. Any change to scope, value or schedule is handled via written change control per the SOW and, where value-affecting, a revised or supplementary PO.

• Intellectual property. IP in bespoke deliverables transfers to the buyer on full payment; pre-existing frameworks/components remain the supplier’s and are licensed for use within the deliverables

• Dependencies. Live fintech rails and all licences/approvals are buyer-procured; software is delivered ready-to-integrate. Buyer-side delays pause the affected workstream clock.

• Confidentiality. This PO and all engagement information are Strictly Private & Confidential.

# Authorisation

| Authorised by — Omara Digitech Pvt. Ltd. Buyer Name: Designation: Signature: Date: | Acknowledged by — 365 AI Tech Solutions Supplier Name: Designation: Signature: Date: |
| --- | --- |

Placeholder Register  (to be completed before issue): PO sequence number · Buyer registered address · Buyer GSTIN · Supplier contact/email · Authorised approver name & designation.