## Task List
# | Phase | Task | Requirements | Depends on | Size | Status | Owner | Notes
1 | 0. Setup | Repository, workspaces, TypeScript, linting, formatting | - | - | S | Not started
2 | 0. Setup | Single-image Dockerfile with process supervisor; compose for external services | OPS-001, OPS-004 | Repository | M | Not started
3 | 0. Setup | Typed configuration schema with production guards | OPS-003 | Repository | M | Not started
4 | 0. Setup | CI: build, typecheck, lint, test, dependency and secret scanning | SEC-002, QA-001 | Repository | M | Not started
5 | 1. Foundation | Correlation ID propagation through request, job and provider calls | CORE-001 | Setup | S | Not started
6 | 1. Foundation | Tenant context resolution and enforcement | CORE-002 | Correlation ID | M | Not started
7 | 1. Foundation | Error envelope and global exception filter | CORE-005 | Setup | S | Not started
8 | 1. Foundation | Money value type in integer minor units | CORE-006 | Setup | S | Not started
9 | 1. Foundation | Idempotency service with unique-key collapse | CORE-003 | Tenant context | M | Not started
10 | 1. Foundation | Transactional outbox and publisher | CORE-008 | Tenant context | L | Not started
11 | 1. Foundation | Base schema, base repository, soft delete, optimistic concurrency | CRUD-001, CRUD-002, CRUD-006, CORE-009 | Tenant context | L | Not started
12 | 1. Foundation | Listing: filtering, search, sorting, cursor and offset pagination | CRUD-003, CRUD-004 | Base repository | M | Not started
13 | 1. Foundation | Bulk upsert, bulk archive, bulk delete | CRUD-005 | Base repository | M | Not started
14 | 1. Foundation | Migration and seed CLI | OPS-005 | Base schema | M | Not started
15 | 2. Identity | Firebase Admin integration and ID-token verification | AUTH-001 | Foundation | M | Not started
16 | 2. Identity | Google sign-in flow end to end | AUTH-001 | Firebase integration | M | Not started
17 | 2. Identity | Mobile OTP flow with rate limiting | AUTH-002 | Firebase integration | M | Not started
18 | 2. Identity | Identity linking across Google and phone | AUTH-003 | Google, OTP | M | Not started
19 | 2. Identity | Platform sessions: access and rotating refresh tokens, reuse detection | AUTH-004 | Firebase integration | L | Not started
20 | 2. Identity | Account states and session/device management | AUTH-005, AUTH-006 | Platform sessions | M | Not started
21 | 2. Identity | Identity-provider interface and mock adapter | AUTH-007 | Firebase integration | S | Not started
22 | 3. Access control | Permission catalogue with startup validation | RBAC-001 | Foundation | M | Not started
23 | 3. Access control | Five seeded roles and scope model | RBAC-002, RBAC-003 | Permission catalogue | M | Not started
24 | 3. Access control | Ability factory compiling ownership scopes into query filters | RBAC-006 | Permission catalogue | L | Not started
25 | 3. Access control | Route guards and service-level enforcement | RBAC-005 | Ability factory | M | Not started
26 | 3. Access control | Reseller isolation and its authorization matrix tests | RBAC-004 | Ability factory | M | Not started
27 | 3. Access control | Effective-permissions endpoint and cache invalidation | RBAC-007 | Ability factory | M | Not started
28 | 3. Access control | User lifecycle, memberships, CSV import | USR-001, USR-002, USR-003 | Access control | L | Not started
29 | 4. Audit and observability | Append-only audit store with redaction | AUD-001, AUD-002, AUD-003 | Foundation | L | Not started
30 | 4. Audit and observability | Activity timelines and privileged-read recording | AUD-004, AUD-006 | Audit store | M | Not started
31 | 4. Audit and observability | Retention and hash-chained archive with verification | AUD-005 | Audit store | M | Not started
32 | 4. Audit and observability | Structured logging with redaction | OBS-001 | Foundation | S | Not started
33 | 4. Audit and observability | OpenTelemetry tracing from both entry points | OBS-002, OBS-005 | Foundation | M | Not started
34 | 4. Audit and observability | Metrics and health endpoints | OBS-003, OBS-004 | Foundation | M | Not started
35 | 5. Billing | Plans, versions, prices, entitlements and quotas | BILL-001 | Foundation | L | Not started
36 | 5. Billing | Subscription state machine | BILL-002 | Plans | M | Not started
37 | 5. Billing | Immutable usage events with idempotent ingestion | BILL-003 | Plans, Idempotency | M | Not started
38 | 5. Billing | Entitlement and quota checks callable by any module | BILL-004 | Plans | M | Not started
39 | 5. Billing | Invoices, tax fields and gapless numbering | BILL-005 | Plans, Money | L | Not started
40 | 5. Billing | Payment-provider interface and mock adapter | BILL-011 | Foundation | M | Not started
41 | 5. Billing | Razorpay orders from server-calculated amounts | BILL-006 | Provider interface | M | Not started
42 | 5. Billing | Signature verification and security events | BILL-007 | Razorpay orders | S | Not started
43 | 5. Billing | Raw-body webhook route, persistence and deduplication | BILL-008 | Razorpay orders | M | Not started
44 | 5. Billing | Refund request and approval flow | BILL-009 | Razorpay orders | M | Not started
45 | 5. Billing | Scheduled reconciliation and exception report | BILL-010 | Razorpay orders | M | Not started
46 | 6. Notifications | Channel-neutral notification service and adapter interface | NOTI-001 | Foundation | M | Not started
47 | 6. Notifications | Versioned templates in a sandboxed engine | NOTI-002 | Notification service | M | Not started
48 | 6. Notifications | In-app inbox, unread count and retention | NOTI-003 | Notification service | M | Not started
49 | 6. Notifications | Email adapter and local capture | NOTI-004 | Notification service | S | Not started
50 | 6. Notifications | SMS adapter with suppression | NOTI-005 | Notification service | M | Not started
51 | 6. Notifications | FCM push and device-token registration | NOTI-006 | Notification service | M | Not started
52 | 6. Notifications | Preferences, mandatory categories and quiet hours | NOTI-007 | Notification service | M | Not started
53 | 6. Notifications | Delivery tracking, retry and dead-letter | NOTI-008, NOTI-009 | Notification service | M | Not started
54 | 7. Transactions | Transaction type registry and schemas | TXN-001 | Foundation | M | Not started
55 | 7. Transactions | Single-step execution and result recording | TXN-002 | Type registry | M | Not started
56 | 7. Transactions | Multi-step workflow engine with state transitions | TXN-003 | Type registry | L | Not started
57 | 7. Transactions | Human tasks with assignment and permissions | TXN-004 | Workflow engine | M | Not started
58 | 7. Transactions | Entitlement check and usage recording per transaction | TXN-005 | Workflow engine, Entitlements | M | Not started
59 | 7. Transactions | Retry, compensation and history | TXN-006, TXN-007 | Workflow engine | M | Not started
60 | 8. Rules and scoring | Rule definition, validation and versioning | RULE-001, RULE-002 | Foundation | L | Not started
61 | 8. Rules and scoring | Rule evaluation and decision audit | RULE-003, RULE-006 | Rule definitions | M | Not started
62 | 8. Rules and scoring | Tenant scoping and simulation | RULE-004, RULE-005 | Rule definitions | M | Not started
63 | 8. Rules and scoring | Score definitions and computation | SCORE-001, SCORE-002 | Rules | L | Not started
64 | 8. Rules and scoring | Leaderboards with deterministic ranking | SCORE-003, SCORE-004 | Scores | M | Not started
65 | 8. Rules and scoring | Score history | SCORE-005 | Scores | S | Not started
66 | 9. Reporting | Report registry with permissions and schemas | REP-001 | Foundation | M | Not started
67 | 9. Reporting | JSON query definition and injection guard | REP-002 | Report registry | L | Not started
68 | 9. Reporting | Dashboard metrics with enforced tenant filtering | REP-003 | Report registry | M | Not started
69 | 9. Reporting | Saved views validated at save and execution | REP-004 | Report registry | M | Not started
70 | 9. Reporting | Asynchronous export to object storage | REP-005 | Report registry | M | Not started
71 | 9. Reporting | Scheduled reports with execution-time permission checks | REP-006 | Exports, Notifications | M | Not started
72 | 9. Reporting | Report execution audit | REP-007 | Report registry, Audit | S | Not started
73 | 10. Integrations | Integration registry and configuration schemas | INT-001 | Foundation | M | Not started
74 | 10. Integrations | Secret references and connection testing | INT-002, INT-003 | Integration registry | M | Not started
75 | 10. Integrations | Tenant API keys with scopes and rotation | INT-006 | Access control | M | Not started
76 | 10. Integrations | Outbound webhooks: signing, retry, replay, history | INT-004 | Integration registry, Outbox | L | Not started
77 | 10. Integrations | Inbound webhook verification and deduplication | INT-005 | Integration registry | M | Not started
78 | 10. Integrations | Rate limiting across IP, user, tenant and key | INT-007 | API keys | M | Not started
79 | 11. Support | Ticket model and lifecycle | SUP-001 | Foundation | M | Not started
80 | 11. Support | Threaded messages, attachments and internal notes | SUP-002 | Ticket model | M | Not started
81 | 11. Support | Assignment, priority and due dates | SUP-003 | Ticket model | S | Not started
82 | 11. Support | Visibility by tenant and role | SUP-004 | Ticket model, Access control | M | Not started
83 | 11. Support | Ticket notifications | SUP-005 | Ticket model, Notifications | S | Not started
84 | 12. Frontend | Next.js application shell, API client generation, session handling | WEB-002 | Identity | L | Not started
85 | 12. Frontend | Google sign-in and OTP screens | WEB-001 | Application shell | M | Not started
86 | 12. Frontend | Role-aware navigation from effective permissions | WEB-002 | Application shell | M | Not started
87 | 12. Frontend | Tenant and organization-unit selection | WEB-003 | Application shell | M | Not started
88 | 12. Frontend | Configurable CRUD screens with search, filter and bulk actions | WEB-004 | Application shell | L | Not started
89 | 12. Frontend | Dashboards, charts and saved views | WEB-005 | Reporting | L | Not started
90 | 12. Frontend | Notification bell and inbox | WEB-006 | Notifications | M | Not started
91 | 12. Frontend | Billing, subscription, invoice and refund screens | WEB-007 | Billing | L | Not started
92 | 12. Frontend | Support ticket screens | WEB-008 | Support | M | Not started
93 | 13. Hardening | Security headers, CORS, payload limits, injection protection | SEC-001 | All modules | M | Not started
94 | 13. Hardening | Contract tests and API versioning checks | CORE-010 | All modules | M | Not started
95 | 13. Hardening | Tenant-isolation suite across API, repository, jobs, reports and files | RBAC-004, CORE-002 | All modules | L | Not started
96 | 13. Hardening | Browser end-to-end journeys for every major path | QA-001 | Frontend | L | Not started
97 | 13. Hardening | Graceful shutdown and job draining | OPS-006 | All modules | S | Not started
98 | 13. Hardening | Backup, restore and restore verification | OPS-007 | All modules | M | Not started
99 | 13. Hardening | Fresh-clone verification and definition of done | QA-002 | All modules | M | Not started

## Requirements
ID | Section | Requirement | Acceptance | Status
CORE-001 | 1. Platform foundation | Correlation identifier: Every request receives a correlation ID propagated to logs, jobs, outbound integrations and audit events. | One identifier traces a request across API, worker and provider logs. | Not started
CORE-002 | 1. Platform foundation | Tenant context required: All tenant-owned operations resolve a tenant context before any repository access. Tenant identity is never read from a request body. | Requests without a resolved tenant are rejected; a body-supplied tenantId is refused rather than ignored. | Not started
CORE-003 | 1. Platform foundation | Idempotency: Write endpoints whose retry could duplicate a financial, usage or notification effect accept an idempotency key. | Reusing a key returns the original outcome and creates no second record. | Not started
CORE-004 | 1. Platform foundation | Input validation: All input passes a global validation pipe with an allowlist; unknown fields are rejected. | An unknown field returns a documented validation error, not a silent drop. | Not started
CORE-005 | 1. Platform foundation | Error envelope: One versioned error envelope carries code, message, correlation ID and optional field errors. | Clients receive the same shape for 4xx and 5xx across every module. | Not started
CORE-006 | 1. Platform foundation | Money representation: Money is stored as integer minor units with an ISO currency code. Floating-point money is prohibited. | Billing tests operate in paise with no rounding drift across many lines. | Not started
CORE-007 | 1. Platform foundation | Time representation: Timestamps are stored in UTC; tenant and user time zones apply only at presentation and scheduling boundaries. | Scheduled work resolves the configured zone correctly across a DST change. | Not started
CORE-008 | 1. Platform foundation | Transactional outbox: Writes needing asynchronous side effects append to an outbox inside the same database transaction. | A simulated worker outage loses no side effect; replay creates no duplicate. | Not started
CORE-009 | 1. Platform foundation | Soft deletion: Soft deletion is the default for user-managed records. Financial, payment and audit records are never hard-deleted. | Restore works where permitted; protected records refuse deletion. | Not started
CORE-010 | 1. Platform foundation | Contract versioning: Public API and event contracts are versioned and backward-compatible within a major version. | A contract test detects an unintended breaking change. | Not started
AUTH-001 | 2. Authentication (Firebase) | Google sign-in: Users authenticate with Google through Firebase; the platform verifies the Firebase ID token server-side on every exchange. | A forged or expired token is rejected; a valid one yields a platform session. | Not started
AUTH-002 | 2. Authentication (Firebase) | Mobile OTP: Users authenticate with phone number and OTP through Firebase phone auth. | OTP issuance is rate-limited per number and per IP; a replayed OTP fails. | Not started
AUTH-003 | 2. Authentication (Firebase) | Identity linking: A Google identity and a phone identity resolve to one platform account when they belong to the same verified user. | Signing in by either method reaches the same account and its memberships. | Not started
AUTH-004 | 2. Authentication (Firebase) | Platform sessions: The platform issues its own short-lived access token and rotating refresh token; only hashed refresh identifiers are stored. | Refresh-token reuse revokes the family and records a security event. | Not started
AUTH-005 | 2. Authentication (Firebase) | Account states: Accounts carry invited, active, suspended and archived states. | A suspended or archived account cannot obtain or refresh a session. | Not started
AUTH-006 | 2. Authentication (Firebase) | Session and device management: Users list their sessions and revoke one or all. | A revoked session cannot refresh or reach a protected endpoint. | Not started
AUTH-007 | 2. Authentication (Firebase) | Provider abstraction: Firebase sits behind an identity-provider interface so another provider can be added without touching account or session logic. | A mock provider and Firebase pass the same contract tests. | Not started
USR-001 | 3. Users, tenancy and RBAC | User lifecycle: Create, invite, view, update, suspend, reactivate and archive users. | Each transition requires a permission and emits an audit event. | Not started
USR-002 | 3. Users, tenancy and RBAC | Memberships: Users hold memberships in tenants and organization units with effective dates and status. | Removing a membership removes access immediately after cache invalidation. | Not started
USR-003 | 3. Users, tenancy and RBAC | Bulk import: Users import from CSV as an asynchronous validated job with preview and row-level errors. | A failed row does not corrupt successful rows; duplicate policy is explicit. | Not started
RBAC-001 | 3. Users, tenancy and RBAC | Permission catalogue: A central catalogue registers every permission with a stable identifier. Startup fails when a role references an unknown permission. | Booting with a typo in a role definition aborts with an actionable error. | Not started
RBAC-002 | 3. Users, tenancy and RBAC | Role hierarchy: Superadmin, admin, enterprise client, reseller and customer are seeded roles with documented scopes. | Each role's permission set is asserted by an authorization matrix test. | Not started
RBAC-003 | 3. Users, tenancy and RBAC | Scope isolation: A tenant-scoped grant can never satisfy a platform-scoped permission. | A user holding every tenant permission is still refused a platform operation. | Not started
RBAC-004 | 3. Users, tenancy and RBAC | Reseller isolation: A reseller sees only their own customers; two resellers with identically named customers remain isolated. | A cross-reseller read returns nothing, not a filtered subset. | Not started
RBAC-005 | 3. Users, tenancy and RBAC | Dual enforcement: Permissions are enforced in route guards and again in sensitive service and repository operations. | Calling a service outside an HTTP controller cannot bypass authorization. | Not started
RBAC-006 | 3. Users, tenancy and RBAC | Ownership scopes: Ownership rules cover own, team, organization-unit and all-tenant scopes, compiled into the database query itself. | A scoped user never loads records they may not see. | Not started
RBAC-007 | 3. Users, tenancy and RBAC | Effective permissions: An endpoint returns the caller's effective permissions for menu and action visibility. | Frontend hints never replace backend enforcement; a forged hint changes nothing. | Not started
CRUD-001 | 4. CRUD foundation | Base document: Every tenant-owned document carries id, tenant, organization unit, status, tags, custom fields, audit stamps, soft-delete marker and version. | A generated domain schema inherits the approved base fields. | Not started
CRUD-002 | 4. CRUD foundation | Reusable services: Create, view, list, update, archive and restore are provided with hooks for validation and authorization. | A reference entity is implemented without copying infrastructure code. | Not started
CRUD-003 | 4. CRUD foundation | Listing, search and filter: Standardised pagination, field allowlists, sorting, filtering and search. | An unapproved field or operator is rejected; normal filters hit an index. | Not started
CRUD-004 | 4. CRUD foundation | Pagination: Cursor pagination for large or volatile collections; offset pagination only where bounded. | Paging duplicates or omits no record while data changes underneath. | Not started
CRUD-005 | 4. CRUD foundation | Bulk operations: Bulk upsert, bulk archive and bulk delete, each tenant-scoped and matched on a tenant-scoped key. | A bulk upsert cannot touch another tenant's rows even with a colliding key. | Not started
CRUD-006 | 4. CRUD foundation | Optimistic concurrency: Conflict-sensitive updates carry a version; a stale update is refused. | A stale write returns a documented conflict rather than overwriting. | Not started
CRUD-007 | 4. CRUD foundation | Custom fields: Typed custom-field definitions with validation, an explicit indexing policy and per-field permissions. | Invalid values are rejected and no index is created from request input. | Not started
CRUD-008 | 4. CRUD foundation | Import and export: Asynchronous import and export with preview, validation and a downloadable error file. | Large operations do not block the API and remain tenant-isolated. | Not started
BILL-001 | 5. Billing and payments (Razorpay) | Plans and pricing: Plans carry versions, prices, intervals, trials, entitlements and quotas with effective dates. | Changing a plan creates a new version and rewrites no historical invoice. | Not started
BILL-002 | 5. Billing and payments (Razorpay) | Subscriptions: Subscription states are pending, trialing, active, past_due, paused, cancelled and expired with an explicit transition table. | Only valid transitions are accepted; each is audited. | Not started
BILL-003 | 5. Billing and payments (Razorpay) | Usage events: Usage events are immutable and carry tenant, metric, quantity, unit-price snapshot, source reference and idempotency key. | A duplicate event is ignored and remains traceable. | Not started
BILL-004 | 5. Billing and payments (Razorpay) | Entitlements and quotas: Real-time entitlement and quota checks are callable by any business module. | A protected action is refused when the plan, credit or quota disallows it, and no usage is recorded for the refused call. | Not started
BILL-005 | 5. Billing and payments (Razorpay) | Invoices: Invoices carry line items, discounts, taxes, totals, currency and payment status, with configurable GST fields and gapless numbering. | Totals are reproducible from stored line-item snapshots; numbering has no gaps under concurrent issue. | Not started
BILL-006 | 5. Billing and payments (Razorpay) | Razorpay orders: Orders are created from server-calculated amounts. Amount and tenant are never taken from the client. | A tampered client amount cannot alter the order. | Not started
BILL-007 | 5. Billing and payments (Razorpay) | Signature verification: Payment signatures are verified server-side before a payment is marked successful. | An invalid signature is rejected and logged as a security event. | Not started
BILL-008 | 5. Billing and payments (Razorpay) | Webhooks: Razorpay webhooks are received on an authenticated route, verified against the raw request body, persisted before processing and deduplicated on provider event id. | Repeated delivery produces exactly one business outcome; a re-serialized body fails. | Not started
BILL-009 | 5. Billing and payments (Razorpay) | Refund requests: Refunds follow a request-and-approval flow with reason, permission, idempotency and audit; full and partial are distinguished. | A duplicate refund request returns the existing result rather than refunding twice. | Not started
BILL-010 | 5. Billing and payments (Razorpay) | Reconciliation: Scheduled reconciliation compares local payments against the provider and reports exceptions. | A mismatch is surfaced without silently changing financial history. | Not started
BILL-011 | 5. Billing and payments (Razorpay) | Provider abstraction: Razorpay sits behind a payment-provider interface with a mock adapter for local development. | Mock and Razorpay adapters pass identical contract tests. | Not started
TXN-001 | 6. Transactions and workflow | Transaction types: Transaction types are declared as configuration with a stable identifier, input schema, output schema, permissions and pricing hook. | A new type is added without changing engine code. | Not started
TXN-002 | 6. Transactions and workflow | Single-step transactions: A single-step type executes, records its result and completes. | The stored result is reproducible from the recorded inputs. | Not started
TXN-003 | 6. Transactions and workflow | Multi-step workflow: A multi-step type advances through declared states with entry and exit conditions. | An invalid transition is refused; the current state is always reconstructable. | Not started
TXN-004 | 6. Transactions and workflow | Human tasks: Steps requiring a person create an assignable task with a permission and a due date. | A cross-tenant decision attempt is refused. | Not started
TXN-005 | 6. Transactions and workflow | Transaction billing: A transaction consults entitlements before executing and records usage on success. | An exhausted quota refuses the transaction and bills nothing. | Not started
TXN-006 | 6. Transactions and workflow | Retry and compensation: A failed step retries with backoff; a non-retryable failure runs its declared compensation. | A partially completed multi-step transaction leaves no inconsistent state. | Not started
TXN-007 | 6. Transactions and workflow | Transaction history: Every state change is recorded with actor, timestamp, reason and correlation ID. | The full path of a transaction is retrievable for support. | Not started
RULE-001 | 7. Business rules manager | Rule definitions: Rules are declared with conditions and outcomes, validated on save. | An invalid rule is refused at authoring time, not at evaluation time. | Not started
RULE-002 | 7. Business rules manager | Rule versioning: Rule sets are versioned and immutable once published. | A past decision replays against the exact version that produced it. | Not started
RULE-003 | 7. Business rules manager | Evaluation: Rules evaluate against a declared input schema and return a decision plus the matched rule. | The same inputs and version always yield the same outcome. | Not started
RULE-004 | 7. Business rules manager | Tenant scoping: Rule sets are tenant-scoped with optional platform defaults. | One tenant's rules never influence another's decision. | Not started
RULE-005 | 7. Business rules manager | Simulation: A rule set is testable against sample inputs before publication. | A dry run produces the decision without side effects. | Not started
RULE-006 | 7. Business rules manager | Decision audit: Every evaluation records inputs, version, matched rule and outcome. | A disputed decision is explainable after the fact. | Not started
SCORE-001 | 8. Scoring engines | Score definitions: A score is declared with its inputs, computation, scale and refresh policy. | A new score is added through configuration. | Not started
SCORE-002 | 8. Scoring engines | Score computation: Scores compute on demand or on a schedule and are stored with the version that produced them. | A recomputation with the same inputs and version reproduces the score. | Not started
SCORE-003 | 8. Scoring engines | Leaderboards: Leaderboards rank entities within a tenant with configurable window and tie-breaking. | Ranking is deterministic and paginated; ties resolve consistently. | Not started
SCORE-004 | 8. Scoring engines | Tenant isolation: A leaderboard never includes another tenant's entities. | A cross-tenant probe returns nothing. | Not started
SCORE-005 | 8. Scoring engines | Score history: Score changes are retained so movement over time is reportable. | A score's trajectory is retrievable for a given entity. | Not started
NOTI-001 | 9. Notifications | Channel-neutral service: Modules submit a notification intent; adapters deliver it. | Swapping a provider changes no domain module code. | Not started
NOTI-002 | 9. Notifications | Templates: Versioned templates carry subject, body, variables, locale, tenant override and preview, rendered in a sandboxed engine. | A missing or unsafe variable fails validation before send. | Not started
NOTI-003 | 9. Notifications | In-app inbox: An inbox with unread count, read state, category and deep-link metadata backs a bell icon in the UI. | A user sees only notifications addressed to them; the badge clears on read. | Not started
NOTI-004 | 9. Notifications | Email: Email delivers through a configured provider, with a local capture adapter for development. | Local startup sends no real email and exposes test deliveries. | Not started
NOTI-005 | 9. Notifications | SMS: SMS delivers through a provider adapter with opt-out and suppression handling. | A suppressed recipient is never contacted. | Not started
NOTI-006 | 9. Notifications | Push (FCM): Device tokens register per user and device; push delivers through FCM. | An invalid token is disabled after provider feedback. | Not started
NOTI-007 | 9. Notifications | Preferences and quiet hours: User preferences, mandatory transactional categories, quiet hours and tenant policy are respected. | Optional notifications honour consent while security messages still deliver. | Not started
NOTI-008 | 9. Notifications | Delivery tracking: Queued, sent, delivered, failed, bounced and suppressed states are tracked with provider message IDs. | Support traces an attempt without exposing message contents. | Not started
NOTI-009 | 9. Notifications | Retry and dead-letter: Transient failures retry with backoff; exhausted deliveries dead-letter. | A retry creates no duplicate in-app record or duplicate provider send. | Not started
SUP-001 | 10. Support requests | Ticket lifecycle: Tickets move through open, in progress, waiting on customer, resolved and closed. | Only valid transitions are accepted and each is audited. | Not started
SUP-002 | 10. Support requests | Threaded messages: Tickets carry a message thread with attachments and internal notes. | An internal note is never visible to the customer. | Not started
SUP-003 | 10. Support requests | Assignment: Tickets assign to an agent or queue with priority and due date. | Reassignment is recorded with actor and reason. | Not started
SUP-004 | 10. Support requests | Tenant and role visibility: A customer sees their own tickets; a reseller sees their customers'; staff see their scope. | A cross-tenant or cross-reseller ticket read is refused. | Not started
SUP-005 | 10. Support requests | Notifications: Ticket events raise notifications through the notification service. | A reply notifies the counterparty on their preferred channel. | Not started
REP-001 | 11. Reports and dashboards | Report registry: Reports are registered with a stable identifier, permission, parameter schema, result schema and data source. | An unknown or unauthorized report cannot be executed. | Not started
REP-002 | 11. Reports and dashboards | JSON-defined queries: Report queries are declared as validated JSON against an allowlisted field and operator set. | A raw database expression, JavaScript or unrestricted projection is rejected. | Not started
REP-003 | 11. Reports and dashboards | Dashboard metrics: Dashboard endpoints accept tenant, date range and organization-unit filters. | Every aggregation receives an enforced tenant filter. | Not started
REP-004 | 11. Reports and dashboards | Saved views: Users and tenants save report views, filters and column selections. | A saved view cannot reference a disallowed field, including after the allowlist changes. | Not started
REP-005 | 11. Reports and dashboards | Exports: Large reports export asynchronously to object storage with a time-limited download. | The API returns a job identifier and the download expires. | Not started
REP-006 | 11. Reports and dashboards | Scheduled reports: Reports schedule with recipient, channel, tenant time zone and retention. | Schedules are idempotent and re-check recipient permissions at execution time. | Not started
REP-007 | 11. Reports and dashboards | Report audit: Execution records requester, filters, duration, row count and export access. | Administrative usage and performance are analysable. | Not started
INT-001 | 12. External integrations manager | Integration registry: Integrations are registered with a type, configuration schema and required permissions. | An unknown integration type cannot be configured. | Not started
INT-002 | 12. External integrations manager | Credential references: Integration credentials are stored as secret references, never plaintext, and are write-only through the API. | No API response or log ever contains a credential value. | Not started
INT-003 | 12. External integrations manager | Connection testing: A connection test returns sanitised diagnostics. | The test confirms connectivity without persisting or exposing a secret. | Not started
INT-004 | 12. External integrations manager | Outbound webhooks: Tenants subscribe to events and receive signed deliveries with retry, replay and delivery history. | A consumer verifies the signature; a replay creates no duplicate effect. | Not started
INT-005 | 12. External integrations manager | Inbound webhooks: Inbound webhooks verify signatures against the raw body and deduplicate on provider event id. | An altered payload is rejected before processing. | Not started
INT-006 | 12. External integrations manager | API keys: Tenant API keys carry hashed secrets, scopes, expiry, last-used timestamp and rotation. | The full key is shown once and cannot be recovered afterwards. | Not started
INT-007 | 12. External integrations manager | Rate limiting: Per-IP, per-user, per-tenant and per-key rate limits apply where relevant. | A rate-limited response carries a stable code and retry metadata. | Not started
AUD-001 | 13. Audit | Append-only events: Audit events record authentication, authorization, administration, data change, billing, payment and security actions. | Audit records cannot be updated or deleted through any application path. | Not started
AUD-002 | 13. Audit | Event context: Each event captures tenant, scope, actor, action, entity, timestamp, correlation ID, source, reason and sanitised before and after values. | Every sensitive mutation has enough context to investigate. | Not started
AUD-003 | 13. Audit | Redaction: Secrets, tokens, password hashes, payment signatures and configured sensitive fields are redacted. | A test asserts a known secret value never appears in a stored audit document. | Not started
AUD-004 | 13. Audit | Activity timelines: Entity timelines derive from authorized audit events. | A user sees only events for records they can access. | Not started
AUD-005 | 13. Audit | Retention and archive: Retention is configurable; archived batches are hash-chained to object storage. | Tampering with or removing an archived batch is detectable. | Not started
AUD-006 | 13. Audit | Privileged reads: Privileged reads and exports are recorded, not only writes. | A sensitive export is attributable to a user and a request. | Not started
OBS-001 | 14. Observability (OpenTelemetry) | Structured logs: Logs are structured JSON carrying timestamp, level, service, environment, correlation ID, tenant and a safe actor identifier, with PII and secrets redacted. | A log scan finds no configured sensitive pattern. | Not started
OBS-002 | 14. Observability (OpenTelemetry) | Tracing: OpenTelemetry instruments API, database, queue and outbound provider calls, starting before instrumented libraries are imported. | A sampled request shows the complete distributed path in the trace backend. | Not started
OBS-003 | 14. Observability (OpenTelemetry) | Metrics: Metrics cover request latency and error rate, dependency health, queue age and failures, provider failures and billing runs. | A scrape endpoint serves them and alert thresholds are documented. | Not started
OBS-004 | 14. Observability (OpenTelemetry) | Health endpoints: Liveness, readiness and dependency health are exposed without leaking internals. | An orchestrator distinguishes alive, ready and degraded. | Not started
OBS-005 | 14. Observability (OpenTelemetry) | Trace correlation: The correlation ID appears in logs, traces and audit events for the same request. | One identifier joins a log line, a trace and an audit record. | Not started
WEB-001 | 15. Frontend (Next.js) | Authentication UI: Google sign-in and mobile OTP flows, including the OTP entry and resend path. | A browser test completes both flows against a real backend. | Not started
WEB-002 | 15. Frontend (Next.js) | Role-aware navigation: Menus and actions render from effective permissions. | A low-privilege user does not see an action they cannot perform, and forging the hint still fails server-side. | Not started
WEB-003 | 15. Frontend (Next.js) | Tenant and hierarchy selection: Users switch tenant and organization unit; visible data follows. | Switching changes the data set; a unit scope excludes sibling units. | Not started
WEB-004 | 15. Frontend (Next.js) | Configurable CRUD screens: List, search, filter, bulk select and detail screens driven by module metadata. | A new module gains screens without bespoke UI code. | Not started
WEB-005 | 15. Frontend (Next.js) | Dashboards and reports: Charts and tables render from report endpoints with saved views. | A report renders from live API data, not fixtures. | Not started
WEB-006 | 15. Frontend (Next.js) | Notification bell: A bell icon shows unread count and opens the in-app inbox. | The badge reflects server state and clears on read. | Not started
WEB-007 | 15. Frontend (Next.js) | Billing screens: Plan, subscription, usage, invoices and refund requests. | A quota refusal is shown to the user with the reason, not failed silently. | Not started
WEB-008 | 15. Frontend (Next.js) | Support screens: Ticket creation, thread and status. | A customer sees only their own tickets. | Not started
OPS-001 | 16. Delivery and operations | Single application image: Next.js and NestJS build into one image, started by a process supervisor, configured entirely by environment variables. | docker run with a database URL starts a working application. | Not started
OPS-002 | 16. Delivery and operations | External database: MongoDB runs outside the image as a replica set, since transactions back the outbox and idempotency. | Replacing the container loses no data; a standalone mongod is refused at startup. | Not started
OPS-003 | 16. Delivery and operations | Configuration validation: Configuration is validated against a versioned schema before startup, with production guards for transport encryption, real providers and secret references. | An invalid or unsafe production configuration fails fast with an actionable report. | Not started
OPS-004 | 16. Delivery and operations | Local development stack: Compose brings up the database, cache, object storage and a mail capture service. | A clean machine starts the stack with one documented command. | Not started
OPS-005 | 16. Delivery and operations | Migrations and seed: Schema and index migrations are versioned, idempotent and support a dry run; seed data creates demo accounts safely. | Running migrations twice is a no-op; seed refuses to run in production. | Not started
OPS-006 | 16. Delivery and operations | Graceful shutdown: Requests drain and in-flight jobs complete or return to the queue on shutdown. | A restart corrupts no write and loses no acknowledged job. | Not started
OPS-007 | 16. Delivery and operations | Backup and restore: Backup configuration and a documented restore path exist and are tested. | A test backup restores and verifies in a non-production environment. | Not started
SEC-001 | 16. Delivery and operations | Transport and headers: Secure headers, CORS allowlist, payload limits and injection protection are enforced; TLS is required in deployed environments. | Security tests cover injection and request manipulation; production refuses insecure endpoints. | Not started
SEC-002 | 16. Delivery and operations | Dependency and secret scanning: CI runs dependency, secret and container scanning and blocks on critical findings. | The build produces a clear pass or fail, and an allowlist entry never disables detection elsewhere. | Not started
QA-001 | 16. Delivery and operations | Automated suites: Unit, integration against real containerised dependencies, API contract, tenant-isolation, security and browser end-to-end suites. | All suites run in CI on every change. | Not started
QA-002 | 16. Delivery and operations | Definition of done: A clean clone installs, builds, type-checks, tests, generates its API client without drift and passes CI. | The remote revision and the locally verified revision match. | Not started

## Summary
Phase | Tasks | S | M | L
0. Setup | 4 | 1 | 3 | 0
1. Foundation | 10 | 3 | 5 | 2
2. Identity | 7 | 1 | 5 | 1
3. Access control | 7 | 0 | 5 | 2
4. Audit and observability | 6 | 1 | 4 | 1
5. Billing | 11 | 1 | 8 | 2
6. Notifications | 8 | 1 | 7 | 0
7. Transactions | 6 | 0 | 5 | 1
8. Rules and scoring | 6 | 1 | 3 | 2
9. Reporting | 7 | 1 | 5 | 1
10. Integrations | 6 | 0 | 5 | 1
11. Support | 5 | 2 | 3 | 0
12. Frontend | 9 | 0 | 5 | 4
13. Hardening | 7 | 1 | 4 | 2
Total tasks | 99
Total requirements | 122
Size key | S = up to ~1 day, M = ~2-4 days, L = ~1 week or more
Estimates assume one engineer familiar with the stack.