## Summary
VisaReady × SaaS Boilerplate — features requiring code beyond the boilerplate
Assumption: web only; roles customer / admin / agency / superadmin on one login URL. Generated 10 Aug 2026 from the three PRDs in visaready2/Req (Customer v5.0, Admin v1.1, Agency v1.1 + amendment sheet).
Bucket | Items | Share of total build effort | Meaning
Covered by boilerplate (config/data only) | — | ~50% | Auth, RBAC (4 roles map to seeded roles; agency = reseller scope), sessions, billing/plans/payments/refunds, entitlements & token quotas, rules & scoring engines with simulation, notification templates/channels, support, audit, reports engine, ops/CI. Not listed below.
Custom — from scratch | 20 | ~35% | No boilerplate counterpart — new product code.
Custom — framework-accelerated | 13 | ~15% | New code, but riding boilerplate frameworks (CRUD/screens/reports/workflow) at roughly half normal effort.

## Pending features
# | Feature | Source (PRD § / screen) | Roles affected | Category | Why the boilerplate cannot cover it as-is | What it CAN lean on | Effort (S/M/L)
1 | 6-step guided assessment flow (Steps 1–6 UI + domain model) | Customer 4.7–4.12 | Customer, Agency (on behalf) | Custom — from scratch | The visa-application entity, step routing, resume/save state and all step screens are client-specific domain work (explicitly out of boilerplate scope). | CRUD base schema/services, custom-field validation, workflow engine for application lifecycle. | L
2 | Agency code generation / re-generation & attribution mapping | Admin AD-12, Agency §8, Customer 4.13 | All | Custom — from scratch | The 6-digit agency code lifecycle and application→agency attribution are new; visibility isolation itself is covered by reseller scoping. | RBAC-004 reseller isolation enforces who sees what. | M
3 | Agency registration + KYC document submission & verification workflow | Agency Screens 1–2, Admin AD-06/07 | Agency, Admin | Custom — from scratch | Agency entity with KYC states (pending/active/suspended/blacklisted), document review and approval workflow is a new domain module. | CRUD foundation, workflow engine, reseller-scoped RBAC for visibility. | M
4 | Automatic flags & warnings surfaced inline during the flow | Customer 4.20 | Customer, Agency | Custom — from scratch | The inline UX and flag taxonomy are new; only evaluation mechanics come from the rules engine. | Rules engine. | M
5 | Bank-statement analysis & fund-parking flag rules | Admin AD-32, Ext-API #3 | Admin, Customer | Custom — from scratch | Statement parsing/classification is new; only the resulting flags can be expressed as rule-engine rules. | Rules engine (RULE-*) evaluates the extracted signals. | L
6 | Co-applicant / family management | Customer 4.7a | Customer, Agency | Custom — from scratch | Linked-applicant modelling, per-member passports/documents and shared application state are new domain logic. | CRUD foundation for the entities. | M
7 | Document checklist engine + intelligent upload organisation | Customer 4.14, Admin AD-34 | Customer, Agency, Admin | Custom — from scratch | Checklist resolution per (country, visa type, user type), completeness tracking and upload classification/flags are new. | Object-storage config, CRUD screens for the checklist CMS entity. | L
8 | Dynamic form field & range configuration driving the runtime forms | Admin AD-26 | Admin → Customer/Agency | Custom — from scratch | Custom-field definitions exist as code-config; an ADMIN-EDITABLE field/range registry that re-renders the customer forms at runtime is a new layer. | Custom-field validation machinery (CRUD-007) underneath. | L
9 | Lead management & routing (customer-entered codes, admin allocation) | Admin AD-08, Agency Screen 16 | Admin, Agency | Custom — from scratch | Lead entity, allocation rules and routing notifications are new. | CRUD screens, notifications, reseller scoping. | M
10 | Passport OCR scan & auto-fill | Customer 4.7 (Step 1), Ext-API #3 | Customer, Agency | Custom — from scratch | OCR/document-intelligence has no counterpart in the boilerplate; provider integration, parsing, confidence handling and form auto-fill are new. | Integrations manager for credential storage and connection tests only. | L
11 | Promo code generation, allocation, distribution & redemption tracking | Admin AD-62, Agency §6 | Admin, Agency, Customer | Custom — from scratch | No coupon/promo concept exists; generation, per-agency allocation, email distribution, redemption and tracking are new. Only invoice-level discounts exist (BILL-005). | Notifications for delivery; billing to apply the discount. | M
12 | Score improvement recommendations & reason codes content | Customer 4.16a, Admin AD-35 | Customer, Admin | Custom — from scratch | Mapping rule outcomes to personalised improvement guidance is new logic + content; reason-code CMS entity is new. | Rules engine outcomes drive it; CRUD screens for the CMS entity. | M
13 | VisaMatrix™ multi-page PDF report (sections, QR verification, watermark, co-branding) | Customer 4.16, Admin AD-65 | All | Custom — from scratch | The boilerplate exports report DATA asynchronously; a designed, branded, multi-page PDF document with section toggles and QR verification is a new generator. | Async export/job machinery and object storage for the artifact. | L
14 | WhatsApp Business API integration (outreach links, status notifications, report sharing) | Customer 3, Agency Screen 7, Ext-API #2 | Customer, Agency | Custom — from scratch | WhatsApp is not one of the four boilerplate channels; a new channel adapter plus template approvals are required. | Channel-neutral notification service accepts a new adapter without domain changes. | M
15 | WhatsApp conversational assessment bot + web hand-off deep link | Customer 3 | Customer | Custom — from scratch | A stateful conversational flow mapping chat answers into application steps is entirely new. (Drops out if scope stays strictly web.) | Assessment domain model shared with the web flow. | L
16 | Agency branding (logo upload, top-bar rules, report co-branding) | Agency Screens 12, §7; Admin AD-65 | Agency | Custom — from scratch | Tenant/agency theming and report co-branding have no boilerplate counterpart. | Object storage for assets. | S
17 | Application conclusion / outcome capture + review-link prompt | Customer 4.17, Amendment s-1 | Customer | Custom — from scratch | Outcome taxonomy (approved/rejected/withdrawn), embassy-outcome capture and the review prompt are new. | Workflow engine records the state transitions. | S
18 | Email OTP sign-in (primary customer login) | Customer 4.3 | All | Custom — from scratch | Boilerplate auth is Google + mobile OTP via Firebase; a 4-digit email OTP issuance/verification path is a new identity-provider extension. | Provider abstraction (AUTH-007) makes it a contained plug-in; sessions/accounts unchanged. | S
19 | GSTIN / PAN validation | Agency Screen 1, Ext-API note | Agency | Custom — from scratch | Format validation is trivial; a live verification API (if client opts in) is a new integration. | Integrations manager for credentials. | S
20 | Maintenance mode toggle + branded 403/maintenance pages | Admin AD-69/70 | Admin | Custom — from scratch | A platform-wide maintenance switch is a small new middleware + config surface. | Config validation, health endpoints. | S
21 | Agency credit wallet presentation & recharge packages | Agency Screens 8–9 | Agency | Custom — framework-accelerated | Wallet semantics map onto entitlements/usage/quotas and Razorpay payments; the package catalogue and wallet UX are the new part. | BILL-003/004, TXN-005, payments controller end-to-end. | M
22 | Content CMS entities: country requirements, FAQ, cover letters & itineraries, library, legal | Admin AD-33/36/41/63/64, Customer 4.19 | Admin, Customer | Custom — framework-accelerated | Each is a shallow CRUD content entity plus a customer-facing read screen; no CMS exists but the CRUD framework makes these schema+metadata work. | CRUD foundation + metadata screens. | M
23 | Country rules, risk rules & weightage configuration UI | Admin AD-24/25, AD-30/31, AD-39 | Admin | Custom — framework-accelerated | Evaluation, versioning and simulation are covered by the rules engine; a friendlier authoring UI than the JSON inspector is the new part. | RULE-001..006 end-to-end incl. simulate. | M
24 | Customer home dashboard & profile sub-screens (passport/address/travel preferences) | Customer 4.5–4.6 | Customer | Custom — framework-accelerated | Customer-specific layout and profile sections beyond the generic user profile. | Session, users module, settings/notification-preferences screens already exist. | M
25 | Fill / continue an application on the client's behalf (shared record) | Agency §4, Screens 5–7 | Agency | Custom — framework-accelerated | Same assessment domain as the customer flow, exercised by an agency actor against the shared record; permission toggles map to sub-user grants. | Org-unit memberships + granular permissions (sub-users) fully covered. | M
26 | Scoring weights configuration & Lite-vs-Final modes | Admin AD-27/28 | Admin | Custom — framework-accelerated | Two score definitions and their weights are ENGINE CONFIG; an admin authoring UI is the new part. Simulation (AD-29) already exists. | SCORE-001..005 + score simulation route. | M
27 | VisaReady-specific analytics (approval trends, platform KPIs, revenue analytics) | Admin AD-04/05, AD-37/38/40 | Admin | Custom — framework-accelerated | Each analytic is a registered report definition + dashboard config; the engine, saved views, exports and scheduling are covered. | REP-001..007 + dashboards. | M
28 | Application status override with reason | Admin AD-19 | Admin | Custom — framework-accelerated | Thin admin action over the workflow engine's transition machinery on the (new) application entity. | TXN-003/007 transitions + audit. | S
29 | Countries & visa types configuration | Admin AD-20–23 | Admin | Custom — framework-accelerated | Plain CRUD entities (country, visa type, embassy URL); new schemas + metadata screens only. | CRUD-001/002 + WEB-004 metadata-driven screens. | S
30 | Onboarding carousel + splash routing + consent versioning screens | Customer 4.1–4.4 | Customer | Custom — framework-accelerated | Simple bespoke screens and a consent-acceptance record; content is admin-editable. | Auth/session routing, legal-content CMS entity via CRUD. | S
31 | Per-report token pricing hooks (2 free regenerations, 3rd paid) | Customer 4.15/4.16, Agency §5 | Customer, Agency | Custom — framework-accelerated | Transaction pricing hook and regeneration counter are thin config/code on the transaction engine. | TXN-001/005 pricing hook + entitlements. | S
32 | Share report via WhatsApp / email / link | Customer 4.16 | Customer, Agency | Custom — framework-accelerated | Share-link tokens and channel hand-offs are thin new code. | Notification channels (email), WhatsApp adapter (separate row), signed URLs. | S
33 | User-facing reports list (My VisaMatrix reports) | Customer 4.18 | Customer | Custom — framework-accelerated | List of generated report artifacts with share/download; artifact index is new, plumbing is not. | Export/object-storage machinery, time-limited downloads. | S